## PublicDataReport
Collection Period | Department/ Agency Name | Agency Short Name | Project ID | Project Title | Government Domain | ICT Project Category | Description | Stage | Benefit Category ( Benefit Type) | Date of Closure/ Postponement | PM Methodologies | Initiation Start Date | Planned Initiation End Date | Revised Initiation End Date | Business Case Approval Date | Planned Initiation Cost | Revised initiation Cost | Planned Delivery Start Date | Revised Delivery Start Date | Planned Delivery End Date | Revised Delivery End Date | Planned Delivery Cost | Revised Delivery Cost | Q3 24-25 | Q4 24-25 | Q1 25-26 | Q2 25-26 | Q3 25-26 (Current) | Reporting Comments
Q3 25-26 | Country Fire Authority | CFA | 2151 | CFA Mobile Data Capability and Short Status Messaging (SSM) | Emergencies and Safety | Communication | Development and deployment of the Mobility Data Capability (MDC) platform. Incorporating Short Status Messaging will deliver operational efficiency and safety benefits to members and the community. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2026-03-25 | PRINCE2 | 2010-10-01 | 2012-07-01 | 2020-06-30 | 2020-07-01 | 0 | 45000 | 2020-07-01 |  | 2021-06-30 | 2027-06-30 | 2850000 |  | Amber | Amber | Amber | Amber | Green | The Mobile Data Capability (MDC) scope is completed, with 925 MDC tablets delivered. The completion of this lays the foundation for the future integration of the Short Status Messaging (SSM) component into a broader technology upgrade across the emergency sector. The integration activities will be delivered through a separate, future project.
Q3 25-26 | Court Services Victoria | CSV | 2452 | Courts Case Management System | Law and Justice | Tracking and Workflow | The CMS Project aims to procure and implement a new case management system for Magistrates’ Court and Children’s Court. The system will enable better information sharing between courts and other agencies, and provide better access to case information | Delivery | Efficiency/Productivity (Non Financial) |  | Project Management Excellence (PME) | 2016-07-01 | 2017-05-02 |  | 2017-05-02 | 0 |  | 2017-07-01 |  | 2022-06-30 | 2026-06-30 | 89200000 | 158650000 | Red | Red | Amber | Amber | Amber | Criminal release delivery and readiness activities continue, with go-live timing to be confirmed following governance endorsement of readiness.
Q3 25-26 | V/Line Corporation | V/Line | 2490 | Workforce management | Transport and Vehicles | Human Capital / Workforce Management | The Workforce management project will streamline the workforce management function and deliver an electronic rostering system that support V/Line to ensure it is able to meet daily staffing challenges to provide punctual and reliable train services | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-01-18 | 2018-02-28 | 2023-04-28 | 2023-05-01 | 250000 | 690251 | 2023-05-31 |  | 2026-07-31 | 2026-12-31 | 9680463 | 9992358 | Green | Green | Green | Green | Green | The overall health of the Project is on-track.
Q3 25-26 | South West Alliance of Rural Health | SWARH | 2597 | Barwon Health Rostering Project | Health | Management of Process ,Human Capital / Workforce Management ,Human Resources | This project will deliver a Rostering and Time & Attendance system to automate staff rostering processes, improving workforce utilisation, accuracy of resource allocation and delivery of patient care. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2017-07-19 | 2018-05-31 |  | 2018-06-08 | 110640 |  | 2018-07-11 |  | 2019-12-31 | 2026-06-30 | 3443281 | 4289360 | Amber | Red | Red | Red | Red | Delivery of the Rostering and Time & Attendance system continues with 7370 staff now live across 440 business units.
Q3 25-26 | Department of Justice and Community Safety | DJCS | 2851 | Digital Radio Upgrade Program - Stage 2 | Emergencies and Safety | Communication | This Program will transition Ambulance Victoria's (AV) regional comms off analogue radio system onto the State’s shared digital network and replace AV's regional radio fleet to provide secure comms and improve community safety and health outcomes. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2019-07-01 | 2019-07-02 |  | 2019-07-02 | 0 |  | 2019-07-03 |  | 2023-06-30 | 2027-04-30 | 70378000 | 117867000 | Green | Green | Green | Green | Green | The project schedule has been revised to accommodate new site approvals. The project is tracking well against scope, budget and the revised schedule.
Q3 25-26 | South West Alliance of Rural Health | SWARH | 3003 | Barwon Health Community Electronic Medical Record | Health | Content Management,Data Management,Forms Management,Management of Process ,Security Management ,Systems Management,Tracking and Workflow | Implementation of an Electronic Health Record (EHR) solution for community nursing and community mental health to replace legacy systems | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PMBoK | 2018-03-01 | 2020-10-01 | 2022-04-07 | 2022-04-07 | 0 | 0 | 2022-04-11 |  | 2023-08-28 | 2026-08-17 | 6074206 | 10879302 | Red | Red | Amber | Amber | Amber | The roll out of the Community Electronic Medical Record continues with the successful go live of Community Nursing. Post Acute Care, Social Support & Connected Care go live planning continues.
Q3 25-26 | Fire Rescue Victoria | FRV | 3030 | Rostering and Shift Change | Emergencies and Safety | Systems Management | Purchase and implement a contemporary off the shelf Rostering and Shift Change system to replace multiple legacy systems. | Delivery | Efficiency/Productivity (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-06-26 | 2020-12-08 | 2021-09-14 | 2021-09-14 | 0 |  | 2021-09-15 |  | 2022-11-02 | 2026-06-30 | 3760000 | 4349947 | Amber | Amber | Green | Green | Amber | The solution implementation for the shift changes and recall functionality for FRV Division A (metropolitan fire stations) went live in January 2026. The agreement for the remaining rostering requirements for full end to end rostering for FRV Division A is with stakeholders for approval, but is taking longer than planned. As a result, a review of the schedule, including the project end date, is underway. FRV Division B (regional fire stations) implementation is complete.
Q3 25-26 | Wannon Region Water Corporation | WAN Water | 3091 | Billing and Customer Relationship Management Systems | Environment and Water | Customer Relationship Management | The replacement of the organisation's Billing and Customer Relationship Management Systems | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2020-01-01 | 2021-03-31 | 2022-06-24 | 2022-06-24 | 100000 | 130000 | 2022-08-15 | 2023-01-03 | 2024-03-22 | 2026-06-30 | 8200000 | 20084484 | Amber | Amber | Green | Green | Green | The project reset is proceeding well with contract negotiations now underway.
Q3 25-26 | Goulburn Valley Region Water Corporation | GVR Water | 3130 | Billing and Customer Relationship Management System | Environment and Water | Customer Relationship Management | The project will replace Goulburn Valley Water's existing legacy billing and CRM systems with a modern, efficient and customer focused system | Initiated |  |  | Internal project management methodology | 2018-10-01 | 2021-06-30 | 2026-09-30 |  | 75000 | 487457 | [11 empty] | GVW has engaged a consultant to update and revise the Business Case and revisit the Sourcing Strategy for this project which is expected to be presented to The Board by 4th Quarter FY 25/26.
Q3 25-26 | Department of Justice and Community Safety | DJCS | 3168 | Post Sentence Authority Case Management System | Law and Justice | Tracking and Workflow | A case management system, crucial to sustainable operations and managing the risks associated with manual information flow, will be delivered. Real time information will be provided for informed decisions about offenders to uphold community safety. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2021-03-30 | 2021-07-15 | 2023-06-30 | 2023-06-30 | 150000 | 213455 | 2024-03-01 |  | 2025-12-31 | 2027-04-17 | 1878947 | 3274857 | Amber | Green | Green | Green | Green | Delivery activities for the latest iteration commenced in late January 2026. Since that time, the delivery schedule has been refined in partnership with relevant vendors, with the forecast completion date now revised to April 2027. Delivery is currently on schedule, and priorities are focused on integration with departmental systems to reduce double handling, improve staff efficiency, and lower operational risk associated with incorrect information. The project has undergone several iterative changes over the life of the project to ensure alignment with the overall organisational IT strategy and architecture. This resulted in multiple changes to schedule, scope, and budget.
Q3 25-26 | Department of Justice and Community Safety | DJCS | 3170 | Technology and resources to support Victoria’s fines system | Law and Justice | Systems Management | Delivery of next generation of fines platform by incrementally implementing functions into the business landscape to complement existing technology, ensuring better revenue collection, assistance for vulnerable Victorians and debtor-centric services. | Delivery | Customer Satisfaction (Non Financial), Increased Revenue (Financial) |  | Hybrid - Waterfall and Agile | 2021-03-10 | 2021-08-30 | 2021-12-16 | 2021-12-16 | 0 | 10367000 | 2022-01-09 | 2022-01-01 | 2025-06-30 | 2026-06-30 | 131615000 | 169961000 | Amber | Red | Red | Red | Red | The project is reporting a Red status due to schedule pressure and slower than anticipated delivery velocity. Previous adjustments to the program's delivery approach, including transitioning to shorter delivery cycles, has improved throughput. Following more detailed analysis on alternative delivery approaches, the project has identified a need for a schedule revision. A re-baseline is under review.
Q3 25-26 | Department of Justice and Community Safety | DJCS | 3171 | Better Technology Tools Enabling Responsibility (BTTER) | Law and Justice | Development and Integration | Deliver applications to automate processes, reduce costs and risks associated with existing manual systems for safety benefits. Prison management systems will be uplifted, and rehabilitation and reintegration services will be enhanced. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2020-07-21 | 2021-02-19 |  | 2021-02-19 | 324114 |  | 2021-02-22 |  | 2023-06-30 | 2029-06-30 | 18868800 | 46682876 | Green | Green | Green | Green | Green | The program is tracking well against budget schedule and scope. In Q4 2024-25, the delivery cost was revised from the planned $18.86m to $46.68m due to an increase in scope to facilitate the statewide deployment of the automation technology. The delivery end date was also revised from June 2025 to June 2029 to accommodate the additional scope
Q3 25-26 | Department of Government Services | DGS | 3199 | RTBA - Bond Management System Replacement | Community Services | Customer Relationship Management | This project will deliver an enhanced, updated solution to the Residential Tenancies Bond Authority legacy systems which are reaching end of life. The solution will ensure alignment to the business vision. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - Waterfall and Agile | 2021-04-12 | 2021-12-31 | 2021-12-31 | 2022-02-28 | 975000 | 1178280 | 2022-03-01 |  | 2023-06-30 | 2026-05-11 | 8900000 | 25030000 | Amber | Amber | Amber | Green | Green | BMSR implementation was completed successfully. Enhancements and continuous improvement activity is underway as user feedback is being collected. New portable bonds functionality is awaiting finalisation of go live - targeting June/July 2026.
Q3 25-26 | Melbourne Water | MELB Water | 3214 | Strategic Relationship Management Tool Phase 1-2 | Environment and Water | Collaboration | To enhance delivery of business goals by improvement in business capabilities and relationship management tools to allow ongoing management and continuity of relationships to achieve strategic improvements in organisational goals. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2020-11-25 | 2021-08-01 |  | 2021-11-04 | 0 |  | 2021-11-04 |  | 2022-06-28 | 2026-05-28 | 3174023 | 2260484 | Green | Green | Green | Red | Green | As at 20260331: Change Request has been approved for alignment of scope for core platform delivery, project to close in Q4.
Q3 25-26 | Fire Rescue Victoria | FRV | 3254 | FRV Operational Station Connectivity | Emergencies and Safety | Assets/Materials Management | The implementation of the FRV network and FRV Station Turn Out systems across ex CFA stations. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-09-01 | 2021-03-23 |  | 2021-03-23 | 0 |  | 2021-03-25 |  | 2023-06-30 | 2026-08-17 | 16689890 | 18418852 | Green | Amber | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q3 25-26 | Department of Health | DH | 3261 | Health Information Exchange (HIE) | Health | Data Management,Development and Integration | Deliver a Health Information Exchange for secure sharing of pathology information at the Point of Care, and to facilitate planning for increased scope/budget in subsequent years to cater for all key clinical domains for VPHS state-wide rollout. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-06-01 | 2021-06-30 |  | 2021-06-30 | 0 |  | 2021-07-01 |  | 2025-06-30 | 2026-06-30 | 27220000 | 34850442 | Red | Red | Red | Amber | Amber | Project roll out to expanded Health Services is progressing. Project is reporting an Amber status due to constraints in accessing required services, placing pressure on schedule.
Q3 25-26 | Peter MacCallum Cancer Centre | Peter MAC | 3278 | People and Payroll Transformation Program - Rostering Project | Health | Human Capital / Workforce Management ,Human Resources | The People Systems Program will deliver a Rostering solution which will increase efficiency and improve data security and integrity by eliminating paper time sheets and manual processes. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2021-09-01 | 2022-07-01 | 2023-08-02 | 2023-08-02 | 50000 | 500000 | 2023-08-03 |  | 2025-06-30 | 2027-06-30 | 6428267 | 11849537 | Green | Green | Green | Red | Red | System Integration Testing was paused to work through detailed configuration/integration solutions not originally part of the build design. Timeline currently being updated and confirmed for SIT re-start.
Q3 25-26 | Oral Health Victoria | OHV | 3280 | Electronic Oral Health Record (EoHR) | Health | Development and Integration | The Electronic Oral Health Record (EoHR) aims to replace and consolidate the legacy solution to deliver a single state-wide oral health record to support improved dental health outcomes in Victoria | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-04-01 | 2020-10-30 |  | 2020-10-30 | 390000 |  | 2021-09-22 |  | 2023-06-30 | 2027-06-30 | 9490000 |  | Amber | Amber | Amber | Amber | Amber | R2 planning and development of training and engagement plan has continued with the business and sector. Product development has commenced and recruitment of additional project resources was initiated.
Q3 25-26 | Department of Transport and Planning | DTP | 3312 | Smarter Roads Program - Timetable Systems Uplift | Transport and Vehicles | Content Management,Data Management,Systems Management | The objective of the project is to implement public transport timetabling solution for each mode which will improve business process and data accuracy, providing Victorian commuters consistent and timely information when using public transport. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-05-03 | 2021-12-30 | 2022-02-07 | 2022-02-07 | 0 |  | 2022-02-07 |  | 2023-03-31 | 2026-04-30 | 4739268 | 6716680 | Green | Amber | Red | Amber | Amber | The project status is reported as amber due to the delay against the initial schedule completion of end of September 2025. The project schedule has now been re-baselined and is now tracking completion against April 2026 end.
Q3 25-26 | Department of Transport and Planning | DTP | 3318 | Automatic Vehicle Monitoring Sustainment (AVMS) | Transport and Vehicles | Systems Management | Address key short-term challenges affecting Melbourne’s tram network through targeted initiatives to sustain the AVM system in the short-term while the Department continues to develop options for a future Tram Monitoring and Control (TMC) system. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PTV Investment Lifecycle | 2021-07-01 | 2022-04-29 | 2023-08-30 | 2023-08-30 | 1785000 | 0 | 2023-08-31 |  | 2025-06-30 | 2026-09-15 | 32018000 |  | Green | Green | Green | Green | Green | The AVMS On Board project is tracking well with the on-board tram installations of AVMS now extending across more than 90% of the E Class fleet.
Q3 25-26 | Fire Rescue Victoria | FRV | 3325 | Human Resources Information System (HRIS) | Emergencies and Safety | Human Resources | HRIS Project has the primary focus this year to address foundation data issues, collaborate with the Rostering and Shift Change project and build a business case for approval. Scope includes Payroll and HR | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | FRV Project Management Framework (PMF) | 2021-12-10 | 2022-06-30 | 2023-02-28 | 2023-02-28 | 0 | 0 | 2023-03-01 |  | 2025-03-01 | 2026-09-16 | 22392000 |  | Green | Amber | Red | Red | Red | Tender evaluation is complete. Funding is required from government to progress the project., resulting in a red cost status until the funding has been resolved.
Q3 25-26 | South West Alliance of Rural Health | SWARH | 3334 | Regional Electronic Health Record Upgrade (excluding Barwon Health) | Health | Customer Relationship Management,Data Management,Development and Integration ,Management of Process ,Records Management ,Systems Management,Tracking and Workflow | Upgrade to the regional Electronic Health Record (EHR) solution, that supports 11 health services across South West Victoria. The project will improve clinician and patient user experience, focusing on quality and safety of patient care. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-10-16 | 2022-03-31 | 2022-08-31 | 2022-09-01 | 180000 | 300000 | 2022-09-05 |  | 2025-06-30 | 2027-04-01 | 23495000 |  | Red | Green | Amber | Amber | Green | The project timelines have been revised by the SteerCo and the project is now on track.
Q3 25-26 | Melbourne Water | MELB Water | 3338 | Electronic Content Management Phase 1 | Environment and Water | Content Management | This project will upgrade Melbourne Waters current document storage repositories and migrate to a new Electronic Document and Records Management System (EDRMS) | Initiated |  |  | PMBoK | 2021-10-08 | 2022-09-22 | 2026-04-01 |  | 0 | [12 empty] | As at 20260331: Business Case under review.
Q3 25-26 | Victoria Police | VicPol | 3358 | Electronic Document and Records Management System | Law and Justice | Document Management | The overall objective of the project is to implement a fully integrated, enterprise-wide Electronic Document and Records Management Solution and an Enterprise Service Management platform to uplift information management maturity. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2020-11-25 | 2021-11-25 | 2024-12-31 | 2025-12-31 | 8559000 | 8559000 | Green | Green | Amber | Amber | Amber | The core objective of the business case has been achieved, with the Records365 delivered in March 2025, and the supporting solutions (DekkoSecure, and Automated Briefing and Correspondence), implemented in December 2025. Whilst the EDRMS project is effectively delivered, its status remains AMBER due to ongoing ingestion of data into Records365 and progressive roll out of the briefing product. This will be continued as part of the funded BAU support and iterative enhancement activity in 2026 to fully roll out the EDRMS capability organisation wide.
Q3 25-26 | Victoria Police | VicPol | 3359 | Finance Systems Program (Oracle Cloud) | Law and Justice | Investment Management | Delivery of a new financial system, updating technology and business processes across finance, purchasing and supply chain functions to increase efficiency and improve access to accurate information to support decision-making. | Postponed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) | 2026-03-31 | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2021-11-25 |  | 2025-06-30 |  | 32453000 |  | Red | Red | Red | Red | Red | The project has been paused pending validation of business requirements and integration and assessment against financial capacity.
Q3 25-26 | Victoria Police | VicPol | 3360 | Enterprise Rostering | Law and Justice | Human Capital / Workforce Management | The project will deliver an enterprise wide rostering and timesheet solution, consolidating disparate systems and manual processes into one integrated system to better support rostering and timesheet management. | Postponed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) | 2026-03-31 | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2020-11-25 | 2021-11-24 | 2024-12-31 | 2025-09-30 | 21490000 | 21490000 | Red | Red | Red | Red | Red | The project is currently POSTPONED pending validation of business requirements and integration and assessment against financial capacity. Path to Green includes approval to restart project activities development of a phased and integrated project delivery model approval of request for budget rephasing. Schedule can then be re-baselined with confirmed scope and project schedule dates beyond September 2025 per current schedule.
Q3 25-26 | Country Fire Authority | CFA | 3369 | CFA Radio Replacement Program | Emergencies and Safety | Communication | CFA’s current Tait 9100 series radios are no longer manufactured and are approaching the end of their practical life for operational purposes. These will be replaced across Victoria and will introduce a technology refresh with enhanced functionality. | Closed - Completed | Cost Avoidance (Financial), Risk Reduction (Non Financial) | 2026-03-31 | Project Management Excellence | 2021-07-01 | 2022-03-31 | 2022-03-31 | 2022-03-31 | 235465 | 235465 | 2022-04-01 |  | 2024-06-30 | 2025-12-31 | 138595535 | 136247000 | Green | Green | Green | Green | Green | The project has delivered all radios and the project is complete.
Q3 25-26 | Department of Government Services | DGS | 3377 | Digital Victoria Marketplace | Government and Economy | Collaboration ,Data Management,Records Management | The Marketplace is an initiative by Digital Victoria to provide a simpler, and easier way for Government and Industry to interact through the eServices register and various other SPC's. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-10-01 | 2021-10-13 |  | 2021-10-13 | 0 | 7708 | 2022-02-01 |  | 2027-06-30 |  | 16790000 |  | Green | Green | Green | Green | Green | The Digital Marketplace is meeting agreed timelines for releasing functionality into the production version of Digital Marketplace which aligns with the expected benefit delivery
Q3 25-26 | Alfred Care Group – Bayside Health | ALFRED Care Group | 3378 | Alfred Health / Monash Health - Shared Laboratory Information System | Health | Records Management | The shared LIS program will deliver a Laboratory information system as a foundational technology for the Alfred Monash Pathology partnership supporting the DoH Pathology sector reform initiative to consolidate pathology systems and services. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-10-05 | 2022-08-31 | 2023-02-28 | 2023-02-28 | 2000000 | 2000000 | 2023-02-28 |  | 2025-06-30 | 2026-06-30 | 25000000 | 41800000 | Red | Red | Amber | Amber | Amber | Amber status reflects fixed project timelines which caused some functionality to be descoped, and the management of solution defects. Appropriate mitigations are in place to limit impacts to clinical go-live. The solution go-live was completed as scheduled for Bayside Health - Alfred Care Group in January 2026, and for Western Health in February 2026. Monash Health go-live is scheduled for May 2026.
Q3 25-26 | Department of Transport and Planning | DTP | 3399 | Victraffic Upgrade Project | Transport and Vehicles | Communication,Customer Initiated Assistance,Customer Preferences | Objective of this project is to support transport users and emergency response units to safely and confidently move around our road network during an emergency situation and improve road closure capture and uplift the user experience. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-27 | 2022-09-19 | 2023-07-10 | 2023-07-10 | 0 |  | 2023-07-10 |  | 2024-06-30 | 2026-06-30 | 22637000 |  | Green | Green | Green | Green | Green | The overall status is green, and the project is on track with all implemented systems in the process of being transitioned to operations.
Q3 25-26 | Court Services Victoria | CSV | 3451 | Victorian Civil and Administrative Tribunal digital service transformation | Law and Justice | Content Management,Customer Initiated Assistance,Development and Integration ,Security Management ,Tracking and Workflow,Data Management,Document Management ,Forms Management,Knowledge Management ,Management of Process ,Records Management ,Routing and Scheduling | The project aims to upgrade digital services infrastructure including the case management system and increase process automation, to deliver more accessible and timely provision of justice to citizens and businesses | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - Waterfall and Agile | 2020-11-01 | 2021-02-04 |  | 2021-05-15 | 0 |  | 2021-07-01 | 2021-07-01 | 2024-12-01 | 2026-06-30 | 56681000 |  | Amber | Amber | Amber | Amber | Amber | With the go-live of Residential Tenancies and the Guardianship List in the last quarter, the project achieved all of its planned milestones. The completion of remaining milestones for these divisions of VCAT will mean over 90% of VCAT's caseload will be managed within the CMS.
Q3 25-26 | Victorian Institute of Forensic Mental Health (Forensicare) | Forensicare | 3458 | Human Capital Management (HCM) Rostering Payroll System | Health | Human Capital / Workforce Management ,Human Capital / Workforce Management | Forensicare is implementing a new Human Capital Management system to replace and integrate its ageing payroll, rostering and recruitment systems. This system will better meet staff needs and improve capacity for better care to growing customer base | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-08-23 | 2022-09-08 | 2023-12-11 | 2023-12-11 | 0 | 221000 | 2024-01-15 |  | 2025-09-30 | 2027-02-26 | 2580000 |  | Green | Amber | Amber | Green | Green | Pre-discovery and discovery (design) is underway and the project remain on track and Green and working toward the delivery of Phase 2. Note: The schedule revision is to incorporate Phase 2 delivery timeframe.
Q3 25-26 | V/Line Corporation | V/Line | 3465 | Payroll Improvements | Transport and Vehicles | Human Capital / Workforce Management | The objective of the payroll improvement project is to improve data collection for Leave, Time & Attendance information to support V/Line’s payroll function, in creating a more robust and consistent payroll operation organisation wide. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2023-03-31 | 2024-05-31 | 2024-05-31 | 0 | 500000 | 2024-06-03 | 2024-12-09 | 2025-09-30 | 2027-06-30 | 3300000 |  | Green | Green | Green | Green | Green | The project has completed development and testing of all payroll processing exception reports, which are now in active use by the payroll team. In parallel, work has progressed on establishing an enterprise Time and Attendance capability. Following a comprehensive market assessment, including a Request for Information process and completion of the Human Capital Management System tender, a preferred approach has been endorsed to meet organisation wide requirements. The selected Time and Attendance solution, procured through the Human Resource Information System (HRIS) project, will support effective and efficient alignment with the HR platforms.
Q3 25-26 | Central Highlands Region Water Corporation | CHR Water | 3466 | Digital Metering Program | Environment and Water | Customer Initiated Assistance,Customer Relationship Management | Replace analogue meters with digital, resulting in improved customer experience, reduced operational risk, improved environmental and sustainability footprint, and utilise water meter data to provide greater oversight of the water and sewer network. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Eco Improvement (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2020-07-01 | 2022-12-31 |  | 2023-01-02 | 0 |  | 2023-01-02 |  | 2026-09-30 | 2026-12-30 | 19500000 | 20708032 | Green | Green | Green | Green | Green | Project proceeding to stakeholder expectations
Q3 25-26 | Melbourne Health | Melb H | 3496 | Parkville Laboratory Information System (LIS) Program | Health | Management of Process ,Records Management ,Systems Management,Tracking and Workflow | The LIS Connect Program will procure and implement a single LIS solution for Pathology Network West across the Parkville precinct pathology services. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2022-03-01 | 2023-12-31 | 2024-07-31 | 2024-07-31 | 6047518 |  | 2024-09-23 |  | 2026-08-28 |  | 23817159 | 31572148 | Amber | Amber | Amber | Amber | Red | The program is tracking Red overall with key testing activities behind schedule. The Protected Industrial Action (PIA) is impacting resourcing and poses a material risk to the project schedule. A go-live delay and re-baseline may need to be considered if resource availability continues to decline.
Q3 25-26 | Department of Transport and Planning | DTP | 3497 | Victorian Transport Digital Engineering Transformation Program | Transport and Vehicles | Assets/Materials Management,Content Management,Data Management,Document Management ,Visualisation | Objective of this project is to develop a roadmap to progressively move to a digital environment for engineering, design and data management. DoT and MTIA will collectively deliver the DE Transformation, Horizon 1 -3 projects over the next 2-3 years. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-04 | 2022-12-30 | 2023-02-06 | 2023-02-06 | 0 |  | 2023-02-06 |  | 2023-12-29 | 2026-06-30 | 5135000 | 45000518 | Green | Amber | Amber | Amber | Amber | The program is reporting an amber status as it is experiencing resourcing risks and budget pressure on the pilots. Re-planning is ongoing to ensure value is obtained from these pilots. The build activities continue across all initiatives and are tracking relatively well.
Q3 25-26 | Fire Rescue Victoria | FRV | 3505 | Implementing Protective Marking and Information Protection | Emergencies and Safety | Data Management | Implementing processes for managing protective markings on official or higher classified content (documents and emails) in line with the Office of the Victorian Information Commissioner : Victorian Protective Data Security Standards. | Closed - Merged | Compliance (Non Financial), Risk Reduction (Non Financial) | 2026-01-31 | FRV Project Management Framework (PMF) | 2022-02-11 | 2022-06-30 |  | 2022-06-30 | 0 |  | 2022-07-01 |  | 2024-06-30 | 2026-06-30 | 1512000 |  | Green | Green | Green | Green | Green | The Implementing Protective Marking and Information Protection project has delivered a majority of the scope. However to optimise efficient delivery in Q3 2025-26 the project has been merged with the "Cyber Uplift Program". The remaining scope and functionality will be delivered through the new program.
Q3 25-26 | Peninsula Care Group – Bayside Health | PEN Care Group | 3522 | Peninsula Health NHCA Smart Ward | Health | Business Intelligence | National Centre for Healthy Aging (NCHA), a Monash University (MU) and Peninsula Health (PH) collaboration, has established a program of works that includes the establishment of a Smart Ward to collect patient observations for Research. | Delivery | Customer Satisfaction (Non Financial) |  | PRINCE2 | 2022-11-07 | 2023-01-31 | 2024-02-29 | 2024-03-07 | 0 | 19968 | 2024-03-07 |  | 2025-07-31 | 2026-04-30 | 1222641 | 1423459 | Green | Green | Green | Green | Green | The project is currently in hyper-care, handover to BAU documentation is complete, the project closure activities will be undertaken next period.
Q3 25-26 | Ambulance Victoria | AVS | 3547 | Cloud & Infrastructure Program | Health | Assets/Materials Management | The program will upgrade network infrastructure and address the closure of data centres and the end-of-life of data centre assets through migrating workloads to Cloud. This program will deliver improved security and performance for our services. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-04 | 2023-01-31 |  | 2023-01-31 | 341911 | 155621 | 2023-02-01 |  | 2025-11-28 | 2027-06-30 | 18295989 | 14522917 | Green | Green | Red | Red | Red | The project reported a red status due to project budget confirmation in progress. Delivery continues to progress well, with key systems and a major test environment transitioned in Q3. The project will be rebaselined once the budget is confirmed.
Q3 25-26 | Royal Children's Hospital | RCH | 3551 | Identity and Access Management (IDAM) | Health | Security Management | Implementation of new identity management solution | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2022-11-28 | 2023-06-02 | 2025-01-23 | 2025-01-23 | 0 |  | 2025-01-23 |  | 2025-12-31 | 2026-12-17 | 3368053 |  | Green | Green | Green | Green | Amber | The IDAM environment is currently being configured and undergoing testing activities. Integration with SAP and ServiceNow has been completed and is now in Test phase.
Q3 25-26 | Melbourne Water | MELB Water | 3557 | HR Modernisation | Environment and Water | Human Resources | Implement new Human Resources Information System (HRIS) technology to provide a sustainable, efficient and contemporary solution for people and payroll management, people performance and learning organisation goals. | Closed - Terminated | Compliance (Non Financial), Efficiency/Productivity (Non Financial) | 2026-03-31 | PMBoK | 2022-10-05 | 2023-08-31 | 2023-11-13 | 2023-12-13 | 0 |  | 2023-12-13 |  | 2024-11-19 | 2025-08-15 | 2722712 | 6892613 | Green | Red | Red | Green | Red | As at 20260331: Initiative to be closed. Project closure activities underway.
Q3 25-26 | Loddon Mallee Rural Health Alliance | LMRHA | 3563 | Regional integrated Electronic Patient Record | Health | Records Management | Delivery of an integrated Electronic Patient Record for members of the Loddon Mallee Rural Health Alliance (excluding Bendigo Health) - this will support more connected patient care for patients region wide. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-10-03 | 2023-06-30 | 2026-06-30 |  | 70000 | 0 | [11 empty] | Project scope and approach has been agreed to. Planning is progressing to confirm project schedule and cost prior to commencing project delivery. Project initiation end date has been extended to 30th June 2026.
Q3 25-26 | Loddon Mallee Rural Health Alliance | LMRHA | 3575 | Patient Administration System Replacement | Health | Data Management,Records Management ,Reporting | Replacement of Bendigo Health's current Patient Administration System (PAS) solution to align with the Electronic Patient Record (EPR) - moving to a single for both capabilities will ensure smoother patient care and support. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-06-06 | 2023-06-30 | 2023-09-30 | 2023-10-02 | 150231 |  | 2023-10-23 |  | 2025-07-15 | 2026-04-30 | 4930809 |  | Amber | Red | Amber | Amber | Amber | The project status is AMBER due to a number of activities overlapping to meet April Go Live, with key items being solution validation and data migration issue remediation.
Q3 25-26 | Department of Health | DH | 3599 | Mental Health and Wellbeing Website | Health | Communication | This project will deliver a mental health website, addressing recommendations 6.4 and 31.3 of the Royal Commission into Victoria's Mental Health System, to help Victorians navigate the mental health system and find relevant services and supports. | Postponed |  | 2023-06-30 | Agile | 2022-09-21 | 2023-05-12 | 2023-06-30 |  | 843493 | 1185694 |  |  |  |  | 0 | [6 empty] | Project on pause due to priority being given to other mental health and wellbeing initiatives.
Q3 25-26 | South West Alliance of Rural Health | SWARH | 3602 | HR Digital Solution | Health | Human Resources | The scope of the strategic HRIS is to replace the Health Services HR applications and manual, paper-based processes with a contemporary, fit-for-purpose, strategic HRIS solution. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2023-02-24 | 2023-10-27 | 2023-12-01 | 2023-12-01 | 834297 |  | 2024-01-15 |  | 2026-04-30 |  | 13629603 |  | Red | Red | Red | Red | Red | The project has been delayed due to data readiness and technical integration issues. A revised timeline and budget is under development.
Q3 25-26 | Central Highlands Region Water Corporation | CHR Water | 3612 | ERP Upgrade | Environment and Water | Assets/Materials Management,Financial Management,Human Capital / Workforce Management ,Supply Chain Management | This project will upgrade the existing platform(s) due to an impending end of support timeline with a contemporary integrated solution to improve the Finance, Procurement, Commercial and Asset Management processes of CHW | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-01-02 | 2023-06-30 | 2023-09-29 | 2023-09-29 | 0 |  | 2023-10-02 |  | 2025-09-30 | 2026-12-18 | 9510000 | 11910255 | Green | Green | Green | Green | Green | The project is tracking in line with stakeholder expectations
Q3 25-26 | Eastern Health | EH | 3638 | Enable Program | Health | Human Capital / Workforce Management ,Human Resources | Enable success of our people through 3 x HR systems projects: 1. Rostering Project - Replace RosterOn with Optima 2. People Journey Project - Replace eMercury with SAP SuccessFactors 3. Payroll Project - Replace SAP Payroll with SAP SuccessFactors | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-10-01 | 2023-03-31 |  | 2023-06-07 | 75000 |  | 2023-06-07 |  | 2025-10-31 | 2027-02-01 | 10148335 | 10592143 | Green | Green | Green | Green | Amber | The project report is amber due to the Vendor resourcing constraints. The project team has conducted workshops with the vendor to assess impact and reprioritise deliverables. The revised scope and schedule pending governance approval.
Q3 25-26 | WorkSafe Victoria | WorkSafe | 3642 | Digital Identity Uplift (Enterprise IDAM Uplift) | Employment, Skills and Workplace | Systems Management | Uplift the Digital Identity environment to ensure people have the right access to resources, at the right time. This will enhance the user experience and strengthen security controls. Project name was changed from Enterprise IDAM Uplift. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-02-01 | 2023-03-31 |  | 2023-04-04 | 0 |  | 2023-06-05 |  | 2025-06-30 | 2026-10-31 | 4316783 | 4224778 | Green | Red | Red | Green | Green | On track
Q3 25-26 | Grampians Rural Health Alliance | GRHA | 3645 | Maryborough Hospital Redevelopment ICT Project | Health | Development and Integration ,Systems Management | The Maryborough Hospital redevelopment ICT project provides infrastructure integration of clinical equipment mobile/desktop devices to support clinical care in the new state-of-the-art healthcare facility; improving care outcomes for patients. | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-12-01 | 2021-06-01 |  | 2021-06-01 | 0 |  | 2021-06-01 |  | 2025-06-30 | 2026-06-26 | 5158000 |  | Green | Green | Green | Green | Green | ICT equipment and systems operational in new hospital. Minor close out works still continuing with a planned completion for June 2026.
Q3 25-26 | Triple Zero Victoria | TZV | 3651 | Next Generation Computer Aided Dispatch System | Emergencies and Safety | Systems Management | Implement a new enhanced, reliable and secure emergency services Computer Aided Dispatch system to support enhanced critical emergency services 000 call taking and dispatch capability. | Delivery | Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-07-01 | 2024-11-27 | 2024-12-01 | 20588172 |  | 2024-12-02 |  | 2027-06-30 | 2028-06-30 | 233301093 |  | Green | Green | Green | Green | Amber | The project is tracking in accordance with overall scope and planned delivery cost. The project is reporting an amber status due to increased schedule risk, with risk mitigations required to manage delivery velocity and critical skill availability issues with vendors. There is no change to delivery timeframe of June 2028 for transition into operational service.
Q3 25-26 | Gippsland Health Alliance | GHA | 3654 | EMR Rural Expansion (Phase 4) | Health | Records Management | Expansion of EMR into 6 x Rural health services in the Gippsland Region | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial) |  | PMBoK | 2023-03-14 | 2023-11-30 | 2024-11-22 | 2024-11-22 | 200000 | 2675777 | 2025-03-12 |  | 2025-11-11 | 2026-04-30 | 3383375 | 5224223 |  | Green | Green | Green | Green | Primary project scope completed, on track to complete the consolidation project
Q3 25-26 | Northern Health | NH | 3666 | Patient Engagement/Entertainment System (PES) | Health | Communication | To provide patient TVs and other supported clinical workflows for better patient care at Northern Health | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-02 | 2021-12-31 |  | 2021-12-31 | 50000 |  | 2023-02-01 | 2023-08-01 | 2024-07-30 | 2026-10-31 | 3450000 |  | Green | Amber | Green | Green | Green | Project completion date adjusted following vendor's feedback.
Q3 25-26 | Queen Elizabeth Centre | QEC | 3667 | Client Information Management System | Health | Data Management,Document Management ,Forms Management,Management of Process ,Reporting | QEC is focused on developing a Client Information Management System (CIMS) that can accommodate growth diversity and emerging evidence; enable clinical implementation of the outcomes framework; and meet funding and reporting requirements. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-11-23 | 2023-10-18 | 2023-11-15 | 2023-11-29 | 225000 | 283153 | 2023-12-04 |  | 2025-12-30 | 2026-06-30 | 1314347 | 1413472 | Green | Green | Green | Green | Green | Project is tracking as expected.
Q3 25-26 | Grampians Rural Health Alliance | GRHA | 3688 | Ballarat Base Hospital Redevelopment - ICT Program - Stage 3 | Health | Systems Management | Stage 3 will deliver ICT systems to support the project works, improving patient and staff systems & support. | Delivery | Social Improvement (Non Financial) |  | PMBoK | 2022-01-03 | 2025-12-01 | 2026-02-27 | 2026-02-27 | 0 |  | 2026-02-27 |  | 2027-12-17 |  | 21370116 | [5 empty] | Green | 2 major ICT packages have been awarded and works have commenced. Remaining scoping & procurement activities will continue to occur though until late 2026.
Q3 25-26 | Hume Rural Health Alliance | HRHA | 3694 | ICT transition to Hume Rural Health Alliance (KDHS) | Health | Organisational Management | The project will transition Kyabram District Health Service (KDHS) ICT from Loddon Mallee Rural Health Alliance to Hume Rural Health Alliance to provide IT oversight and support. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-03-31 |  | 2024-04-24 | 100000 | 37000 | 2024-04-24 |  | 2025-06-30 | 2026-06-30 | 3463000 |  | Amber | Amber | Amber | Amber | Amber | The remaining scope under the KDHS ICT Transition Program comprises the Telephony upgrade and establishment of a Clinical Grade Network at the Stanhope site. An interim alternative connection has been proposed, with delivery expected in approximately two months. The Telephony project has completed its initial assessment of current telephony usage at KDHS. Implementation approach, timeline, and costs for Payroll and Time & Attendance remain under discussion and are yet to be confirmed.
Q3 25-26 | Grampians Rural Health Alliance | GRHA | 3695 | MDHS ICT transition to Grampians Rural Health Alliance | Health | Organisational Management | The project will transition Maryborough District Health Service from Loddon Mallee Rural Health Alliance to Grampians Rural Health Alliance to better align with natural patient flows in the region (improved patient experience ). | Delivery | Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-11-17 | 2025-04-01 | 2025-04-01 | 0 | 150000 | 2025-04-01 |  | 2026-12-31 | 2027-04-01 | 3450000 |  |  | Green | Green | Amber | Red | The project was temporarily paused in February 2026 due to concerns regarding project budget and scope as well as identification of change management risks. During the pause project stakeholders through Project Control Group (PCG) oversight progressed clarification of scope cost drivers and delivery dependencies. The project is now unpaused and active but remains Red due to unresolved timing of the critical-path dependencies. Detailed planning is progressing to confirm the timing of this activity.
Q3 25-26 | Loddon Mallee Rural Health Alliance | LMRHA | 3696 | HR Information System | Health | Human Capital / Workforce Management | Implementation of a Human Resources Information System (HRIS) for members of Loddon Mallee Rural Health Alliance -this uplift will enable resource planning and management visibility across the region. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-12-31 |  | 2023-12-31 | 65000 | 175000 | 2024-01-01 | 2025-08-28 | 2025-12-20 | 2027-06-30 | 13500000 |  | Amber | Amber | Amber | Amber | Green | Project progressing to timelines with progress on the design workbooks nearing completion. Change Impact Assessment is being conducted with an assessment of additional resources required to manage the change.
Q3 25-26 | Transport Accident Commission | TAC | 3698 | Digital Identity Uplift | Transport and Vehicles | Systems Management | Uplift the Digital Identity environment to ensure people have the right access to resources, at the right time. This will enhance the user experience and strengthen security controls. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-05-18 | 2023-05-18 |  | 2023-05-18 | 0 |  | 2023-06-05 |  | 2025-06-30 | 2026-10-31 | 4316783 |  | Green | Red | Red | Green | Green | Project is tracking to plan for Q3 FY25/26.
Q3 25-26 | V/Line Corporation | V/Line | 3699 | HRIS (Human Resources Information System)​ system replacement | Transport and Vehicles | Human Capital / Workforce Management ,Human Resources | To implement a new human resource information system for V/Line, in order to improve accuracy and reliability of HR data for service delivery. | Initiated |  |  | PRINCE2 | 2023-07-01 | 2024-11-29 | 2026-04-24 |  | 900000 | 1476107 | [11 empty] | The project has identified a preferred Human Capital Management solution and implementation partner, with contract negotiations and preparatory activities currently underway. The next phase of the project is scheduled to commence in Q1 of 2026–27 financial year. As part of the procurement process, the solution was also confirmed as suitable to support enterprise-wide Time and Attendance requirements. Work is now progressing to integrate the Payroll Improvement Project with the HRIS Modernisation program, enabling improved efficiency and enhanced business benefits.
Q3 25-26 | Department of Health | DH | 3731 | Managed Services Provider Replacement (MSPR) | Health | Data Management,Development and Integration | Replacement of the Managed Service Provider (MSP) for the Oracle Cloud Infrastructure tenancies to better support the departments operations. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2023-06-01 | 2023-06-30 |  | 2023-06-30 | 0 |  | 2023-07-01 |  | 2025-12-31 | 2026-05-31 | 1412500 | 1088061 | Red | Amber | Amber | Amber | Amber | Project is reporting an Amber health status due to earlier constraints in accessing the required services and responding to a large number of vendor inquiries placing pressure on schedule.
Q3 25-26 | Department of Health | DH | 3733 | St Vincent's Electronic Medical Record Project | Health | Analyses and Statistics ,Collaboration ,Communication,Forms Management,Organisational Management ,Records Management | Implementation of an electronic medical record (EMR) to streamline clinical documentation medication management and other clinical activities to support the provision of safer higher quality and more efficient patient care. | Initiated |  |  | PRINCE2 | 2023-09-01 | 2024-07-01 | 2026-06-01 |  | 0 | 3000000 | [11 empty] | The primary focus of the St Vincent's Hospital Melbourne Electronic Medical Record (EMR) project continues to be on procurement and contracting processes in collaboration with another Victorian health service. Organisational readiness tasks continue, noting the network uplift activities have now been completed.
Q3 25-26 | Lower Murray Urban and Rural Water Corporation | LMUR Water | 3749 | Technology Uplift Program (Formerly - Business Transformation Program) | Environment and Water | Customer Relationship Management,Data Management,Financial Management,Human Capital / Workforce Management ,Human Resources,Reporting ,Supply Chain Management | Enabling LMW of the Future. The program will uplift capabilities across key business functions, including customer service, billing, assets and workforce and financial management to enable improved customer service and efficiency.​ | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2024-02-02 | 2024-05-30 | 2024-05-31 | 899582 |  | 2024-06-03 |  | 2026-06-30 |  | 12100105 | 15524022 | Green | Green | Green | Green | Green | Scheduled activities are proceeding as planned with minimal/no impacts for this quarter.
Q3 25-26 | Department of Families, Fairness and Housing | DFFH | 3756 | Communities and Families Transformation - Stage 1 | Community Services | Customer Relationship Management | Deliver a business case with options for strategic investment in technology platforms, underpinning delivery of care services to communities and families, to enable seamless interactions and experience for our clients and sector partners. | Delivery | Social Improvement (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2022-08-15 | 2024-01-11 | 2023-01-11 | 2023-06-19 | 0 |  | 2023-07-01 |  | 2025-06-30 | 2026-06-30 | 14429000 | 16282000 | Green | Green | Green | Green | Green | The business case setting out multiple delivery options has been completed and submitted for consideration as part of the 2026–27 Budget process.
Q3 25-26 | Department of Transport and Planning | DTP | 3757 | Human Capital Management (HCM) Project - Phase 2 | Transport and Vehicles | Business Intelligence,Customer Initiated Assistance,Forms Management,Management of Process ,Tracking and Workflow | To lead the implementation of SAP SuccessFactors (including Payroll) for DTP . Program scope includes the changes required for the Machinery of Government (MoG) changes announced in December 2022. | Closed - Completed | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) | 2026-03-31 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-01 | 2023-06-30 |  | 2023-08-14 | 0 |  | 2023-08-14 |  | 2024-06-30 | 2025-12-31 | 7490000 | 15675000 | Amber | Amber | Green | Amber | Green | The program status is green. The delivery activities have been completed and closure activities are progressing well.
Q3 25-26 | Yarra Valley Water | YV Water | 3762 | Enterprise Analytics Platform - Phase 2 | Environment and Water | Data Management | Replacement of YVW's data warehouse, operational data-store and business intelligence reporting technologies with a modern, scalable data and analytics platform | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2023-09-01 | 2023-09-30 |  | 2023-09-30 | 0 |  | 2023-10-01 |  | 2025-04-28 | 2026-06-30 | 6640340 | 8243140 | Amber | Amber | Amber | Amber | Amber | The project is currently reporting an Amber status due to issues internally and with the vendor resulting in the need to go back out to market. The result has caused the original schedule and budget to be inadequate, with a change request for both expected.
Q3 25-26 | Melbourne Polytechnic | MelbPoly | 3767 | Melbourne Polytechnic Student Management System Implementation | Employment, Skills and Workplace | Systems Management | Selection and Implementation of new Student Management System for Melbourne Polytechnic to improve student and user experience, increase digitalisation and automation, and improve functionality and compliance. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-29 | 2023-12-31 |  | 2024-01-08 | 182000 |  | 2024-01-15 |  | 2027-01-29 | 2027-07-30 | 7818000 | 13258270 | Green | Green | Green | Green | Green | Key scope schedule and budget review conducted. Budget now reflects OTCD Grant and MP internal costs aligned to scope and schedule. Project progressing to revised plan and targets. Further stage gate review underway.
Q3 25-26 | Department of Transport and Planning | DTP | 3773 | Future Public Transport Ticketing System | Transport and Vehicles | Customer Initiated Assistance,Customer Preferences,Financial Management,Systems Management | The future Public Transport Ticketing (PTT) System will deliver modern customer payment features and progressively replace the current myki Ticketing System (myki System) | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-07-01 | 2021-10-18 |  | 2021-10-18 | 0 |  | 2021-10-18 |  | 2028-06-30 | 2028-12-31 | 543000000 | 680350000 | Green | Green | Green | Green | Green | The program is reporting an overall status as green. The program implementation activities are ongoing.
Q3 25-26 | Melbourne Water | MELB Water | 3807 | Network Resilience FY25-26 | Environment and Water | Assets/Materials Management | To continue investing in our IT network ensuring that we reduce the risk of unplanned network outages meet compliance requirements improve our security posture increase capacity reliability and bandwidth to accommodate future growth. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PMBoK | 2023-12-08 | 2024-02-27 |  | 2024-07-24 | 0 |  | 2024-07-24 | 2024-10-22 | 2026-06-22 | 2027-03-19 | 4966804 | 5128521 | Green | Red | Amber | Red | Amber | As at 20260331: Project scope and delivery approach under review as a result of increases in potential costs to complete.
Q3 25-26 | WorkSafe Victoria | WorkSafe | 3811 | Contact Centre Capability Uplift | Employment, Skills and Workplace | Communication | WorkSafe’s telephony system is built upon ageing infrastructure and tech. The introduction of a contact-centre-as-a-service will uplift person-centred services and ensure continuity for frontline support of injured workers & the Victorian community. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2022-01-01 | 2023-11-26 |  | 2023-12-11 | 441569 | 326274 | 2023-12-11 |  | 2025-12-31 | 2026-04-30 | 7321441 | 3867488 | Green | Green | Green | Green | Green | On track
Q3 25-26 | Grampians Rural Health Alliance | GRHA | 3812 | Grampian Health - Electronic Medical Record System | Health | Data Management | Implementation of an Electronic Medical Record system across five campuses of Grampians Health, namely Ballarat, Dimboola, Edenhope, Horsham, and Stawell. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-10-31 | 2028-06-30 | 2026-06-01 |  | 0 | [12 empty] | The Grampians Health Electronic Medical Record (EMR) project remains primarily focused on procurement and contracting activities undertaken in collaboration with another Victorian health service. Organisational readiness activities are continuing, including Network uplift, Data preparation, Stakeholder engagement, and the delivery of supporting infrastructure initiatives to ensure the clinical environment is prepared.
Q3 25-26 | Ports Victoria | PortsVic | 3824 | Port Management Information System (PMIS) Project | Transport and Vehicles | Routing and Scheduling | Implementation of a Port Management Information System (PMIS), directly supporting the management of maritime navigation and operational safety, providing safe, fair, and efficient access for the commercial ports of Melbourne, Geelong and Hastings. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-03 | 2024-12-20 | 2026-04-30 |  | 0 | 249990 | [11 empty] | The Blueprint and pre-contract readiness engagement experienced delivery delays and is on track to conclude at the end of March 2026. The resulting Blueprint and pre-contract readiness deliverables will underpin the implementation cost, scope and schedule. Due to delays, the final business case is re-scheduled for Governance Committee consideration in April 2026.
Q3 25-26 | Chisholm Institute of TAFE | Chisholm TAFE | 3825 | Chisholm Student Management System Transformation Project | Employment, Skills and Workplace | Records Management | The project will migrate legacy student management system to new technology offered by the existing vendor to minimize technology risk and maintain student experience and business continuity. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-01-09 | 2023-05-31 |  | 2023-05-31 | 0 |  | 2023-11-16 |  | 2026-09-25 | 2027-12-31 | 8000000 |  | Amber | Green | Green | Green | Amber | The project plan is being reviewed to support the design and build of complex functionality with strong ongoing consultation with the vendor ensuring all deliverables continue to progress. Go-live options are being considered.
Q3 25-26 | Department of Transport and Planning | DTP | 3828 | Trusted and Secure Program | Transport and Vehicles | Data Management,Security Management ,Systems Management | The objective of this program is to implement cyber and information security standards, enhancing information security measures and reducing risks of cyber incidents, by embedding robust and proactive cyber security practices. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2023-10-02 |  | 2023-10-02 | 0 |  | 2023-10-03 |  | 2024-06-30 | 2026-06-30 | 6800000 | 17334852 | Green | Amber | Amber | Amber | Green | The program status is reporting as green. The program remains on track with fourteen project streams completed and nine in progress.
Q3 25-26 | Austin Health | AH | 3837 | CRM Statewide Project | Health | Customer Relationship Management | Make five CRM modules available to all metropolitan and some regional health agencies, improving referral management and waitlist management, providing efficiencies and improved waiting lists. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-01 | 2023-12-22 |  | 2023-12-22 | 0 |  | 2024-01-02 |  | 2024-12-31 | 2026-06-30 | 4565000 | 9509070 | Green | Green | Green | Green | Green | - Deployed Module 1 at West Gippsland - Deployed Module 4 at Goulburn Valley Health - Deployed Module 2 at Grampians Health - Ballarat - Module 5 deployment halted due to lower uptake
Q3 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3839 | Biosciences Advanced Scientific Computing (BASC) Infrastructure Refresh Project | Government and Economy | Knowledge Discovery | The BASC Infrastructure Refresh project will deliver refreshed infrastructure to replace an end-of-life system that supports agricultural research. This project will be delivered in three phases over the next three years. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Eco Improvement (Non Financial), Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-09-25 | 2024-06-28 | 2024-12-31 | 2024-12-31 | 150000 | 399415 | 2025-01-01 |  | 2027-12-18 |  | 3675686 | 5836104 | Amber | Amber | Green | Green | Green | Phase 1 and 2 activities have been successfully completed. Note that the project budget reflects the Phase 1 & 2 budget only and will be incrementally adjusted based on the subsequent phase planned commitment.
Q3 25-26 | Barwon Region Water Corporation | BR Water | 3841 | C1430 - Network Segmentation | Environment and Water | Security Management | The Network Segmentation project will segregate and segment the operational and corporate networks reducing the impact and recovery time of a network security breach ensuring the reduction in cyber incident risk profile and improved SOCI compliance. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-02-01 | 2023-04-14 |  | 2023-04-14 | 15000 |  | 2023-04-14 |  | 2024-11-07 | 2026-12-31 | 1477000 | 2983000 | Green | Green | Amber | Amber | Green | The IT/OT separation is on schedule. The OT Network is in production and the first Water Plant has been cutover to the new OT Network successfully. Project rescheduling has been approved and the project has been extended by 6 months with no requested increase in budget.
Q3 25-26 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3843 | Human Resources Information System Replacement | Education | Human Resources | Replace BKI’s ageing HR and Payroll systems with a modern cloud-based platform which will enable improved HR processes, improved user experience and significantly improved people data and reporting. | Postponed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2025-09-24 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-09-01 | 2023-12-08 |  | 2023-12-08 | 370000 | 125000 | 2024-02-01 |  | 2025-03-31 | 2025-12-19 | 2643965 | 3161265 | Red | Red | Red | Red | Red | Phase 2 of the HRIS project was paused pending the outcome of Enterprise Agreement negotiations. Following their conclusion, the organisation is considering the path forward.
Q3 25-26 | Department of Health | DH | 3844 | Security Access Modernisation | Health | Systems Management | Cloud application migration from legacy TAM6 to ISVA10 environment, and engagement with business teams to transition their onboarding process to use Departmental User Onboarding Portal V2, reducing operational risk of the unsupported TAM6 platform. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-06-28 |  | 2024-06-28 | 574077 |  | 2024-06-28 |  | 2025-06-30 | 2026-06-30 | 1413388 | 1387986 | Amber | Green | Green | Green | Amber | Project is amber due to constraints in procuring the required services which is impacting the schedule.
Q3 25-26 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3845 | Apprentice and Trainee Management Module Implementation | Education | Systems Management | This project will deliver functionality into the core student management system to be enable apprentice and trainee student management. This will bring all BKI students management onto one platform, reducing integration and data risks | Postponed | Increased Revenue (Financial) | 2025-06-05 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-30 | 2023-12-08 |  | 2023-12-08 | 200000 |  | 2024-01-08 |  | 2025-06-30 | 2025-12-31 | 3157730 | 4311828 | Red | Red | Red | Red | Red | The project is currently paused. A deep dive has assessed the system build as complete. Consideration is now being given to the most appropriate approach to implementation, aligned with other TAFE deployments.
Q3 25-26 | Workplace Injury Commission | WIC | 3853 | Case Management System | Law and Justice | Tracking and Workflow | Implementation of a new case management system that improves efficiency and productivity, to support the resolution of workplace injury disputes for Victorian workers. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-02-14 | 2024-10-30 | 2025-05-28 | 2025-05-28 | 0 | 1900000 | 2025-05-29 |  | 2027-06-30 |  | 12000000 |  |  |  | Green | Green | Green | The project is progressing as planned with the vendor onboarded and discovery activities underway to refine requirements. The project remains on schedule, within budget, and continues to track green overall, with minor resourcing impacts being actively managed.
Q3 25-26 | Department of Health | DH | 3856 | Mental Health and Wellbeing Client Management System Implementation Project (MHWCMS) | Health | Data Management,Development and Integration | Delivery of a Mental Health and Wellbeing Client Management System to the Mental Health Sector to replace CMI/ODS and acquit recommendation 62 in the Royal Commission into Victoria’s Mental Health System. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2023-12-01 | 2023-12-22 |  | 2023-12-22 | 0 |  | 2024-01-01 |  | 2026-06-30 | 2028-06-30 | 40229527 | 64701864 | Red | Red | Red | Red | Amber | Status improved to Amber following approval of the revised project schedule. The project remains Amber due to ongoing risks associated with delayed sector engagement and residual uncertainty in several assumptions underpinning the deployment sequencing.
Q3 25-26 | North East Link State Tolling Corporation | NELSTC | 3858 | Toll Collection Capability (TCC) - Roadside Systems (RSS) | Transport and Vehicles | Analyses and Statistics ,Communication,Data Management,Development and Integration ,Records Management ,Reporting | The Roadside Systems will effectively & efficiently detect vehicles and capture tag or vehicle details ensuring toll revenue is collected accurately and road users have a seamless experience while accessing North East Link. | Initiated |  |  | PMBoK | 2023-06-27 | 2025-09-26 | 2026-06-29 |  | 1117000 | [12 empty] | The TCC RSS contract was awarded in FY25 Q4 and now in the delivery phase. RSS activities are progressing in line with planned schedules with the contractor completing the Preliminary Design Phase and commencing the Detailed Design phase. The project will remain in initiation until TCC - Back Office Systems (BOS) procurement completes in FY26 Q4 to maintain procurement integrity. The TCC RSS and TCC BOS projects are complementary streams of the one project which share a budget. Disclosing the full cost of TCC RSS could potentially enable TCC BOS respondents to derive the BOS budget compromising procurement integrity and competitive positioning. The Revised Initiation End Date reflects this approach.
Q3 25-26 | North East Link State Tolling Corporation | NELSTC | 3859 | Toll Collection Capability (TCC) - Back Office Systems (BOS) | Transport and Vehicles | Communication,Customer Initiated Assistance,Customer Relationship Management,Management of Process ,Reporting | The Back Office Systems will efficiently manage trip formation, interoperability between Australian Toll Roads, billing and collection of toll revenue while providing road users an efficient way to pay for their travel on North East Link. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-27 | 2026-06-29 |  |  | 1117000 | [12 empty] | The project will remain in initiation until procurement completes in FY26 Q4 to maintain procurement integrity.​ The BOS procurement activities are progressing in line with baseline schedule and forecasted within the approved budget.
Q3 25-26 | Coliban Region Water Corporation | Coliban Water | 3860 | Core Capability Uplift | Environment and Water | Financial Management | New software implementation and business processes optimisation to uplift the Commercial and Financial Management capabilities, directly contributing to the strategic goals of ‘Financial Sustainability’ and ‘An Adaptive and Resilient Organisation’. | Delivery | Efficiency/Productivity (Non Financial) |  | PMBoK | 2023-08-08 | 2024-07-02 | 2025-07-02 | 2025-07-02 | 0 |  | 2025-07-07 |  | 2026-08-13 | 2026-11-30 | 11070000 |  |  |  | Amber | Green | Green | The project remains on track.
Q3 25-26 | Greater Western Water Corporation | GW Water | 3863 | Asset, Works & Field Services Mgmt Consolidation (Concordia) | Environment and Water | Assets/Materials Management,Collaboration ,Data Management,Development and Integration ,Human Capital / Workforce Management ,Reporting ,Systems Management | AWFSMC serves as a foundational pillar to transform future ready Field Service mgmt & Asset & Works Mgmt capabilities . It will increase business & customer satisfaction & will be delivered in phases with budget increases reflecting each phase | Delivery | Compliance (Non Financial), Cost Avoidance (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-09-11 |  | 2023-09-11 | 760490 |  | 2023-09-11 |  | 2028-06-30 | 2026-06-30 | 3436310 | 8470976 | Amber | Green | Green | Green | Amber | Revised integrated schedule in progress. Impacts to end-to-end timelines being assessed.
Q3 25-26 | Greater Western Water Corporation | GW Water | 3864 | Geospatial Capability Uplift (OSO 2030) | Environment and Water | Analyses and Statistics ,Assets/Materials Management,Data Management,Visualisation | The project will enhance geospatial capability through modern standards and technologies to maximise value of spatial information in order to gain new insights for improved asset management capabilities across the organisation. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial) |  | Waterfall | 2023-07-01 | 2024-04-07 |  | 2024-04-07 | 3900000 |  | 2024-04-07 |  | 2028-06-30 |  | 20300000 |  | Green | Green | Green | Green | Green | Release 1 of data remediation completed in Q3, data migration preparation activities continue to Q4; review of procurement approach in progress.
Q3 25-26 | Department of Justice and Community Safety | DJCS | 3869 | Replacement DJCS Safety Incident Management System | Community Services | Reporting | Procurement, and implementation of a safety incident management system will streamline how safety incidents are reported and investigated. This system will foster a proactive safety culture where incidents are managed efficiently and effectively. | Postponed |  | 2025-06-30 | Project Management Excellence | 2023-12-19 | 2024-01-31 | 2024-01-04 |  | 0 | [5 empty] | 0 | [6 empty] | Due to resourcing constraints, the project was postponed in June 2025. The project completed the initiation phase in January 2024 and was approved to commence procurement activities for the provision of a safety incident management system. Once resources become available, the project will transition to the delivery phase, commencing with procurement activities. The delay in procurement commencement does not result in any additional risk as the project seeks to deliver a replacement system that enhances functionality and provide efficiencies beyond what the current system offers. The current system is still fully functional and operational.
Q3 25-26 | Holmesglen Institute of TAFE | Holmesglen TAFE | 3870 | Identity Governance and Administration | Employment, Skills and Workplace | Security Management | The IGA project will deliver a new Identity Governance & Administration platform. The new IGA platform will improve staff/student identity governance and security by enabling contemporary features such as attestation and hardened authentication. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-09-14 | 2023-11-15 |  | 2023-12-06 | 0 |  | 2024-03-01 |  | 2025-03-28 | 2026-07-31 | 1205132 |  | Green | Amber | Amber | Amber | Amber | The IGA Project is currently Amber, reflecting delivery and commercial risks identified in the previous reporting period. During Q3, the project team undertook targeted actions to address these risks and progress the project in a controlled and sustainable manner. This included re‑evaluating functional and technical requirements following the decision to move key student business logic into the Student Management System. This change improves architectural alignment and reduces integration complexity, supported by a corresponding redesign of the API layer. The team worked closely with the vendor to workshop updated solution designs. Project timelines will be re‑baselined once design validation is complete,
Q3 25-26 | South East Water | SE Water | 3879 | Sample Management | Environment and Water | Assets/Materials Management,Management of Process | The project will deliver a sample management system to streamline current processes, modernising the system capability, and enabling improved reporting, faster processes and insights for customer water quality. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2024-04-08 | 2024-08-01 |  | 2024-08-01 | 159445 |  | 2024-09-02 |  | 2025-07-31 | 2026-06-30 | 1937205 |  | Green | Green | Green | Green | Green | Phase 2 of project was successfully delivered in FY26 Q2. Decision has been made to remove Phase 3 from the scope of this project.
Q3 25-26 | Northern Health | NH | 3880 | Active Directory Segregation from Melbourne Health | Health | Systems Management | Northern and Melbourne Health are currently sharing the same Active Directory. Segregating from this shared active directory to a more modern version will allow NH to initiate its journey into cloud and enhance cyber security across all campuses | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2022-01-01 | 2022-09-27 |  | 2022-09-27 | 0 |  | 2023-03-09 |  | 2025-09-30 | 2026-06-30 | 3200000 |  | Green | Amber | Green | Green | Green | The project timeline has been revised to allow for the transition of Cardiology to the new domain and the migration of users into the updated Citrix environment. This schedule adjustment will not affect the budget, as it is being absorbed by the project contingency funds. Furthermore, the Radiology domain transition was completed successfully without any significant complications. Given that this was the most technically complex stage of the project, its smooth delivery marks a major milestone for the team.
Q3 25-26 | WorkSafe Victoria | WorkSafe | 3881 | Medical Panels Capability Uplift | Employment, Skills and Workplace | Tracking and Workflow | Medical Panels technology will migrate to a modern system enabling digital record-keeping, workflow automation, and improved cyber security. This mitigates the risk of end-of-life tech, improves efficiency, and uplifts staff / stakeholder experience. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-03 | 2024-12-05 | 2025-02-24 | 2025-02-24 | 947722 | 758291 | 2025-02-25 | 2025-04-14 | 2025-10-31 | 2026-06-30 | 4999889 | 4914431 | Amber | Amber | Red | Amber | Red | Status downgraded to Red due to budget impact. It is intended to undertake a system build assessment to quantify the functional gaps and system defects. To achieve this a change request to extend the schedule of the project with an increase in funding is pending governance approvals. A plan for additional resources is in development to support executing the Go to Green plan.
Q3 25-26 | Melbourne Water | MELB Water | 3882 | Business Process Optimisation 24-26 | Environment and Water | Systems Management | This project aims to optimise business processes and workflows using modern process management tool, improving process efficiency & reducing reliance on manual processes. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-06-13 | 2024-10-25 |  | 2024-11-14 | 0 |  | 2024-11-14 |  | 2026-07-21 |  | 2900000 | 2800000 | Green | Green | Amber | Red | Green | As at 20260331: Decision made to run proposed change request to scope as a separate project to ensure appropriate governance.
Q3 25-26 | Grampians Rural Health Alliance | GRHA | 3886 | Grampians Health Success Factors Phase 2 | Health | Human Resources | Implementation of SAP SuccessFactors, including Employee Central Payroll, refactoring of Employee Central, Recruitment, Onboarding, and implementation of Performance & Goals. Phase 2 will deliver integration with rostering, finance and IT systems. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-13 | 2023-12-15 |  | 2023-12-15 | 0 |  | 2024-08-14 |  | 2025-09-26 | 2026-05-29 | 2905553 |  | Green | Green | Green | Green | Green | From the 3rd November 2025, employee Central Payroll Employee Central Time off and the upgrades to our existing modules of Employee Central (including concurrent employment) Recruitment and onboarding are now live. This includes integrations to our rostering system Optima. 13 full fortnightly pay processes have been completed successfully in the new system as well multiple offline cycles. There are 2 outstanding items that remain to be finalised with those being the integration with Epicor and Fit2Work. These are due to be finalised by the end of May 2026.
Q3 25-26 | Greyhound Racing Victoria | GRV | 3887 | Greyhound Whole of Life Tracking (GWOLT) | Business and Industry | Analyses and Statistics ,Business Intelligence,Customer Relationship Management,Management of Process | Digital Whole of Life Greyhound Tracking (DGT) involves the digitised data capture storage and retrieval to automate processes for tracking and recording the location and health of Victorian greyhounds throughout stages of their lives. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial) | 2026-03-31 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-01-08 | 2025-01-31 | 2025-03-23 | 2025-03-23 | 0 |  | 2025-03-24 |  | 2026-03-31 |  | 2920000 |  | Green | Green | Green | Green | Green | This project is was delivered on 31 March 2026. The scope was delivered within schedule and budget.
Q3 25-26 | Department of Government Services | DGS | 3889 | Common Corporate Platform (CCP) - VicGov People - DGS/DPC/DTF Cluster | Government and Economy | Human Capital / Workforce Management | Onboarding the Departments of Government Services, Premier and Cabinet, and Treasury and Finance on a common human capital management platform (VicGov People) to drive efficiency and productivity, enhancing employee experience and corporate services | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-04 | 2024-06-28 | 2024-06-01 | 2024-06-25 | 0 |  | 2024-07-01 | 2024-07-01 | 2026-06-30 | 2026-03-27 | 25000000 |  | Green | Amber | Amber | Amber | Green | The project has implemented on schedule and is progressing through hypercare successfully. The project is expecting to finalize hypercare in the next quarter and complete transition to the business as usual functions.
Q3 25-26 | Yarra Valley Water | YV Water | 3891 | Altus PPM Tool Implementation | Environment and Water | Investment Management | Implementation of a PPM tool to centralise visibility of up-to-date program information, support consistency in the way projects get delivered, and provide insights on demand. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-08-01 | 2024-08-15 |  | 2024-08-26 | 421280 |  | 2024-09-02 |  | 2026-06-10 |  | 2947600 |  | Amber | Amber | Amber | Amber | Amber | Project is reporting Amber due to change in scope for Phase 1 (the major delivery phase to implement the enterprise capability). Some lower priority integrations have been excluded with minimal impact on the benefits
Q3 25-26 | Fire Rescue Victoria | FRV | 3893 | Asset Sustainment | Emergencies and Safety | Assets/Materials Management | This project aims to procure ICT equipment to replace components at end-of-life. This includes equipment such as network equipment and fire station switches and will ensure a safe ICT environment and ensure ongoing reliability. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-07-01 | 2020-10-05 |  | 2020-10-05 | 0 |  | 2022-02-14 |  | 2024-12-31 | 2026-06-30 | 7069087 | 6967773 | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q3 25-26 | Department of Education | DE | 3896 | Kindergarten Attendance Program | Education | Analyses and Statistics ,Business Intelligence,Data Management | Delivery of a digital solution to collect kindergarten attendance data to improve child outcomes and to report on performance indicators as required by the Commonwealth Preschool Reform Agreement. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Increased Revenue (Financial) |  | Agile | 2023-02-01 | 2023-07-31 |  | 2023-08-01 | 0 |  | 2023-08-01 |  | 2026-06-30 |  | 20965000 |  | Green | Green | Green | Green | Green | The project is GREEN, with successful kindergarten funding deployments completed during Q3 2025-26 quarter. This milestone completes the technical delivery in accordance with agreed timeframes. Additional work is in progress to enable and sustain the solution. The remaining budget spend is tracking to plan.
Q3 25-26 | Department of Health | DH | 3899 | Health Technology Services Application Cloud Migration | Health | Data Management,Development and Integration | Migrate three Health Technology Services applications to the department’s ICT Cloud environments, namely Finance and Material Information System, Client Management System and HealthCollect, to improve data availability, security and reliability. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2024-05-01 | 2024-05-31 |  | 2024-05-31 | 0 |  | 2024-06-03 |  | 2025-06-30 | 2026-06-30 | 2715200 | 3091807 | Red | Amber | Amber | Red | Amber | The project is progressing, and its status has improved to Amber following approval of the revised schedule to 30 June 2026 by the Project Steering Committee. The project remains Amber due to risks associated with sector testing progress and tight delivery timelines.
Q3 25-26 | Westernport Region Water Corporation | WPR Water | 3906 | Asset Management Information System Replacement | Environment and Water | Assets/Materials Management | The project will replace legacy asset management and work order management systems improving functionality and flexibility to enable more accurate, accessible and comprehensive information for decision-making. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-09-03 | 2025-06-30 | 2025-04-14 | 2025-04-14 | 200000 | 254000 | 2025-04-14 |  | 2026-10-30 |  | 1440000 |  |  | Green | Green | Green | Green | Project remains on-track and on-budget. Phases 1A-1D to be implemented by October 2026.
Q3 25-26 | Peninsula Care Group – Bayside Health | PEN Care Group | 3907 | Peninsula Health Project Phoenix (MePACS Refresh) | Health | Customer Relationship Management | A technology refresh of the core MePACS systems with a modern Customer Relationship Management System (CRM) to secure the ongoing viability of the MePACS business. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-06-03 | 2024-10-31 |  | 2024-10-31 | 340000 |  | 2024-11-04 |  | 2025-10-31 | 2026-06-30 | 2620000 | 2621445 | Green | Green | Green | Green | Green | Performance Verification Testing for all alarm devices and signals is complete. Changes to the vendor delivery team arising from organisational restructuring resulted in the replacement of several project resources. This necessitated replanning of the Phase 2 implementation approach particularly in relation to cutover activities and post–go-live hypercare/support arrangements.
Q3 25-26 | Monash Health | Monash H | 3912 | Maternity Digital Transformation Project | Health | Management of Process | The project will implement EMR and breast milk management module onto a single EMR platform, supporting a single view of the patient's medical record, improving clinical outcomes for both mother and baby. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-10-31 | 2024-04-04 | 2024-04-04 | 0 | 0 | 2024-11-01 |  | 2026-05-27 |  | 11522379 |  | Amber | Green | Green | Red | Red | The vendor has advised they are unable to meet the current project timeline, requiring the project schedule to be re‑baselined. An impact assessment of the revised schedule and associated mitigation options is underway. Board approval is sought for additional funding to support the proposed project extension. A revised project plan and a contract variation are being requested from the vendor.
Q3 25-26 | Barwon Region Water Corporation | BR Water | 3915 | C1062 - Works and Asset Management | Environment and Water | Assets/Materials Management | Improve strategic and operational asset management and service delivery through the implementation of Maximo Works Management providing benefits such as, a more financially sustainable business and keeping bills affordable for all. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-01 | 2025-03-31 | 2025-07-01 | 2025-07-01 | 824310 | 2162000 | 2025-07-01 |  | 2026-12-31 | 2027-04-30 | 10208000 |  |  |  | Green | Amber | Amber | The program progressed Phase 1 with External Works deployed to production in February and the BAS Land Management team scheduled to transition at the start of the new FY. Finance and Supply Chain integrations with Barwon Water’s TechnologyOne system are nearing completion. During Q3 work advanced on integrating new Maximo work management processes for Digital Metering, Operations and Maintenance. Following the departure of key resources and identification of additional design effort the Phase 2 approach was reviewed. Re-planning commenced in late Q3 revising design governance and re-baselining the schedule resulting in an adjusted delivery timeframe of approximately two months.
Q3 25-26 | Department of Families, Fairness and Housing | DFFH | 3917 | Public Housing Maintenance Modernisation Technology Enablement Program | Community Services | Development and Integration | Uplift digital capability of Homes Victoria systems including new housing maintenance portal, improvements to HiiP system, and integration capability with Contractor Work Systems, providing greater process efficiencies and ease of use by tenants. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-10-01 | 2024-10-11 |  | 2024-10-11 | 1214790 |  | 2024-10-11 |  | 2026-06-30 | 2027-06-30 | 23066733 | 32988210 | Red | Red | Red | Amber | Amber | The program status is amber and improving. Change request for additional scope and schedule extension has been approved. Program expected to return to green in next reporting period once contractor onboarding go-live date has been confirmed. This will relieve IT delivery scope and schedule pressure.
Q3 25-26 | South East Water | SE Water | 3923 | Acumen Phase 2 | Environment and Water | Business Intelligence,Data Management | Phase 2 of Acumen will deliver foundation components, including architecture review and data preparation for ingestion and modelling. This will deliver key foundational elements necessary to support future phases. | Closed - Completed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2026-02-28 | Agile | 2024-01-01 | 2024-02-29 |  | 2024-02-29 | 0 |  | 2024-02-29 |  | 2025-04-30 | 2026-02-28 | 3600000 | 6585000 | Green | Amber | Amber | Green | Green | The project is reporting GREEN and has now been completed.
Q3 25-26 | South East Water | SE Water | 3924 | Information Management Strategy Delivery | Environment and Water | Business Intelligence,Data Management,Reporting | Program of work delivering multiple initiatives that is delivering on the Information Strategy including - Enterprise Content Management Data & Information Management Analytics & Reporting. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-06-01 | 2023-06-30 |  | 2023-09-26 | 0 |  | 2023-09-26 |  | 2025-07-31 | 2026-07-31 | 1859425 |  | Red | Amber | Green | Green | Green | The project is currently tracking GREEN with deliverables all on track as per baselined schedule.
Q3 25-26 | South East Water | SE Water | 3925 | Lentic Performance Enhancements | Environment and Water | Communication | Optimization of IoT platform to ensure scalability and optimal performance within the boundaries of the current architecture. This will ensure the IoT platform will support the mass roll out of digital meters across SEW network. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2024-03-01 | 2024-04-18 |  | 2024-06-05 | 0 |  | 2024-08-01 |  | 2025-12-31 | 2026-06-30 | 1161000 |  | Amber | Amber | Green | Green | Green | Project had returned to GREEN. Phase 2 implementation successfully implemented in FY26 Q2. Work has commenced on Phase 3 and deliverables are on track as per baselined schedule.
Q3 25-26 | Gippsland Health Alliance | GHA | 3928 | Payroll and Talent Modernisation (HRIS) | Health | Human Capital / Workforce Management | The project involves implementing a single instance of SAP SuccessFactors across eleven agencies in Gippsland. This initiative aims to modernise processes and systems, enhancing efficiency and collaboration among the agencies. | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2022-02-18 | 2022-05-20 |  | 2023-02-17 | 180000 |  | 2023-04-10 |  | 2025-06-27 | 2026-06-30 | 1600000 | 2300000 | Amber | Amber | Green | Green | Green | All remaining sites live across two phases. One group in February and the second in March-April '26. Now focusing on closing out the project and moving into operations.
Q3 25-26 | Transport Accident Commission | TAC | 3931 | Strategic Analytics Program Phase 2 | Transport and Vehicles | Business Intelligence | Build capability for both analysts & the broader enterprise in working optimally to deliver use cases from a prioritised backlog that will result in well managed & trusted data, improved customer & workforce satisfaction, platform efficiencies. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-07-01 |  | 2024-07-01 | 0 |  | 2024-07-01 |  | 2026-06-30 |  | 11000000 |  | Green | Green | Green | Green | Green | The program has delivered most of planned deliverables for Q3 FY25/26. Delivery Teams have been working with stakeholders to review and refine Q4 delivery plans.
Q3 25-26 | Melbourne Water | MELB Water | 3932 | Cyber Defence Initiatives | Environment and Water | Security Management | Redesign the existing SOC capability in line with the new Security Operations Operating Model. Deliver a better asset discovery and inventory capability, providing cyber control coverage assurance to the organisation. | Delivery | Risk Reduction (Non Financial) |  | PMBoK | 2024-07-26 | 2025-02-20 | 2025-07-07 | 2025-07-07 | 0 |  | 2025-07-07 |  | 2026-06-10 |  | 4868275 | 4547353 |  |  | Green | Green | Green | As at 20260331: Project on track..
Q3 25-26 | WorkSafe Victoria | WorkSafe | 3933 | Strategic Integration Platform | Employment, Skills and Workplace | Systems Management | Integration technology connects systems and data across platforms. This project will move existing integrations to the Strategic Integration Platform a modern cloud-based solution that reduces failures and speeds recovery benefitting all users. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 0 |  | 2024-07-01 |  | 2025-06-30 | 2026-06-30 | 4597071 | 10624421 | Amber | Red | Green | Green | Amber | The final phase of the project is tracking to schedule (Q4 FY25-26) however additional funding is required to complete the validation and deployment of a few complex integrations. The additional funding request is pending approval in Q4.
Q3 25-26 | WorkSafe Victoria | WorkSafe | 3934 | Licensing CRM (Customer Relationship Management) FY25 | Employment, Skills and Workplace | Customer Relationship Management | Transition of the remaining 5 license journeys from the legacy mainframe. This completes the transition of License Management capability to the CRM, unifying business processes, centralising data, and enhancing both customer and employee experiences. | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2026-03-31 | Agile | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 0 |  | 2024-07-01 |  | 2025-06-30 | 2026-03-31 | 4466242 | 7054661 | Red | Green | Amber | Red | Amber | A decision has been made to close the project following the determination that the licensing journeys are significantly more complex than originally anticipated and would require substantially more time and budget to complete the approved scope. Alternative options were explored; however considerable uncertainty remains regarding the time, effort, and cost required to transition the remaining three licences. The project will proceed to closure with the closure report to be completed in Q4.
Q3 25-26 | Independent Broad-based Anti-corruption Commission | IBAC | 3941 | Case Management System Enhancement Project | Government and Economy | Business Intelligence,Collaboration | This project is to deliver enhancements to IBAC's case management system and improvements to data maturity in the form of analytics, reporting and dashboard outputs. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-03 | 2024-12-31 | 2025-01-31 | 2025-01-31 | 0 | 270000 | 2025-02-01 |  | 2026-06-30 |  | 2443584 | 2443584 | Amber | Amber | Amber | Green | Amber | Overall project cost and completion date are on track. The project is currently rated Amber due to delays in Phase 2 User Acceptance Testing (UAT) which has resulted in a subsequent shift to the planned Phase 2 go-live date. As Phase 3 development is dependent on the successful completion and go-live of Phase 2 this has also delayed the commencement of Phase 3 activities. This represents a schedule- related risk only.
Q3 25-26 | Yarra Valley Water | YV Water | 3943 | Digital Meter Integrated Software Solution (HES/MDMS) | Environment and Water | Analyses and Statistics ,Assets/Materials Management,Knowledge Discovery ,Tracking and Workflow,Visualisation | Implementation of an integrated software solution for an Internet of Things Head End System (IoT HES) and Meter Data Management System (MDMS) to enable YVW’s digital water metering and IoT strategy which plans to deploy around one million digital met | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2022-08-01 | 2023-12-31 |  | 2024-01-09 | 1062000 |  | 2024-01-10 |  | 2025-06-30 | 2026-06-30 | 6678000 |  | Green | Green | Green | Green | Green | The project is tracking well against scope and budget with a minor schedule delay to last milestone due to business reprioritisation. The software platform is live with over 48.5k meters deployed with enhanced features to identify customer leaks.
Q3 25-26 | Yarra Valley Water | YV Water | 3945 | WorksPortal System and Asset Creation Replacement | Environment and Water | Customer Relationship Management | The current WorksPortal System is reaching end of life with support expiring by July 2026. As the system relates to asset creation and revenue, a replacement is required. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-07-01 | 2025-03-31 | 2025-05-31 | 2025-06-19 | 650000 | 736000 | 2025-06-19 |  | 2026-04-30 |  | 3936260 |  |  | Green | Green | Amber | Amber | Due to the earlier resourcing constraints, the project schedule and budget require extensions. A change request is currently underway
Q3 25-26 | Yarra Valley Water | YV Water | 3946 | Land Development System (easyACCESS) Replacement | Environment and Water | Customer Relationship Management | Full replacement of the current easyACCESS Land Development portal with a Salesforce solution, before the portal reaches end of life | Initiated |  |  | Agile | 2024-07-01 | 2025-06-30 | 2026-03-31 |  | 1772100 | 3795600 | [11 empty] | The New Land Dev Portal RFT identified a material gap in our current high-level process and requirements definition. That indicated further detailed requirements work, needed prior to full scale development. A revised approach was endorsed by YVW’s Portfolio Control Board on 26 Feb. This introduces a “Dedicated Planning and Solution Design” stage prior to full delivery commitment, to i) further mature detailing of business processes and requirements, ii) incorporate vendor expertise into solution design due to complexity of the system, iii) finalise the solution design and build approach, increasing confidence levels in Delivery Phase costings.
Q3 25-26 | Melbourne Water | MELB Water | 3948 | End User Computing Lifecycle Renewal FY24-26 | Environment and Water | Assets/Materials Management | Staff have been provided devices including laptops, tablets, heat sets and mobile phones to perform their tasks. These devices need to be regularly updated to ensure suitable performance and enabling the use of modern applications. | Initiated |  |  | PRINCE2 | 2024-09-30 | 2025-02-06 | 2026-05-01 |  | 0 | 0 | [11 empty] | As at 20260331: Business Case still under development. Submission now expected in Q4.
Q3 25-26 | Melbourne Water | MELB Water | 3949 | Identity and Access Management Initiatives | Environment and Water | Security Management | Process uplift, technology build and onboarding to the current identity access platform. | Delivery | Risk Reduction (Non Financial) |  | PMBoK | 2024-07-26 | 2025-05-21 | 2024-12-11 | 2024-12-11 | 0 |  | 2024-12-11 |  | 2026-06-30 |  | 4807000 | 4205076 | Green | Red | Green | Green | Green | As at 20260331: Project is on track.
Q3 25-26 | Melbourne Water | MELB Water | 3950 | Intranet Renewal | Environment and Water | Communication | Renew or replace current Melbourne Water Intranet, including full investigation of options and user impacts. Re-imagine employee access to internal information. | Initiated |  |  | PMBoK | 2024-08-26 | 2024-12-18 | 2026-05-05 |  | 0 | 0 | [11 empty] | As at 20260331: Business Case under review.
Q3 25-26 | Melbourne Water | MELB Water | 3952 | Privilege Access Management Initiatives | Environment and Water | Systems Management | This project aims to implement a comprehensive Privileged Access Management (PAM) system to enhance security by onboarding critical accounts across network and operational technology environments. The investment supports robust identity governance. | Delivery | Risk Reduction (Non Financial) |  | PMBoK | 2024-07-26 | 2025-03-21 | 2024-12-12 | 2024-12-12 | 0 |  | 2024-12-12 |  | 2026-06-30 |  | 2290000 | 1965947 | Green | Red | Green | Green | Green | As at 20260331: Project on track, migration to production and testing of service accounts underway.
Q3 25-26 | Department of Transport and Planning | DTP | 3953 | OneDigital Workplace | Transport and Vehicles | Customer Preferences,Development and Integration ,Organisational Management ,Security Management ,Systems Management | Delivering a new Standard Operating Environment and operating model for the DTP so that all users can access a modern and consistent desktop environment. Includes rationalisation of ITSM tools (ServiceNow). | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2026-06-30 | 2025-02-28 | 2025-02-28 | 10000000 | 0 | 2025-03-03 |  | 2026-06-30 | 2026-12-30 | 10000000 | 10001234 | Green | Green | Green | Green | Green | Overall program status is green and is on track.
Q3 25-26 | Melbourne Water | MELB Water | 3954 | Standalone Server Refresh | Environment and Water | Assets/Materials Management | Standalone servers at or approaching end of life &/or end of support require upgrading to meet ongoing operational requirements. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-08-09 | 2024-10-30 |  | 2024-11-13 | 0 |  | 2024-11-13 |  | 2026-03-12 | 2026-09-21 | 1992000 |  | Green | Green | Green | Green | Amber | As at 20260331: Hardware not currently in scope has been identified requiring to be refreshed, analysis of costs and timeframe to delivery underway. This will inform a decision if this is added to scope or run as a separate initiative.
Q3 25-26 | Melbourne & Olympic Parks | M&OP | 3955 | End of Life Switch Replacement 2024/25 | Culture, Sport and Recreation | Systems Management | The project will replace end-of-life hardware to maintain support for the network switch environment, enabling the organisation to minimise legacy system risks and improve security. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2024-05-01 | 2024-07-01 |  | 2024-07-01 | 0 |  | 2024-07-15 |  | 2025-06-30 | 2026-11-30 | 2750000 |  | Amber | Amber | Amber | Amber | Amber | Phase 1 has now been completed, and activities to appoint a system integrator for Phase 2 have commenced. The project status remains AMBER, as Phase 2 planning is still being finalised. This has affected the certainty of the completion date and is also dependent on phase 2 delivery planning considerate of the Melbourne Park events schedule.
Q3 25-26 | Department of Education | DE | 3956 | Brief Connect | Education | Content Management,Data Management,Document Management ,Management of Process ,Reporting ,Tracking and Workflow | The project will deliver a workflow solution for managing all departmental briefings and correspondence. This solution will enhance the depts digital capabilities by utilising existing Cloud Service. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-12 | 2023-07-04 |  | 2023-09-05 | 0 |  | 2024-07-29 |  | 2025-03-07 | 2026-03-31 | 2657628 | 3757628 | Amber | Green | Green | Amber | Green | The project was successfully implemented on 30 March 2026. Delivery was completed within the revised schedule and budget. The project is now in hypercare until end of April 2026. Project closure activities are in progress.
Q3 25-26 | Department of Education | DE | 3961 | Securing Connected Learners (SCL) Program – Phase 2 | Education | Development and Integration ,Security Management ,Systems Management | Securing Connected Learners a high profile program of work creating enhanced security capabilities for schools, initially addressing child safety & security risks in schools by transitioning schools to platforms with enhanced cyber security features | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-01 | 2024-06-03 |  | 2024-06-03 | 0 |  | 2024-06-03 |  | 2025-06-30 | 2026-06-30 | 3100000 | 6098000 | Amber | Amber | Amber | Amber | Amber | There are no delays or risks associated with this program however the project is reporting as AMBER due to a change in the scope of works for Phase 2 to align with project requirements. This phase of program is now preparing for closure.
Q3 25-26 | Department of Education | DE | 3963 | 50 Early Learning Childcare Centres - Technology Components | Education | Customer Relationship Management | The project will deliver the required technology components in 50 early learning childcare centres over multiple years to support the Victorian Government initiative in broader early learning, enabling a great start for young Victorians. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial) | 2026-03-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-15 | 2024-03-15 |  | 2024-03-18 | 0 |  | 2024-03-18 |  | 2032-06-30 | 2026-03-30 | 2108035 | 2297612 | Green | Green | Green | Green | Green | The program's major deliverable Kidsoft application has been delivered. The remaining application ‘add on’s’ and annual site establishment is now in the Department of Education Business As Usual processes.
Q3 25-26 | State Revenue Office | SRO | 3965 | Vacant Residential Land Tax 2 | Government and Economy | Development and Integration | This project will expand the Vacant Residential Land Tax (VRLT) system to collect and administrate VRLT across all Victorian properties from January 2025 and underdeveloped residential land in Greater Melbourne areas from January 2026. | Closed - Completed | Social Improvement (Non Financial) | 2026-03-31 | Agile | 2024-05-23 | 2024-06-30 |  | 2024-06-30 | 35000 |  | 2024-07-01 |  | 2026-06-30 | 2026-03-31 | 1927652 | 3612544 | Amber | Green | Green | Green | Green | 2026 features delivered. Project closed on 31 March 2026. The budget increase is to reflect the full scope delivery including the 2026 changes.
Q3 25-26 | Alfred Care Group – Bayside Health | ALFRED Care Group | 3968 | Disaster Recovery | Health | Security Management | The Disaster Recovery project will enhance ICT infrastructure for disaster recovery, prioritizing patient safety and data integrity by establishing a robust, adaptable ICT environment that maintains continuous operations during disruptions. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-10-21 |  | 2024-10-21 | 148217 | 69382 | 2024-10-28 |  | 2026-07-01 | 2026-08-31 | 1171783 | 1250618 | Green | Green | Green | Green | Green | The project is on track.
Q3 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3977 | Energy Customer Relationship Management (CRM) Project | Government and Economy | Customer Relationship Management | The Energy CRM Project will deliver a customer management system to enable DEECA's Energy Group to deliver best practice stakeholder engagement and more efficient government processes. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-04 | 2024-12-11 |  | 2024-12-11 | 150000 |  | 2024-12-12 |  | 2025-06-30 | 2026-04-30 | 1277120 | 1250822 | Amber | Green | Green | Green | Green | The project is tracking well against scope budget and schedule. Stage 1 has been successfully completed. Stage 2 delivery has commenced and re-baseline was approved to complete the delivery by the end of Q4.
Q3 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3980 | FireWeb Decommissioning Project | Emergencies and Safety | Management of Process | The FireWeb Decommissioning Project will replace the legacy system FireWeb to improve the accessibility of the information. This infrastructure will be DEECA's primary source for Fire Management. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-01 | 2024-06-30 |  | 2024-06-30 | 0 |  | 2024-07-01 |  | 2028-06-30 |  | 5047000 |  | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q3 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3981 | Emergency Management (EM) Deployment Project | Emergencies and Safety | Management of Process | The EM Deployment project will deliver a modern system to plan and coordinate the commitments and resources for bushfire and other emergency incidents to increase DEECA's capabilities to manage these incidents effectively and in a timely manner. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-01 | 2024-06-30 |  | 2024-06-30 | 0 |  | 2024-07-01 |  | 2026-12-31 | 2026-12-31 | 1223000 |  | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule with a planned incremental increase in spend.
Q3 25-26 | Department of Government Services | DGS | 3982 | Service Victoria - Firearms & Private Security Digital Program - Phase 1 | Government and Economy | Customer Initiated Assistance,Management of Process | The project will deliver a minimum viable product to digitise the Firearms licence renewal process, in addition to enabling Firearms licence holders to obtain and securely store their licences in a digital form through Service Victoria app | Closed - Completed | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) | 2026-03-31 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-09-01 | 2024-03-01 |  | 2024-03-01 | 0 |  | 2024-03-01 |  | 2025-06-30 | 2026-01-30 | 2239255 | 1800000 | Green | Green | Green | Green | Green | DGS has completed the transactions and handed them over for BAU activities jointly managed by DGS and the agency.
Q3 25-26 | Peninsula Care Group – Bayside Health | PEN Care Group | 3985 | Peninsula Health Replacement of legacy Citrix virtual desktop environment & virtual server infrastructure | Health | Systems Management | Replacement of legacy Virtual Desktop and Converged Infrastructure at Frankston Hospital providing clinical application access to all sites, increasing usability and access for all staff to applications and data, including Video conference/telehealth | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-03-04 | 2024-10-18 |  | 2024-10-18 | 10000 |  | 2024-10-18 | 2024-10-21 | 2026-02-27 | 2026-06-30 | 7329269 | 7982065 | Green | Green | Green | Green | Green | Server migration to new hardware is progressing with 177 servers completed and 24 remaining focus is on critical MePACS and Rhapsody servers. Duress migration completed. Frankston Hospital Redevelopment vendors to Citrix Cloud largely completed remaining vendors continuing their transition to the new secure privileged access platform. The Firewall design has been approved and implementation is now underway.
Q3 25-26 | Department of Health | DH | 3987 | Donor Conception Register IT System | Health | Customer Relationship Management | Deliver a new IT system to manage Victoria's donor conception registers and allow applicants (donors, donor-conceived persons', parents, and their families) to request information under the legislation. | Postponed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial) | 2024-09-01 | Agile | 2024-01-15 | 2024-03-26 |  | 2024-03-26 | 7800 |  | 2024-04-01 |  | 2025-06-30 |  | 1522446 |  | Green | Red | Red | Red | Red | Major components of the system were delivered and the project remains on hold. Delivery will progress once the revised scope and remaining funding are confirmed.
Q3 25-26 | South East Water | SE Water | 3989 | CRUX - Stabilisation | Environment and Water | Financial Management | Uplift of ERP solution implemented in 2023. Including Finance Procurement & Project Management functions. | Delivery | Cost Reduction (Financial) |  | Waterfall | 2024-07-01 | 2024-12-20 |  | 2024-12-20 | 0 |  | 2025-01-27 |  | 2026-01-30 | 2026-06-30 | 3510000 | 3990000 | Green | Green | Amber | Amber | Amber | Project overall remains AMBER as a result of delays in closing out remaining modules due to critical resource availability. Remaining deliverables on track to be delivered by end of Q4 FY26.
Q3 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3991 | Victorian Water Register (VWR) Evolve Project | Environment and Water | Development and Integration | The VWR Evolve Project will uplift the Victorian Water Register to a supported platform to improve the integrity security and reliability of Victoria's water market and enable future improvements in service delivery and information sharing. | Initiated |  |  | PRINCE2 | 2024-07-01 | 2025-05-31 | 2026-05-31 |  | 4233990 | [12 empty] | Procurement was initiated in the September 2025 quarter and progressed in the March 2026 quarter to secure a suitable Implementation Partner to support project execution. The Initiation End Date has been revised to May 31st, 2026, as the project has exercised planned contingency in order to take further de-risking activities through the procurement phase. The project business case was approved in 2024-25. Prior to undertaking procurement phase, a proof of concept was successfully completed.
Q3 25-26 | Melbourne Water | MELB Water | 3992 | Routine Telecommunications Upgrades FY24-26 | Environment and Water | Assets/Materials Management | Upgrade and replacement of degrading IT network cabling and devices - including microwave dishes 4G boosters WAPs and GWIP services. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2024-10-04 | 2025-02-13 | 2026-01-29 | 2026-01-29 | 0 |  | 2026-01-29 |  | 2026-07-02 |  | 2253368 | [5 empty] | Green | As at 20260331:Business case approved and hardware received.
Q3 25-26 | Eastern Health | EH | 3994 | Eastern Health EMR and Digitisation in the home | Health | Development and Integration | This project implements the EMR workflows across Care@Home services at Eastern Health alongside new integrated electronic logistics and fleet management applications to improve the coordination and delivery of care outside the hospital walls. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-28 | 2023-06-28 |  | 2023-06-28 | 420139 |  | 2024-12-06 |  | 2025-08-31 | 2026-03-31 | 4832935 |  | Green | Amber | Amber | Green | Amber | Phase 2 planning is underway between the project team and the vendor with the clarifications around solution design ultimately resulting in descoping of HITH Clinic from this delivery. Project progress was put on hold whilst analysis was undertaken by the vendor and health service teams. The revised timeline is planned to be tabled at the May Steering Committee. The project is anticipated to return to reporting Green in the next reporting period.
Q3 25-26 | Eastern Health | EH | 3996 | Eastern Health EMR Mobility and Enterprise Extension (Acute) | Health | Development and Integration | The EMR Mobility and Extension (Acute) Program aims to expand EMR footprint at Angliss and Maroondah Hospitals, simplify clinician workflows and patient information access, and implement EMR Mobility solutions while decommissioning legacy systems. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-01 | 2025-02-28 |  | 2025-02-28 | 0 |  | 2025-03-01 |  | 2025-12-15 | 2026-04-10 | 9979000 |  | Green | Green | Amber | Green | Green | The EMR Mobility and Enterprise Extension changes have successfully gone live at Box Hill Hospital Blackburn Public Surgical Centre and Maroondah Hospital. The final Eastern Health acute site Angliss Hospital has gone live on the 10th March 2026 and successfully exited from Hypercare. The EH project team and vendors continue to work together to provide resolution of outstanding warranty items.
Q3 25-26 | Eastern Health | EH | 4000 | Advancing Cancer Services through Digital Chemotherapy Project | Health | Development and Integration | This project implements the EMR Oncology modules to all Eastern Health sites where Cancer Services are delivered providing electronic cancer medication prescription and management for more safe and timely care. | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-11-01 | 2025-02-28 |  | 2025-02-28 | 0 | 511021 | 2025-03-31 |  | 2026-05-31 | 2026-08-31 | 3438979 |  | Green | Green | Green | Amber | Amber | The February Steering committee accepted new timeline to allow for the appointment scheduling solution to be built and validated. The project's focus has been finalising the appointment scheduling and correspondence solution while in parallel continuing to build and validate treatment protocols.
Q3 25-26 | WorkSafe Victoria | WorkSafe | 4002 | Mature Platform to Target State | Employment, Skills and Workplace | Analyses and Statistics ,Business Intelligence,Data Management | The Mature Platform work has been defined to complete the implementation of the data pipelines and data objects in the EDH aligned to the approved target state architecture and transform and uplift operational processes aligned to new architecture. | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2026-02-27 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-23 | 2024-10-31 |  | 2024-10-31 | 85310 |  | 2025-01-02 |  | 2025-12-31 | 2026-02-28 | 1536799 | 1658785 | Green | Green | Green | Red | Green | Project change request was approved, enabling delivery of remaining scope items with the project now proceeding to closure.
Q3 25-26 | WorkSafe Victoria | WorkSafe | 4003 | Return to Work Product Pipeline Implementation | Employment, Skills and Workplace | Analyses and Statistics ,Business Intelligence,Data Management | Deployment of a production-grade Return to Work (RTW) Dashboard Product to business users including operational support processes user training and change management. As well as automated ingestion of Australian Bureau of Statistics data. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-23 | 2024-10-31 |  | 2024-10-31 | 60290 |  | 2025-01-02 |  | 2025-12-31 | 2026-03-31 | 1318806 | 1505153 | Amber | Green | Amber | Red | Red | Remaining scope items are being assessed and a decision will be made in Q4 on the appropriate approach to progress. A change request for an additional 1-month extension is pending approval in Q4.
Q3 25-26 | Department of Health | DH | 4005 | Enterprise Operational Workforce Management System | Community Services | Human Capital / Workforce Management | Replace end-of-life Rostering, Time and Attendance systems for disability residential services, child protection, emergency response and maternal child health divisions across DFFH and DH to enhance workforce management and improve service delivery. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2023-12-14 | 2024-09-30 |  | 2024-09-30 | 239974 |  | 2024-10-01 |  | 2026-06-30 |  | 3518876 | 3519676 | Green | Green | Green | Green | Green | Project is progressing to cost and schedule.
Q3 25-26 | CenITex | CenITex | 4008 | AWS and Azure Cloud Landing Zone deployment | Government and Economy | Assets/Materials Management | This project iteratively implements Landing Zone feature enhancements. The focus is security enhancement standards implementation. Landing Zone “Official” security status implementation and delivery of a new cost model for efficient Cloud consumption | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Revenue (Financial) | 2026-02-02 | PRINCE2 | 2023-05-01 | 2023-06-30 |  | 2023-06-30 | 0 |  | 2023-07-01 |  | 2025-06-30 | 2026-03-31 | 1420000 | 1433831 | Green | Green | Green | Green | Green | Project Completed.
Q3 25-26 | CenITex | CenITex | 4009 | DC Exit Network Establishment – Phase 2 | Government and Economy | Assets/Materials Management | To establish a network extension from Burwood to Equinix ME2 using VicTrack colocation service at Equinix and then execute the base network infrastructure required at the data centre to start migrating Cenitex workloads out of Burwood to Equinix. | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2024-11-01 | 2024-11-30 |  | 2024-11-30 | 0 |  | 2024-12-01 |  | 2025-10-30 | 2026-10-30 | 1993326 | 3436585 | Amber | Green | Green | Green | Green | Project is tracking to plan.
Q3 25-26 | Goulburn Valley Region Water Corporation | GVR Water | 4011 | SCADA System Replacement | Environment and Water | Assets/Materials Management,Communication,Data Management,Systems Management | Replacement of the Supervisory Control and Data Acquisition (SCADA) System to ensure GVW's core operational monitoring and automation system remains fit for purpose and reduce business continuity risk. | Initiated |  |  | PMBoK | 2023-05-01 | 2025-04-30 | 2026-04-30 |  | 200000 | 415000 | [11 empty] | GVW is finalising procurement. Approval to award contracts will be sought from the Board in June 2026.
Q3 25-26 | Hume Rural Health Alliance | HRHA | 4012 | Hume Regional EMR Preparation Project | Health | Customer Relationship Management,Records Management | The project will develop and deliver a series of business readiness activities prior to the full implementation of a whole of Hume Rural Health Alliance Electronic Medical Record (EMR), ensuring all IT environments are ready for the roll-out | Delivery | Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-13 | 2025-12-31 | 2025-03-31 | 2025-04-30 | 0 | 200000 | 2025-05-01 |  | 2026-06-30 |  | 4200000 |  |  | Green | Green | Green | Green | The focus is on assessing EMR solution options against the region's EMR requirements
Q3 25-26 | Victorian Funds Management Corporation | VFMC | 4013 | Migration to cloud | Business and Industry | Systems Management | This project will transition our investment management system from an on-premises setup to a managed service offering, enhancing support, security and access to new functionality for our core technology platform. | Closed - Completed | Compliance (Non Financial), Risk Reduction (Non Financial) | 2026-03-31 | Agile | 2024-05-01 | 2024-05-28 |  | 2024-05-28 | 0 |  | 2024-12-01 |  | 2025-12-31 | 2026-03-31 | 2787000 |  | Amber | Amber | Amber | Amber | Green | Success migration to cloud. No major issues raised post migration. Project closure finalised
Q3 25-26 | State Revenue Office | SRO | 4045 | Revenue Management System - Foundation | Government and Economy | Development and Integration | The Revenue Management System (RMS) is the core backend software & technology managing tax-related activities for all customers. This initiative aims to establish the technical foundations to transition all revenue lines to utilise modern technology. | Closed - Completed | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) | 2026-03-31 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-02-03 | 2025-06-30 |  | 2025-07-01 | 1370114 |  | 2025-07-02 |  | 2026-06-30 | 2026-03-31 | 11665000 | 6850000 |  |  | Amber | Amber | Amber | Main deliverable (platform establishment) has been completed. After a re-plan remaining deliverables have been de-scoped. Project closure report prepared.
Q3 25-26 | Peninsula Care Group – Bayside Health | PEN Care Group | 4046 | Patient Flow Management Solution | Health | Organisational Management | Electronic Patient Flow Management streamlines patient movement, enhances collaboration, optimises access and demand management, reduces length of stay, improves communication, and increases workplace satisfaction and providing bed visibility. | Delivery | Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2023-09-08 | 2024-06-10 |  | 2024-08-07 | 50000 |  | 2024-12-20 |  | 2026-01-29 | 2026-04-30 | 2440404 |  | Green | Green | Green | Green | Green | Go live planned for the planned 29 April. UAT completed and signed off, key integrations built / activated and PVT activities underway largely complete. Cybersecurity and resourcing are confirmed training is well advanced and final go‑live readiness activities are nearing completion ahead of the Go/No‑Go decision.
Q3 25-26 | Victorian Legal Services Board & Commissioner | VLSBC | 4049 | Regulatory Management System | Law and Justice | Customer Relationship Management | A Regulatory Management System will be delivered. Replacement of legacy systems will improve delivery of service and modernisation of legal regulatory systems will support legal regulation in Victoria. | Postponed | Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2025-02-25 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-11-10 | 2023-08-22 |  | 2023-08-22 | 330680 |  | 2023-11-27 |  | 2026-05-01 |  | 18400000 |  | Red | Amber | Amber | Amber | Amber | Project delivery remains postponed. Tender responses were evaluated and two vendors are participating in a 10 week Proof of Concept (PoC) to assess their capability and ways of working. PoC outcomes will inform selection of preferred delivery partner. Revised delivery dates and budget are subject to confirmation with the preferred delivery partner once selected.
Q3 25-26 | Liquor Control Victoria | LCV | 4050 | Liquor Control Victoria ICT relocation and support for hardware and software | Law and Justice | Systems Management | The project will relocate on-premises servers to Richmond, decommission legacy hardware, and improve software and hardware support to enable business continuity | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-04-01 | 2024-12-01 | 2025-03-31 | 2025-03-31 | 0 |  | 2025-06-27 |  | 2026-01-31 | 2026-06-30 | 4373050 |  |  | Green | Green | Green | Green | The project is tracking well against budget and scope. The server relocation was completed in July 2025. Work is underway to enable the transition of systems and support from the Victorian Gambling and Casino Control Commission (VGCCC) to LCV. In Q2 2025-26, the end date was revised to align with the staged transition of approximately 40 ICT contracts from VGCCC to LCV. These contracts have varying end dates through to June 2026 and are being progressed based on criticality and business continuity requirements, with VGCCC cost reimbursements reducing as transitions are completed.
Q3 25-26 | Liquor Control Victoria | LCV | 4051 | New liquor platform for Liquor Control Victoria (delivered by Service Victoria) | Law and Justice | Customer Initiated Assistance | The project will deliver online licence application forms and a digital proof of age card. Efficiency and data quality will be enhanced, resulting in an improved user experience. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2022-07-01 |  | 2022-07-01 | 0 |  | 2022-10-01 | 2023-06-01 | 2026-06-30 |  | 4580000 | 6835000 | Green | Green | Green | Green | Green | Ten digital application forms are live on the Service Victoria website. An internal delivery partner is planning to launch a new digital proof of age card by the end of FY2026-27. Completion of work to digitise remaining LCV application forms has been scoped and costed, but not yet endorsed to proceed.
Q3 25-26 | South West Alliance of Rural Health | SWARH | 4053 | PACS Replacement | Health | Systems Management | Raplace the existing medial imaging Picture Archiving Communication System (PACS) used by Barwon Health Medical Imaging services. The current system is old and now unsupported with no capacity to upgrade to a new version. | Delivery | Efficiency/Productivity (Non Financial) |  | Waterfall | 2024-09-01 | 2025-01-16 |  | 2025-01-16 | 5000 |  | 2025-02-01 |  | 2025-10-30 | 2026-02-27 | 2295508 |  | Green | Green | Red | Red | Green | The project is on track to go live in Q4.
Q3 25-26 | Department of Jobs, Skills, Industry and Regions | DJSIR | 4055 | TAFE Customer Relationship Management (CRM) tool phase 2 | Education | Customer Relationship Management | The Office of TAFE Coordination and Delivery and the TAFE Network work to improve student experiences and industry outcomes. This phase launches a modern CRM to streamline enrolments at two TAFEs and boost industry engagement across six. | Postponed | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2025-11-28 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-17 | 2024-11-30 |  | 2025-02-19 | 1 |  | 2025-03-24 |  | 2025-11-30 |  | 4718530 |  | Green | Green | Amber | Amber | Amber | The project was placed on hold in November 2025 to reassess the remaining scope and dependencies. Further commercial discussion with vendor was required and project expected to resume in April 2026.
Q3 25-26 | Department of Transport and Planning | DTP | 4056 | Two-way radio | Transport and Vehicles | Communication | The project will leverage the state emergency radio network to implement two-way radio communication system, enabling enhanced safety of roadside operations through real-time location monitoring, duress alarm capability, and broader coverage. | Delivery | Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-01-01 | 2024-12-31 |  | 2025-01-06 | 0 |  | 2025-01-13 |  | 2025-12-01 | 2026-06-05 | 1507000 |  | Amber | Green | Green | Green | Green | The project is tracking well against the project scope, budget, and schedule.
Q3 25-26 | Department of Transport and Planning | DTP | 4058 | Transport Victoria website Release 2 and Release 3 | Transport and Vehicles | Development and Integration | The project will consolidate existing digital channels, delivering an enhanced customer experience that integrates all modes of transport, and enables longer term operational efficiencies by simplifying the underlying technical infrastructure. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-08-01 | 2025-01-06 |  | 2025-01-06 | 0 |  | 2025-01-13 |  | 2026-06-30 |  | 8119044 |  | Amber | Amber | Amber | Green | Green | The project status is green and release 3 activities tracking well against scope, budget, and schedule.
Q3 25-26 | Department of Transport and Planning | DTP | 4059 | Pay Portal for Public Transport Ticketing (PTT) | Transport and Vehicles | Development and Integration | The project will roll out a digital pay portal, enabling commuters to interact with the new public transport ticketing (PTT) system, providing faster and easier ticketing transactions for Victorian commuters. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-12-02 | 2025-02-28 |  | 2025-03-03 | 0 |  | 2025-03-03 |  | 2027-05-13 | 2027-06-30 | 16700000 |  | Amber | Amber | Amber | Green | Green | The project is reporting as green and is tracking well with its budget, scope, and schedule.
Q3 25-26 | South West Alliance of Rural Health | SWARH | 4060 | Citrix environment upgrade | Health | Systems Management | Upgrade to the current Long Term Service Release (LTSR) of Citrix to improve platform performance and supportability. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2026-03-31 | Waterfall | 2024-10-01 | 2024-10-30 |  | 2024-11-30 | 5000 |  | 2025-01-01 |  | 2025-05-31 | 2026-03-01 | 4467000 |  | Green | Green | Amber | Amber | Green | The project has been closed after successful implementation in March
Q3 25-26 | WorkSafe Victoria | WorkSafe | 4062 | Claims Systems Modernisation Initiative - Phase 1 | Employment, Skills and Workplace | Customer Relationship Management | The project will deliver a new claim management solution based on the already established CRM platform uplifting both usability & functionality to improve claims management. Phase 1 will roll out the functionality to WorkSafe's internal claims team. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-02-24 | 2025-02-24 |  | 2025-02-24 | 0 |  | 2025-02-25 |  | 2025-12-31 | 2026-06-30 | 36083436 | 40666844 | Green | Amber | Red | Amber | Red | Three of the four releases for Phase 1 have been delivered. Re‑baselining and delivery improvements have strengthened the program, supported by data‑driven assessments; however, additional time and funding are required to complete both the delivery and implementation into WorkSafe Victoria for Phase 1. A change request for schedule and budget increase is pending approval.
Q3 25-26 | South East Water | SE Water | 4065 | Enterprise Telephony Uplift | Environment and Water | Communication | Replacement and uplift of SEW's enterprise telephony solution across the organisation. | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial) |  | Waterfall | 2025-01-06 | 2025-02-28 |  | 2025-03-03 | 0 |  | 2025-03-03 |  | 2025-11-30 | 2026-05-29 | 1220000 |  | Green | Green | Green | Green | Green | All core project deliverables have been completed and project successfully delivered in FY26 Q3. Remaining technical activities to decommission old solution will extend into Q4 and expect to be completed by May '26.
Q3 25-26 | CenITex | CenITex | 4066 | Software Defined Datacentre (SDDC) Migration | Government and Economy | Assets/Materials Management | To design configure and consume an alternate VMWare based Private Cloud platform, and migrate Cenitex and customer applications from the current platform to the Multicloud solutions including a new IaaS Platform with built-in backup capability. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | PRINCE2 | 2025-02-21 | 2025-04-01 | 2025-02-27 | 2025-02-27 | 0 |  | 2025-11-30 | 2025-03-10 | 2025-11-30 | 2026-04-30 | 1431025 | 1677929 | Green | Green | Green | Green | Green | Project is tracking to plan.
Q3 25-26 | Peter MacCallum Cancer Centre | Peter MAC | 4069 | High Performance Compute and Storage infrastructure refresh and upgrade (HPC) | Health | Assets/Materials Management,Systems Management | The project will deliver a refreshed and upgraded High Performance Compute (HPC) and Storage infrastructure for Peter Mac Research, replacing outdated hardware with advanced, high-performance equipment. | Initiated |  |  | PRINCE2 | 2024-10-01 | 2025-11-28 | 2026-06-30 |  | 0 | [12 empty] | Business case has been drafted and is planned to be presented to the Board to seek funding approval.
Q3 25-26 | Peter MacCallum Cancer Centre | Peter MAC | 4070 | Network Infrastructure Refresh | Health | Assets/Materials Management,Systems Management | The project will deliver a comprehensive refresh of Peter Mac's network infrastructure, including all physical components and the provision of layer 2 and layer 3 services across the WAN, LAN, and WLAN. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-10-01 | 2025-10-31 | 2025-07-23 | 2025-07-23 | 0 |  | 2025-10-01 | 2025-12-10 | 2026-12-31 | 2026-12-04 | 6773270 | 2525426 |  |  |  | Green | Green | The project continues to track against agreed timelines and milestones with financial performance remaining on budget.
Q3 25-26 | State Revenue Office | SRO | 4071 | Inbound Correspondence | Government and Economy | Development and Integration | This Project focuses on inbound communication – phone calls, forms, and emails initially. It aims to enhance data quality, streamline processes, and improve communication channels to deliver a seamless customer experience and boost staff productivity | Closed - Completed | Compliance (Non Financial), Cost Avoidance (Financial), Customer Satisfaction (Non Financial) | 2026-03-31 | Agile | 2025-02-01 | 2025-06-30 |  | 2025-07-01 | 181072 |  | 2025-07-02 |  | 2026-06-30 | 2026-03-31 | 5390331 | 3339000 |  |  | Amber | Amber | Amber | Delivered features on Genesys Roadmap. Decision made to combine remaining scope with another project due to synergies with resourcing.
Q3 25-26 | State Revenue Office | SRO | 4072 | Enabling Technology | Government and Economy | Development and Integration | This project is establishing enabling technologies and processes to enhance security and uplifting capabilities for future project delivery. | Closed - Completed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) | 2026-03-31 | Agile | 2025-02-01 | 2025-06-30 |  | 2025-07-01 | 294163 |  | 2025-07-02 |  | 2026-03-27 | 2026-03-31 | 1232673 |  |  |  | Amber | Amber | Amber | Main deliverable - Identity Access Management Plan (IDAM) - completed. After a re-plan remaining items have been de-scoped.
Q3 25-26 | Western Health | WH | 4073 | Network Switches Asset Replacement 23/24 | Health | Development and Integration | End of life replacement of network switches at Sunshine Hospital to ensure network reliability, supportability and security, enabling WH to deliver services for the future, high quality connected care and better health outcomes for our community. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2024-01-02 | 2024-02-23 |  | 2024-02-26 | 0 |  | 2024-11-18 |  | 2025-08-26 | 2026-05-29 | 4156643 |  | Green | Green | Green | Green | Green | Phase 3 (final) has resumed following Footscray Hospital relocation.
Q3 25-26 | Melbourne Water | MELB Water | 4076 | Mobile Device Management | Environment and Water | Assets/Materials Management | Enhance support for flexible remote working arrangements for staff improving management of corporate devices by implementing a system that effectively addresses the challenges of remote device management and supports Bring your own device policies. | Postponed |  | 2025-09-08 | PMBoK | 2024-08-21 | 2025-05-21 | 2026-09-12 |  | 0 | [5 empty] | 0 | [6 empty] | As at 20251231: The project has been deferred and is now scheduled for delivery in FY2027.
Q3 25-26 | Department of Education | DE | 4078 | Academy Customer Relationship Management_Course Management | Education | Customer Relationship Management,Data Management,Reporting | The project will improve business processes focusing on the Victorian Academy of Teaching and Leadership’s relationship management and enables the effective marketing management delivery and reporting of professional learning to Victorian educators. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-01 | 2024-08-16 |  | 2024-08-30 | 0 |  | 2025-01-28 |  | 2026-08-13 |  | 9649702 |  | Green | Green | Amber | Amber | Amber | The project is reporting Amber due to replanning activities of some workstreams. The project end date remains unchanged and costs are currently within budget.
Q3 25-26 | Yarra Valley Water | YV Water | 4080 | IT Systems Monitoring & Logging | Environment and Water | Security Management ,Systems Management,Visualisation | Implement a platform which will encompass comprehensive monitoring, logging, synthetic monitoring, and a unified monitoring dashboard to enhance security, improve reliability, and visibility into our IT infrastructure and application performance. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-02 | 2025-01-31 |  | 2025-02-04 | 48000 |  | 2025-02-04 |  | 2027-02-28 |  | 1334300 |  | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q3 25-26 | Victorian Fisheries Authority | VFA | 4088 | Licensing Quota Management System | Business and Industry | Customer Initiated Assistance,Data Management,Management of Process ,Reporting ,Systems Management | The project will digitise the commercial quota management, licencing and permit application process, by delivering a self-service mobile application for commercial fishers and permit holders, improving access to data and support from VFA. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-06-01 | 2022-11-14 |  | 2024-07-14 | 0 |  | 2025-01-14 |  | 2026-06-30 |  | 1450000 |  | Green | Green | Green | Green | Green | The project is progressing well and remains on track against key milestones.
Q3 25-26 | Victorian Rail Track | VicTrack | 4090 | Cyber Security Roadmap | Transport and Vehicles | Security Management | To uplift the cyber-security maturity of VicTrack, fulfil our regulatory obligations under VPDSS and the Essential 8, and secure critical assets against cyber threats. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-01-31 | 2025-03-19 |  | 2025-03-19 | 0 |  | 2025-03-19 |  | 2028-06-30 |  | 12530000 |  |  | Amber | Green | Green | Green | The cyber security uplift program is progressing well. Although detailed planning has taken a little longer than anticipated, good progress has continued across the program. A number of important security initiatives have already been implemented resulting in measurable improvements to VicTrack’s cyber security and compliance.
Q3 25-26 | Victorian Rail Track | VicTrack | 4091 | Project Backup Server & Storage Replacement | Transport and Vehicles | Data Management | Refresh of the current storage and backup solution to improve storage capacity, introduce additional security features, uplift to provide better resilience against modern cyber-attacks. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-01-06 | 2025-06-27 |  | 2025-06-27 | 0 |  | 2025-06-27 |  | 2026-06-30 |  | 1594439 |  |  | Amber | Green | Green | Green | Project Progressing
Q3 25-26 | Victorian Public Sector Commission | VPSC | 4102 | Cloud Migration and Transformation | Government and Economy | Analyses and Statistics | Modernising VPSC’s analytics by migrating to a secure cloud platform using Microsoft Fabric, Power Platform, and Entra ID to streamline reporting, improve data quality, and enable scalable, AI-driven workforce insights. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-08-29 | 2024-12-19 |  | 2024-12-19 | 0 |  | 2025-03-21 |  | 2026-06-30 |  | 1773267 | 2097607 |  | Green | Green | Green | Green | The VPSC Cloud Transformation project is progressing well. This period, the team has nearly finalised the build of the new data hub for government users and continues to progress work on the technical configuration for data ingestion.
Q3 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4103 | Common Technology Platform (CTP) Program - Phase 3 | Government and Economy | Security Management | The CTP Program was established to deliver the technology strategy via a 3-year phased approach. Phase 3 will uplift the 2 remaining platforms (spatial and digital) and enhance platforms established during previous phases. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-02-03 | 2024-12-12 |  | 2025-03-21 | 0 |  | 2025-03-21 |  | 2026-06-30 |  | 1798000 |  |  | Green | Green | Green | Green | The project is on track as per the endorsed baseline delivery plan and budget.
Q3 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4104 | Cyber Security Uplift Program | Government and Economy | Security Management | Cyber Security program will deliver a set of controls, processes and education that aligns with the Victorian Cyber Security Strategy and leverages the WoVG capabilities to reduce and address cyber security risks. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-02-01 | 2024-12-12 |  | 2025-03-21 | 0 |  | 2025-03-21 |  | 2027-06-30 |  | 6034000 |  |  | Green | Green | Green | Green | The project is on track as per the revised delivery plan and budget.
Q3 25-26 | Hume Rural Health Alliance | HRHA | 4106 | Cyber Security Maturity Uplift implementation | Health | Security Management | The purpose of this project is to ensure a regional uplift in Cybersecurity through reducing risks uplifting governance and risk management practices and alignment to the Department of Health's Cyber Security Assurance Framework. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-10-02 | 2024-02-12 |  | 2024-02-12 | 0 |  | 2024-07-01 |  | 2027-06-30 |  | 1950000 |  |  | Green | Green | Green | Green | Project activities remain on track.
Q3 25-26 | WorkSafe Victoria | WorkSafe | 4107 | Claims Management System Uplift for Workplace Injury and Rehabilitation Compensation (WIRC) Amendment Act | Employment, Skills and Workplace | Systems Management | This project will operationalise the proposed WIRC Act Amendment Bill (now WIRC Amendment Act 2025) and uplift existing claims management systems to ensure high-quality service and improve support to users of Victoria’s workers compensation scheme. | Delivery | Compliance (Non Financial), Increased Quality (Non Financial), Social Improvement (Non Financial) |  | Waterfall | 2024-11-25 | 2025-03-05 |  | 2025-03-05 | 0 |  | 2025-03-05 |  | 2026-12-15 |  | 1728437 |  |  | Amber | Green | Green | Amber | The project is reporting Amber as it seeks a schedule extension to align implementation of a project stream with changing priorities. A change request is underway and pending approval to return the project to Green.
Q3 25-26 | South East Water | SE Water | 4108 | Service Management System Implementation | Environment and Water | Systems Management | Replacement and transformation of SEW's internal Service Management solution used across multiple business functions. This project will deliver uplift in internal capabilities and deliver efficiencies through streamlining service management processes | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial) |  | Waterfall | 2024-10-01 | 2025-03-28 |  | 2025-04-01 | 0 |  | 2025-04-01 |  | 2026-01-30 | 2026-04-30 | 1380500 |  |  | Green | Amber | Green | Red | Project reporting RED due to lack of scope and schedule clarity for phase 2. Mitigations are underway to finalise phase 2 scope so that schedule and budget can be re-baselined.
Q3 25-26 | WorkSafe Victoria | WorkSafe | 4111 | Cheques Migration Strategy | Employment, Skills and Workplace | Financial Management | This project will operationalise the Victorian Government directive to cease cheque payments and will implement complex system changes to ensure faster payments for injured workers and providers and reduce administration costs. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial) |  | Waterfall | 2024-10-08 | 2025-05-27 |  | 2025-05-28 | 0 |  | 2025-05-28 |  | 2027-12-31 |  | 2143701 |  |  | Green | Green | Green | Red | Work is underway for this project, which is progressing in line with required delivery timeframes. The full scope of system changes is now confirmed which has identified additional system requirements. A change request is pending approval in Q4 to seek funding to deliver these requirements. Approval will return the project to Green.
Q3 25-26 | Department of Transport and Planning | DTP | 4112 | Records Management Uplift - Stage 2b | Transport and Vehicles | Records Management | The project will review and refine the records management environment and consolidate organisational data into Records365, standardising and uplifting the records management solution & practices across the DTP. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-07 | 2025-07-10 | 2025-12-01 | 2025-12-01 | 0 |  | 2025-12-01 |  | 2026-06-30 |  | 3400000 |  |  |  |  | Amber | Amber | The project has reported an amber status due to schedule and delivery risks related to identified technical issues and resourcing factors. The project however is on track with the activities planned to continue testing to complete soft launch of the solution.
Q3 25-26 | Melbourne Water | MELB Water | 4117 | Data Lake | Environment and Water | Data Management | Build a data warehouse solution that is scalable, secure and evolves to meet growing business insights and reporting needs of Melbourne Water. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2024-02-01 | 2024-04-02 |  | 2024-04-02 | 0 |  | 2024-04-02 |  | 2026-05-15 |  | 3301197 | 3212274 |  | Amber | Green | Green | Green | As at 20260331: Data migration complete, report migration on track.
Q3 25-26 | CenITex | CenITex | 4118 | Cenitex Office Relocation | Government and Economy | Assets/Materials Management | Make 35C fit for Cenitex purpose to undertake its core role in providing support and technology solutions for customers across WoVG. With a lease end of Jun’25 at 80C, the timeline to undertake this work is tight with a early June relocation target. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | PRINCE2 | 2025-03-20 | 2025-03-20 |  | 2025-03-20 | 0 |  | 2025-03-20 |  | 2025-10-31 | 2026-06-30 | 2570677 | 2567674 |  | Green | Green | Green | Green | Project is tracking to plan.
Q3 25-26 | Victorian Rail Track | VicTrack | 4120 | HCI Replacement Project | Transport and Vehicles | Systems Management | Hyper-converged infrastructure (HCI) utilises physical servers to create a software-defined IT environment that virtualises all components of traditional hardware-based systems. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-01 | 2025-05-16 |  | 2025-05-16 | 0 |  | 2025-05-16 |  | 2026-12-31 |  | 9000000 |  |  | Green | Green | Green | Amber | Change Request need to address a risk for Deliverable 2 of VMWare being financially unsustainable.
Q3 25-26 | Department of Families, Fairness and Housing | DFFH | 4121 | Replacement Document and Records Management System | Community Services | Records Management | Replace the existing out-of-support records management system (Housing TRIM) with a new, supported record keeping system that uses cloud storage and provides staff with improved business functionality. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-11-29 | 2025-04-09 |  | 2025-04-09 | 351860 |  | 2025-04-09 |  | 2026-03-31 |  | 5898928 | 5898928 |  | Amber | Amber | Green | Amber | Project has successfully delivered core functionality. Project is Amber due to delays in finalising new back up design. Cost and schedule are currently being reviewed and project expected to complete in next reporting period.
Q3 25-26 | Melbourne Water | MELB Water | 4127 | Asset Maintenance application upgrade | Environment and Water | Tracking and Workflow | Upgrade of our asset management system to a modern platform that enhances scalability, security, and usability. Ensuring ongoing support beyond 2025, reduces operational risk, and provides advanced features and improved reporting. | Initiated |  |  | Waterfall | 2023-10-09 | 2026-04-09 | 2026-08-31 |  | 0 | [12 empty] | As at 20260331: Continuing with drafting the business case, with the current focus on defining and assessing potential delivery scenarios
Q3 25-26 | Melbourne Water | MELB Water | 4128 | SCADA For Our Future | Environment and Water | Assets/Materials Management | A next-generation system to enhance real-time monitoring, decision-making, and automation across our water, sewerage, & drainage networks. Providing advance alarm and incident management to meet growing service complexity and performance expectations | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2019-10-25 | 2025-11-25 |  | 2025-11-25 | 0 |  | 2025-11-25 |  | 2028-08-28 |  | 39352377 |  |  |  |  | Red | Red | As at 20260331: Project rebaseline has been approved and the project continues to work through targeted actions to return to green.
Q3 25-26 | Melbourne Water | MELB Water | 4129 | Dam Surveillance Information System | Environment and Water | Management of Process | Replacement of an outdated system with a modern, fully supported solution that brings enhanced automation, smarter features, and improved reporting—empowering the Water Control teams to work more efficiently and make better-informed decisions | Delivery | Risk Reduction (Non Financial) |  | Agile | 2023-05-10 | 2024-12-10 |  | 2024-12-10 | 0 |  | 2024-12-10 |  | 2026-10-05 | 2027-04-01 | 3340950 |  |  | Amber | Green | Green | Green | As at 20260331: Vendor on boarded and detailed deployments planning in progress.
Q3 25-26 | Treasury Corporation of Victoria | TCV | 4130 | Infrastructure IT Refresh | Government and Economy | Systems Management | Deployment of a resilient IT infrastructure with cloud-based disaster recovery and secure remote access. It will enhance system uptime, disaster recovery speed and secure remote work capabilities whilst ensuring continuity of TCV’s critical systems. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial) |  | Waterfall | 2025-04-01 | 2025-04-22 |  | 2025-04-22 | 0 |  | 2025-06-20 |  | 2025-11-30 | 2026-05-31 | 1476000 | 1536000 |  | Green | Green | Green | Green | Working from anywhere implementation is underway with pilot testing, disaster recovery and business continuity plan setup and testing scheduled for next period. Production user acceptance testing and full deployment anticipated for end of May.
Q3 25-26 | Western Health | WH | 4132 | Workstation on Wheels (WoW) replacement | Health | Systems Management | This project will replace end-of-life hardware for Workstations on Wheels (WoW) with updated hardware and software, enabling patient record access and update for doctors and nurses to provide quality patient care. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2025-02-24 | 2025-06-05 |  | 2025-06-06 | 0 |  | 2025-06-23 |  | 2025-11-28 | 2026-04-30 | 2400000 |  |  | Green | Green | Green | Green | Implementation delayed by technical issues (January) and Footscray Hospital relocation in February/March. Currently deploying 15 units weekly of 95 remaining. The revised delivery End Date has been reviewed and approved by the steering committee.
Q3 25-26 | Western Health | WH | 4134 | Network Switches Asset Replacement 24/25 | Health | Systems Management | End of life replacement of network switches across WH sites to ensure network reliability, supportability and security, enabling WH to deliver services for the future, high quality connected care and better health outcomes for our community. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2024-01-02 | 2025-04-23 |  | 2025-04-24 | 0 |  | 2025-08-04 |  | 2026-05-25 | 2026-07-24 | 2353000 |  |  |  | Green | Green | Green | Implementation proceeding on track..
Q3 25-26 | Holmesglen Institute of TAFE | Holmesglen TAFE | 4135 | ICT Infrastructure (Servers, LAN, Wifi, Telephony) & Data Centre Refresh | Employment, Skills and Workplace | Systems Management | The project will replace and upgrade the end-of-life ICT infrastructure and data centre with enhanced cyber security protection, minimising security risks and enabling faster, advanced technology access for students and staff at Holmesglen. | Delivery | Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2025-03-26 | 2025-07-28 | 2025-09-30 | 2025-10-07 | 0 |  | 2025-10-17 |  | 2027-12-17 |  | 32000000 |  |  |  |  | Green | Green | The ICT Infrastructure Refresh Project progressed in line with the delivery plan and remains on track. Preparation of the NextDC data centre was completed, including racking, power and fibre connectivity, and infrastructure hardware deliveries continued as scheduled. Detailed solution design activities commenced and will continue through to July 2026. Change management activities were initiated, including staff updates via internal newsletters and ongoing engagement with stakeholders. Regular steering committee meetings were held to oversee delivery. The first Webex Board installation was completed, providing an early visible improvement ahead of the broader rollout.
Q3 25-26 | Western Health | WH | 4136 | Automatic Dispensing Cabinets (ADC) | Health | Systems Management | Implementation of automated medication cabinets replacing manual shelving for electronically tracked & secure storage of Imprest medications, enabling timely & safe medication access for staff at new Footscray Hospital delivering quality patient care | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2019-05-14 | 2019-09-04 |  | 2020-01-06 | 0 |  | 2024-03-04 |  | 2026-06-28 |  | 2502072 |  |  | Green | Green | Green | Green | Project on track
Q3 25-26 | Southern Metropolitan Cemeteries Trust | SMCT | 4137 | PeoplePro (Human Resources Information System) | Health | Human Capital / Workforce Management ,Human Resources | SMCT's current human resources system is no longer vendor-supported. A replacement system will provide greater efficiencies, employee experience, decision-making and information through more seamless data management and improved processes. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) | 2026-03-31 | Waterfall Agile hybrid | 2022-07-28 | 2024-10-22 |  | 2024-10-22 | 311733 |  | 2024-11-18 |  | 2027-06-30 | 2026-03-31 | 1932705 | 1150994 |  | Amber | Green | Green | Green | Project is now closed with the objectives of the revised scope having been delivered.
Q3 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4140 | Permissions Application Project | Environment and Water | Collaboration ,Customer Initiated Assistance,Customer Relationship Management,Tracking and Workflow | The project will deliver a new system to replace the current Wildlife Licence System, which is now at end-of-life. The new system will feature a self-service portal designed to improve user experience, streamline processes, and enhance compliance. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-01 | 2026-04-01 | 2026-04-30 |  | 390151 | [12 empty] | The project encountered minor delays during the tender evaluation process which has since been completed. The project is currently in the process of completing the RFT process with the new vendor contract endorsement expected by the end of April 2026. The next phase, the development phase to deliver the new permit and licensing application is expected to occur in May 2026.
Q3 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4142 | Emergency Resource Management System (ERMS) Project | Emergencies and Safety | Customer Initiated Assistance,Human Capital / Workforce Management | The project will deliver a fit-for-purpose ERMS to reduce the impact of bio-security, agriculture, and other emergencies on the Victorian community and environment through timely and effective preparedness, response, relief, and recovery services. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - Waterfall and Agile | 2025-07-01 | 2026-01-30 | 2025-12-08 | 2025-12-08 | 240000 |  | 2025-12-09 |  | 2027-05-30 |  | 2534323 | [5 empty] | Green | The procurement phase has been completed with Discovery workshops commencing in April for feature and integration work.
Q3 25-26 | Court Services Victoria | CSV | 4147 | VCAT Long Term Accommodation (LTA ) - Technology Component | Law and Justice | Assets/Materials Management,Development and Integration | The objective of the project requires the preparation of the new VCAT Long Term Accommodation site to be a member of the Cenitex GSP INTERNAL Network for use by CSV/VCAT Staff and Customers. | Delivery | Customer Satisfaction (Non Financial) |  | Waterfall and Agile | 2025-05-06 | 2025-05-06 |  | 2025-05-06 | 0 |  | 2025-07-01 |  | 2026-04-30 |  | 1178028 |  |  |  | Green | Green | Green | Cenitex network build completed.
Q3 25-26 | Barwon Region Water Corporation | BR Water | 4148 | C1419 - Smart Networks Water - Proof of Value (POV) | Environment and Water | Assets/Materials Management | The Smart Networks Water Project will procure, implement and monitor Digital Meters in a series of locations within the Barwon region to capture the benefits, costs, resourcing and effort to inform a Mass Rollout Business Case for PS28. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-10 | 2023-11-21 |  | 2023-11-21 | 376900 |  | 2024-03-04 |  | 2028-06-30 |  | 9490000 |  |  |  | Amber | Amber | Amber | The Smart Networks Water project delivery commenced in March 2024. The project has continued to progress significantly with key deliverables including Digital Meter orders being placed the Fieldforce model being confirmed and key processes and systems to support the deployment being progressed. Barwon Water are currently monitoring international delivery lead times with suppliers and potential impacts.
Q3 25-26 | Barwon Region Water Corporation | BR Water | 4149 | C1441 - Smart Networks Sewer - Proof of Value (POV) | Environment and Water | Assets/Materials Management | The Smart Networks Sewer Project will trial, implement and monitor a series of Sewer Sensors and an analytics capability to capture the benefits, costs, resourcing and effort to inform a Mass Rollout Business Case for PS28. | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-10 | 2023-11-23 |  | 2023-11-23 | 251300 |  | 2024-03-04 |  | 2028-06-30 |  | 7170000 |  |  |  | Green | Green | Green | The Smart Networks Sewer Proof of Value project commenced in March 2024 The project continues to progress with the ongoing trialling of both sewer sensors in higher risk locations and the assessment of an analytics capability to support Barwon Water in forming a predictive view of sewer network behaviour. The Trial is due for completion in Q4 prior to full POV deployment.
Q3 25-26 | Transport Accident Commission | TAC | 4151 | Continuous Delivery 2026 | Transport and Vehicles | Systems Management | The project will deliver enhancement to TAC’s Claims Management system to uplift performance, reduce risk, and improve user experience, ensuring sustained business value and responsiveness to priorities | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2025-07-01 | 2025-07-01 |  | 2025-07-01 | 0 |  | 2025-07-01 |  | 2026-06-30 |  | 5404953 |  |  |  | Green | Green | Green | Next quarter will prioritise incremental enhancements through the Continuous Delivery model with strong focus on legislative and Protocols‑driven change. Key work includes refining and stabilising Protocols functionality from Release 26.3 and iteratively improving eForms workflows and case management to strengthen compliance data quality and operational efficiency. The team will address emerging business priorities while maintaining a consistent release cadence. Ongoing collaboration with stakeholders will ensure changes support operational readiness and benefits realisation. Preparation will continue for future alignment with broader Claims Platform initiatives ensuring dependencies are understood and effectively managed within the delivery plan.
Q3 25-26 | Transport Accident Commission | TAC | 4152 | Microsoft Program of Work for Enterprise Readiness (M-POWER) | Transport and Vehicles | Systems Management | This project will establish a dedicated Microsoft tenancy & cloud infrastructure for TAC, streamlining enterprise systems using a modern platform & minimising the risks associated with legacy technologies to enable more efficient services to clients. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-07-01 |  | 2025-07-01 | 0 |  | 2025-07-01 |  | 2027-12-31 |  | 20000000 |  |  |  | Green | Green | Green | The program delivered a strong quarter, maintaining momentum across all streams as it advances into full execution with core platform and delivery foundations in place. The schedule realignment reflects a disciplined, enterprise‑focused approach that prioritises long‑term outcomes. Increased emphasis on business readiness, testing, and operational stability positions the program for success, with risks well understood and actively managed in alignment with business cycles. Overall, the program is well placed to deliver a secure, resilient, and future‑ready digital foundation for TAC, and confidence remains high in achieving a successful, sustainable go‑live in September 2026.
Q3 25-26 | Melbourne Water | MELB Water | 4153 | Web Enhancements | Environment and Water | Content Management | Additional features to be added to MW website to deliver core functions. | Delivery | Customer Satisfaction (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2025-02-25 | 2026-11-10 | 2026-01-29 | 2026-01-29 | 0 |  | 2026-01-29 |  | 2026-06-09 |  | 1507806 | [5 empty] | Amber | As at 20260331: Business case approved. Amber due to potential for delivery risk to be realised associated with resource constraints. Project team implementing measures to reduce likelihood of this being realised.
Q3 25-26 | Yarra Valley Water | YV Water | 4154 | Finance Transformation | Environment and Water | Financial Management | Implementation of a new Finance system with integrations, including uplift to operating model. Key outcomes being risk reduction achieved by replacing EoL system plus aligning to business priorities of operational efficiencies and UX improvements. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-09-01 | 2026-08-28 |  |  | 1760200 | [12 empty] | The project has completed Expression of Interest (EOI) in the beginning of January successfully, with shortlisted vendors. This was followed by the Request for Tender (RFT) released in March. Currently, the project is progressing well in the Tender Evaluation stage and aiming for preferred tenderer to be selected end of September.
Q3 25-26 | Melbourne Water | MELB Water | 4155 | OS Upgrade | Environment and Water | Systems Management | Upgrading all laptops and PC's to a new operating system. | Delivery | Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2024-10-24 | 2025-07-25 |  | 2025-07-25 | 0 |  | 2025-07-25 |  | 2026-02-27 | 2026-05-01 | 1308000 | 1260625 |  |  | Green | Green | Amber | As at 20260331: Majority roll-out complete. Amber status due to an issues in establishing image for new devices which may impact overall schedule.
Q3 25-26 | Yarra Valley Water | YV Water | 4156 | Customised Collections | Environment and Water | Financial Management | This project will deliver a Customised Collections solution in Oracle CC&B, uplifting YVW’s ability to segment customers and tailor debt management. It will reduce bad debt and improve outcomes for customers and the organisation. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Agile | 2020-08-01 | 2025-09-17 |  | 2025-09-18 | 888100 |  | 2025-09-18 |  | 2026-05-18 |  | 1119197 |  |  |  | Green | Amber | Amber | Delivery is in progress. Due to extended scope and underestimation of effort a change request is required to revise the schedule and budget
Q3 25-26 | Yarra Valley Water | YV Water | 4157 | Digital Metering – Customer Solutions for New Segments | Environment and Water | Communication,Content Management,Customer Relationship Management,Development and Integration | The project will enable the implementation of the more complex customer journeys inclusive of the process uplifts required to facilitate the installation of digital meter to more complex and larger scale customer types. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-06-01 | 2025-08-31 |  | 2025-09-01 | 270000 |  | 2025-09-01 |  | 2026-06-30 |  | 2169620 |  |  |  | Green | Green | Green | Project tracking well against scope. Core milestones pertaining to digital meter customer types deployed. Iterative design and development work continues with no critical issues. Budget and scope on track, schedule is expected to be extended due to iterative nature of project.
Q3 25-26 | WorkSafe Victoria | WorkSafe | 4158 | Safety CRM (Customer Relationship Management) | Employment, Skills and Workplace | Customer Relationship Management | This project will modernise safety inspection and notification systems to improve frontline efficiency and stakeholder experience. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-14 | 2025-05-28 |  | 2025-05-28 | 0 |  | 2025-07-01 |  | 2026-06-30 |  | 4863898 | 4994037 |  |  | Green | Green | Green | The project is tracking Green with work of Quarter 3 being delivered as planned in the increment planning. The budget is also tracking Green for the last quarter.
Q3 25-26 | Department of Government Services | DGS | 4159 | Children's Digital Program | Government and Economy | Development and Integration | Developing an end-to-end digital experience from birth to school that provides parents with a digital family organiser to manage key information about their child. | Delivery | Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-06-03 | 2025-06-24 |  | 2025-06-24 | 0 |  | 2025-06-25 |  | 2026-09-30 | 2026-11-04 | 17003000 |  |  |  | Amber | Amber | Amber | The program status is Amber due to technical design complexities relating to Phase 2 scope.
Q3 25-26 | Department of Health | DH | 4160 | Data Loss Prevention Phase 1 | Health | Security Management | Conduct detailed current state analysis of DH and DFFH Data Loss Protection (DLP) capability for emails classified as 'Protected' and 'Cabinet-in-Confidence' and implement improved DLP controls to emails, reducing risk of accidental data loss. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-10-27 | 2025-10-22 | 2025-10-22 | 74200 | 96525 | 2025-10-23 |  | 2026-06-30 |  | 1407475 |  |  |  |  | Amber | Amber | Project is progressing but is reporting an amber health status due to delay in procuring required services.
Q3 25-26 | V/Line Corporation | V/Line | 4161 | TrackR Stabilisation | Transport and Vehicles | Systems Management | The objective of the project is to stabilise V/Line’s critical train and fleet operations system (TrackR). Stabilisation of TrackR will result in increase in reliability and performance of the system’s key workflows, and improve service delivery. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-09-30 |  | 2025-10-01 | 57000 |  | 2025-10-01 |  | 2027-12-31 |  | 3230000 |  |  |  |  | Green | Green | Project is on track, with no major roadblocks or issues to date.
Q3 25-26 | Goulburn-Murray Rural Water Corporation | GMR Water | 4162 | PC/Laptop Replacement | Environment and Water | Assets/Materials Management | This project will deliver 550 new PCs and laptops, enhancing Goulburn Murray Water’s IT capability by improving performance and reliability, enabling a more productive, digitally enabled workforce for better service delivery. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2025-03-25 | 2025-09-02 |  | 2025-09-02 | 0 |  | 2025-09-02 |  | 2028-06-30 |  | 1300000 |  |  |  | Green | Green | Green | The project has commenced with planning and procurement activities now underway. Initial assessments of staff requirements have been completed and deployment scheduling and coordination with relevant departments are in progress.
Q3 25-26 | Melbourne Health | Melb H | 4164 | Computer Assisted Coding Solution | Health | Management of Process | Computer-assisted coding software, for the entire clinical coding process- to streamline processes, capture complexity, optimise reimbursement, ensure data compliance and make data-informed decisions. | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | PRINCE2 | 2025-03-03 | 2025-06-19 |  | 2025-06-19 | 0 |  | 2026-01-01 | 2026-02-17 | 2026-12-31 | 2027-04-30 | 1007474 | 1728777 |  |  |  |  | Green | Project is on track.
Q3 25-26 | Melbourne Health | Melb H | 4165 | E-referral for outpatient specialist clinics | Health | Development and Integration | Implementing an Electronic Medical Record integrated e-Referral system across the 4 Parkville Precinct hospitals, which enhances management of external GP/Specialists referrals to outpatient specialist clinics and improves patient data quality | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2025-03-03 | 2025-03-05 |  | 2025-03-05 | 0 |  | 2025-09-01 |  | 2026-08-31 |  | 1180854 |  |  |  | Green | Green | Green | Project is on track.
Q3 25-26 | CenITex | CenITex | 4166 | DOH Modern Desktop Implementation | Government and Economy | Assets/Materials Management | The project will support DoH and DFFH to modernise workforce desktop environment, streamlining service provision and enabling workforce efficiency and productivity through modern technology. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2025-07-24 | 2025-07-24 |  | 2025-07-24 | 0 |  | 2025-07-31 |  | 2026-06-30 |  | 1949180 |  |  |  | Green | Green | Green | Project is tracking to plan.
Q3 25-26 | Barwon Region Water Corporation | BR Water | 4167 | C1073 - Information & Records Management (IRM) | Environment and Water | Content Management | This initiative aims to enhance Barwon Water Group's Information Records Management (IRM) capability through a phased maturity uplift. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-01 | 2025-09-08 |  | 2025-09-08 | 537000 |  | 2025-09-08 |  | 2026-10-31 | 2026-12-31 | 580000 |  |  |  | Green | Green | Red | Deployment of the records governance software, Objective Gov365, has been delayed due to several software product issues. The project is working with the system integrator to seek resolution as soon as possible.
Q3 25-26 | Bendigo Kangan Institute of TAFE | BKI TAFE | 4168 | Artificial Intelligence for Recognition of Prior Learning | Employment, Skills and Workplace | Development and Integration | On behalf of the Victorian TAFE Network, BKI will pilot an artificial intelligence (AI) solution to uplift the assessment capability in the Recognition of Prior Learning (RPL), enabling a more efficient processing time for assessors and applicants. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-08-28 | 2025-12-31 | 2026-05-31 |  | 180000 | 300000 | [11 empty] | The Service Design Business Capability phase has been completed, providing a validated foundation of current-state insights and user needs and AI capability gaps. Ongoing scope refinement activities with the Office of TAFE Coordination and Delivery (OTCD) are ensuring alignment with Victorian Government priorities, with particular attention to defining clear outcomes, governance settings, and potential pathways for scaled implementation to inform a broader AI-enabled Lead TAFE model.
Q3 25-26 | South East Water | SE Water | 4170 | Acumen Phase 3 | Environment and Water | Business Intelligence | Acumen Phase 3 will deliver remaining data sources into new Acumen platform. A subset of Data Modelling will be undertaken to support the report development required to decommission the legacy data warehouse and reporting environment. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2025-05-01 | 2025-07-28 |  | 2025-07-30 | 0 |  | 2025-07-30 |  | 2026-12-18 |  | 8220471 |  |  |  | Green | Green | Amber | Project reporting AMBER due to some rework required for some Phase 3 data ingestions. Timeframes remain tight for remaining priority data ingestion in scope for Phase 3.
Q3 25-26 | Victorian Gambling and Casino Control Commission | VGCCC | 4172 | Compass - Gambling License System (GLS) replacement project - Release 2 | Law and Justice | Customer Relationship Management | Release 2 will deliver the remaining components of the new regulatory system to replace the legacy license management system. The project will remediate and uplift VGCCC's ICT infrastructure improving ICT capabilities. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial) | 2026-03-23 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-14 | 2025-09-12 |  | 2025-09-12 | 120000 |  | 2025-09-15 |  | 2026-03-23 |  | 2541000 |  |  |  | Green | Green | Green | This project went live on 17 March 2026. Transition to the new system was successful, with all issues identified during the hypercare period resolved. The project is now completed.
Q3 25-26 | Department of Health | DH | 4173 | Maternal and Child Health IT System | Health | Customer Relationship Management | Deliver a new statewide IT system to support the delivery of Maternal Child Health services, providing additional functions as well as accommodating future growth in service delivery and customer base. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Agile | 2025-03-03 | 2025-05-02 |  | 2025-05-02 | 163733 |  | 2025-05-02 |  | 2027-06-30 |  | 12286267 | 12286267 |  |  | Green | Amber | Amber | Project is progressing but still reporting an amber health status due to development issues impacting schedule. Contingencies have been introduced to increase the speed of design and build work.
Q3 25-26 | Ambulance Victoria | AVS | 4174 | Mobile Data Network Rural (MDNR) | Health | Communication | The project will upgrade and expand communication services for emergency responders in rural Victoria, improving real-time data access to enable dispatch efficiency, enhancing paramedic safety and better patient care. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-10-08 | 2022-10-21 |  | 2022-10-21 | 24043 |  | 2024-11-14 |  | 2027-05-30 |  | 24971040 |  |  |  | Green | Red | Red | The project is reported as Red due to issues identified during dispatch application testing, which delayed the planned go‑live date. The Dispatch Application go-live delay is not expected to impact the overall project end date, 30 May 2027. The project schedule will be rebaselined to reflect the revised go-live date by the end of June 2026 (Q4) alongside a formal change request, pending confirmation of remediation activities by the vendor. Q3 achievements across the other project workstreams include installation of most phone cradles in rural vehicles and delivery of iPhones, ready to commence the deployment phase.
Q3 25-26 | South East Water | SE Water | 4175 | Portfolio & Project Management Uplift | Environment and Water | Financial Management | South East Water is uplifting its ERP environment to enable enterprise-wide project and portfolio management. This project will enhance planning execution reporting and data integration across capital and operational projects. | Initiated |  |  | Waterfall | 2025-07-01 | 2026-02-28 | 2026-06-30 |  | 1388000 | [12 empty] | Project has returned to GREEN following an extension of key project resource and extend time to complete the required discovery work. Alternative solution options are being considered that will meet mandatory business requirements, whilst a longer-term strategic solution is being considered for the future.
Q3 25-26 | Emergency Services Superannuation Scheme | ESS SUPER | 4177 | NetSuite General Ledger Implementation | Business and Industry | Financial Management | ESSSuper is implementing Oracle NetSuite to replace its SunGL general ledger. The new cloud‑based system will enhance efficiency, improve resilience, and provide a secure, scalable platform that better supports the Fund's future requirements. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2025-07-01 | 2025-10-31 | 2025-10-24 | 2025-10-24 | 50000 | 42538 | 2025-11-03 |  | 2026-10-15 |  | 1282333 |  |  |  |  | Green | Green | Project tracking to plan.
Q3 25-26 | State Revenue Office | SRO | 4178 | Emergency Services Volunteers Fund | Government and Economy | Development and Integration | This project implements changes to collect the Emergency Services Volunteers Fund (ESVF) from 1 July 2025, ESVF supports a broader range of emergency services such as floods, storms and other emergencies, replacing the Fire Services Property Levy. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Agile | 2025-04-02 | 2025-06-30 |  | 2025-06-30 | 208928 |  | 2025-07-01 |  | 2026-06-30 |  | 2208201 |  |  |  | Green | Green | Green | Project is tracking to deliver all planned benefits. Project to close in April 2026.
Q3 25-26 | State Revenue Office | SRO | 4179 | Enterprise Service Management | Government and Economy | Development and Integration | The State Revenue Office is procuring a modern Enterprise Service Management tool to provide better business outcomes with automation and self-service capabilities. This initiative procures and integrates the tool and implements the required workflow | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2025-03-05 | 2025-06-30 |  | 2025-06-30 | 29739 |  | 2025-07-01 |  | 2027-06-30 |  | 3643630 |  |  |  | Green | Amber | Amber | Requirements gathering and other project activities continue. Vendor on track to be onboarded in May 2026.
Q3 25-26 | State Electricity Commission (SEC) Victoria Pty Ltd | SECV | 4180 | One-stop shop project | Energy and Resources | Customer Initiated Assistance | Deliver a one-stop shop digital platform to enable Victorian households to be supported by information and access to SEC endorsed installers manage home electrification. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-01 | 2025-07-31 |  | 2025-07-31 | 248955 |  | 2025-08-01 |  | 2026-06-30 |  | 7417752 |  |  |  | Green | Amber | Amber | The project is on track to launch in the next quarter, with active management of resources, issues and risks to remain on track.
Q3 25-26 | State Revenue Office | SRO | 4181 | Data Lakehouse Utilisation | Government and Economy | Development and Integration | Establishing a cloud-based Data Lakehouse is a key element of the SRO's data and analytics strategy to uplift the organisation's data and analytics capacity, capability, operational efficiency and reporting. This project includes 2 use cases. | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | Agile | 2025-02-03 | 2025-06-30 |  | 2025-06-30 | 429284 |  | 2025-07-01 |  | 2026-06-30 |  | 2327800 |  |  |  | Green | Green | Amber | Minor delays and some increased complexity will likely require a small variation to time and cost, to be confirmed in April.
Q3 25-26 | Department of Health | DH | 4183 | Victorian Patient Transport Assistance Scheme (VPTAS) System Replacement | Health | Customer Initiated Assistance | Implement a new VPTAS claims system that leverages the DFFH-DH Enterprise Payments Platform, enabling digitising of the current paper based claimant forms, providing greater efficiencies in the response to and management of claims. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-07-31 |  | 2025-07-31 | 89154 |  | 2025-08-01 |  | 2026-04-30 |  | 1710846 |  |  |  | Amber | Amber | Amber | Initial release of VPTAS Claims system successfully delivered in March 2026 for internal departmental usage, with public launch scheduled for next reporting period. Project is Amber due to tight timeline to complete final testing.
Q3 25-26 | Environment Protection Authority | EPA | 4184 | MAJ143 - Land Renewal | Environment and Water | Tracking and Workflow | The project aims to enable efficient, effective and environmentally safe land development aligned with the Victorian Housing Statement (VHS). | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2026-01-28 | Agile | 2025-05-01 | 2025-05-20 |  | 2025-06-18 | 0 |  | 2025-07-01 |  | 2026-07-31 | 2026-01-28 | 1540840 |  |  |  | Green | Amber | Green | The project has been completed having transitioned into Business as Usual (BAU) operations. The closure report was approved by EPA's Senior Executive Committee on 28 January 2026.
Q3 25-26 | East Gippsland Regional Water Corporation | EGR Water | 4187 | Enterprise Asset Management | Environment and Water | Assets/Materials Management | It is a modern solution for managing the entire asset lifecycle supporting functions such as commissioning maintenance optimization planning reporting and analytics. The system aims to deliver operational cost savings and efficiency improvements. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-10-29 | 2025-01-31 |  | 2025-01-31 | 0 |  | 2025-05-01 |  | 2026-06-30 |  | 1993000 | 1747083 |  |  | Green | Green | Green | The project is tracking well against scope, budget and schedule. Phases one has been implemented and Phase 2 is due for rollout within the next reporting period. Phase 3 is due by 30th June 2026
Q3 25-26 | Department of Education | DE | 4190 | Cove (formerly School Compliance) | Education | Tracking and Workflow | The project will re-platform the current assessment and standards management system, improving time to response with evidence attribution. | Closed - Completed | Compliance (Non Financial) | 2026-01-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-06-30 | 2025-08-15 |  | 2025-08-15 | 0 |  | 2025-08-18 |  | 2026-01-30 |  | 1400000 |  |  |  | Green | Green | Green | The new school assessment and standards management system successfully went live on the 22 January 2026.
Q3 25-26 | Department of Education | DE | 4191 | Student Travel System | Education | Management of Process | The project will digitise Student Travelling applications and centralise information, reducing administrative effort and improving accuracy and timeliness of school bus program. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-02-03 | 2025-03-21 |  | 2025-09-08 | 0 |  | 2025-09-08 |  | 2026-03-20 | 2026-07-10 | 4242287 | 5438770 |  |  | Amber | Amber | Green | The project is GREEN as an result of additional scope budget and timelines being approved to accommodate accessibility requirements and uplift user experience. ​ Design and development sprints for the new Student Travel System are nearing completion. The delivery team is commencing systems integration testing and user acceptance testing to ensure the product meets the department's requirements.
Q3 25-26 | Department of Education | DE | 4192 | School Sport Victoria Website Redevelopment | Education | Management of Process | The project will deliver a modern, secure website to centralise all school sports program information, delivering a comprehensive school sport program information portal to primary and secondary students across Victoria | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-21 | 2025-09-15 |  | 2025-09-15 | 0 |  | 2025-09-30 |  | 2026-04-24 |  | 1200000 |  |  |  | Green | Green | Green | The project is GREEN and is tracking to plan.
Q3 25-26 | WorkSafe Victoria | WorkSafe | 4196 | Information Security and Management Uplift | Employment, Skills and Workplace | Records Management ,Security Management | WorkSafe Victoria is improving its information management security and cyber security maturity to strengthen governance, clarify ownership, uplift capability and reduce risk through targeted improvements and formal assessment. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-10-30 |  | 2025-10-30 | 189460 | 125073 | 2025-11-03 |  | 2026-11-30 |  | 1548186 | 1612573 |  |  |  | Green | Green | On track
Q3 25-26 | Court Services Victoria | CSV | 4199 | Case and List Management System (CLMS) Stabilisation Project - Tranche 1 | Law and Justice | Development and Integration | The project will stabilise and upgrade the existing technology for eCase and CourtConnect, to enhance critical functionalities across County Court of Victoria (CCV) digital infrastructure. | Initiated | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2024-09-01 | 2026-03-31 | 2026-06-30 |  | 0 | 122142 | [11 empty] | Further analysis and costings for delivery options have been undertaken and proposed solutions identified. Subject to approval, work on the projects will commence this financial year.
Q3 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4200 | Procurement @ DEECA – Digital Enablement | Business and Industry | Management of Process | This project will deliver a new technology solution to optimise procurement processes. The primary goal is to implement procurement forms to meet evolving requirements and ensure that updated framework elements are enabled through technology. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid – Waterfall and Agile | 2025-04-07 | 2025-04-07 |  | 2025-08-06 | 0 |  | 2025-08-06 |  | 2026-08-31 |  | 3176852 |  |  |  |  | Green | Green | Delivery is on track as per the approved plan and schedule.
Q3 25-26 | Court Services Victoria | CSV | 4201 | County Court of Victoria Audio-Visual (in-court technology) systems upgrade (2025-29) | Law and Justice | Collaboration ,Communication | Upgrading Audio Visual systems across the County Court of Victoria to deliver modern, integrated solutions for video conferencing, evidence display, and remote participation in 100 spaces, including 53 courtrooms and 39 jury rooms. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial) |  | Waterfall and Agile | 2023-11-03 | 2024-10-01 |  | 2024-10-01 | 14530 |  | 2024-10-01 |  | 2029-10-16 |  | 17039154 |  |  |  |  | Green | Green | Working with internal and external stakeholders on initial/trial courtroom.
Q3 25-26 | Court Services Victoria | CSV | 4202 | Case and List Management System (CLMS) Stabilisation Project - Tranche 2 | Law and Justice | Development and Integration | The project will stabilise and upgrade the existing technology for CLMS and its associated systems, while consolidating and enhancing critical functionalities across County Court of Victoria (CCV) digital infrastructure. | Initiated |  |  | PMBoK | 2024-09-01 | 2026-03-31 | 2026-09-30 |  | 0 | 122142 | [11 empty] | Independent advice is currently being sought to inform decisions on the next stage of the project to meet the mid to longer term strategic goals of the Court.
Q3 25-26 | Yarra Valley Water | YV Water | 4203 | STP Firewalls Replacement and SD-WAN Implementation | Environment and Water | Security Management ,Systems Management | This project replaces EOL firewalls at remote sites and modernises our IT/OT network with SD WAN, delivering a more secure, reliable, high performance network that improves business continuity and simplifies management. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-10-06 | 2026-02-12 | 2025-11-20 | 2025-11-20 | 60000 |  | 2026-02-12 |  | 2026-10-30 |  | 1403000 | [5 empty] | Green | Project has moved into delivery and is progressing well
Q3 25-26 | Yarra Valley Water | YV Water | 4206 | MAINTENANCE SERVICES MOBILISATION | Environment and Water | Development and Integration | This project delivers the digital and system integration foundations required to enable the safe, effective, and coordinated transition to the new Maintenance Services Contracts with new Delivery Partners. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-01-01 | 2025-12-31 | 2025-12-22 | 2025-12-22 | 2125163 |  | 2026-01-01 |  | 2026-11-30 |  | 3158037 | [5 empty] | Green | Overall project is on track with a slight increase to budget forecasted.
Q3 25-26 | Melbourne Water | MELB Water | 4208 | AV Upgrade | Environment and Water | Communication | This project aims to deliver AV upgrades at operational sites across Melbourne Water. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | PMBoK | 2025-11-07 | 2026-02-02 |  | 2026-03-27 | 0 |  | 2026-03-27 |  | 2026-07-01 |  | 1546982 | [5 empty] | Amber | As at 20260331: Business case approved. Electrical fit-out almost complete. AV equipment roll-out underway, Amber status due to the risk of logistical challenges around having multiple vendors accessing remote sites for installation of equipment, potential for minor schedule delays.
Q3 25-26 | Melbourne Water | MELB Water | 4210 | IT Storage Refresh | Environment and Water | Data Management | Current data centre storage and connectivity are end of life in 2026. Project will deliver upgraded storage infrastructure that meets current needs and can scale to support future growth. | Initiated |  |  | PMBoK | 2025-10-08 | 2026-02-16 | 2026-05-01 |  | 0 | [12 empty] | As at 20260331: Business Case under review.
Q3 25-26 | Melbourne Water | MELB Water | 4211 | Telemetry Network | Environment and Water | Systems Management | Current network services will be decommissioned in 2027, this project is to upgrade to scale and support future growth. | Initiated |  |  | PMBoK | 2025-12-08 | 2026-04-08 | 2026-09-09 |  | 0 | [12 empty] | As at 20260331: Business Case to be submitted.
Q3 25-26 | Department of Health | DH | 4212 | Data Centre Exit | Health | Systems Management | Exit the Burwood and Ballarat Data Centres by migrating workloads to alternate data centres, including network establishment, VMware to IaaS migration and SAN/Oracle relocation, to meet June 2026 exit objectives, avoiding increased hosting costs. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-11-10 | 2026-02-27 | 2026-03-31 | 2026-03-31 | 0 |  | 2026-03-31 |  | 2026-06-25 |  | 2420000 | [5 empty] | Amber | Project is progressing but is Amber due to delays with vendor provisioning of data network links.
Q3 25-26 | Melbourne Water | MELB Water | 4213 | Enterprise WAN Refresh | Environment and Water | Systems Management | SD‑WAN integrates all network connections to optimise bandwidth and improve performance. This pilot will validate the technology before a full roll-out that will replace outdated hardware and enhance network management. | Initiated |  |  | PMBoK | 2025-10-23 | 2026-05-29 |  |  | 0 | [12 empty] | As at 20260331: Business Case under development.
Q3 25-26 | Melbourne Water | MELB Water | 4214 | GIS Platform Upgrade | Environment and Water | Systems Management | Major upgrade of Melbourne Waters Geographic Information System to the latest supported version. | Initiated |  |  | PMBoK | 2025-10-25 | 2026-09-30 |  |  | 0 | [12 empty] | As at 20260331: Project currently focused on analysing system inter-dependencies.
Q3 25-26 | Department of Education | DE | 4220 | Student Insight Platform Establishment and Digital Enrolment Product - Phase 3 | Education | Customer Relationship Management | Student Insight is a centralised enrolment and student administration platform, replacing paper-based processes for schools and families. The project will enhance and implement the Digital Enrolment Product across mainstream schools in the SEV & NEV | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - Waterfall and Agile | 2025-07-01 | 2025-10-30 |  | 2025-10-30 | 0 |  | 2025-11-01 |  | 2026-06-30 |  | 11450000 |  |  |  |  | Green | Green | The project is GREEN and tracking to plan without issues.
Q3 25-26 | Department of Education | DE | 4221 | Justice Education System Portal | Education | Analyses and Statistics ,Systems Management,Tracking and Workflow | This Portal brings together various systems and platforms to create a scalable system for justice education. This is to create a well-connected Portal to track and monitor young people at risk or involved in youth justice & those presenting to police | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - Waterfall and Agile | 2025-05-01 | 2025-05-30 |  | 2025-06-25 | 267000 |  | 2025-11-01 | 2025-11-17 | 2027-06-30 |  | 2500000 | 4333100 |  |  |  | Green | Green | The project is GREEN and tracking to plan. Additional project scope budget and delivery timelines have been approved to accommodate business needs and uplift end-user experience. Detailed design for the Portal solution will commence soon with the delivery partner in preparation for deployment in Financial Year 2026-27.
Q3 25-26 | Department of Education | DE | 4222 | VRQA Victorian Home Schooling Register Replacement | Education | Customer Relationship Management | The VRQA is redeveloping the Home Schooling Register to meet current technology and security standards to better support our business needs and improve efficiency across the organisation. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - Waterfall and Agile | 2025-05-16 | 2025-11-25 |  | 2025-11-25 | 0 |  | 2026-01-12 |  | 2027-05-31 |  | 1780000 | [5 empty] | Green | The project is GREEN and tracking to plan. Currently in the build phase, with user acceptance testing planned to start late August 2026.
Q3 25-26 | Development Victoria | Development Vic | 4223 | HRIS & Payroll solution | Property and Planning | Human Capital / Workforce Management | Human Resources and Payroll System implementation to improve operational efficiencies, improve data and reporting quality, reduce risk and improve the employee experience. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-08-18 |  | 2025-08-18 | 0 |  | 2025-08-18 |  | 2027-03-31 | 2027-06-30 | 2551166 | 1456000 |  |  |  | Green | Amber | The project status is amber due to procurement issues impacting the schedule. The project team is actively working to mitigate these impacts. The project will return to ‘on track’ once the issues are resolved and the schedule is rebaselined and approved.
Q3 25-26 | Department of Health | DH | 4224 | Briefings Solution Implementation | Health | Communication,Management of Process ,Tracking and Workflow | The DH & DFFH Briefings Solution will manage ministerial & secretarial briefings/correspondence, parliamentary questions, executive memos & other materials requiring executive approval, improving collaboration & efficiency in correspondence approval. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-01 | 2025-10-10 |  | 2025-10-10 | 684600 |  | 2025-10-13 |  | 2026-06-30 |  | 2509210 |  |  |  |  | Green | Green | Initial release of the Briefing solution, BriefConnect, was successfully delivered in March 2026, with a further release scheduled for the next reporting period.
Q3 25-26 | Department of Government Services | DGS | 4225 | Working With Children Check Employer Platform and Training | Government and Economy | Development and Integration | Provide an improved online and offline experience that supports the revised regulatory framework and further strengthens the Working with Children Check. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-10-08 | 2026-03-04 | 2026-04-20 |  | 200000 | 540000 | [11 empty] | Project is in the process of finalising the Business Case with the project expected to move into execution in April 2026.
Q3 25-26 | Barwon Region Water Corporation | BR Water | 4226 | C1069 - TechOne CiA Transition | Environment and Water | Financial Management | This project aims to maximise the value of the TechnologyOne platform by migrating the remaining Supply Chain Management (SCM) module from Ci to CiA platform. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2024-06-02 | 2025-09-30 |  | 2025-10-30 | 400877 |  | 2025-11-09 |  | 2026-04-30 |  | 781253 | 842123 |  |  |  | Green | Green | Project has successfully deployed to production and hyper care is progressing.
Q3 25-26 | Victorian Funds Management Corporation | VFMC | 4229 | E28 ¦ Modern Cloud Infrastructure | Business and Industry | Systems Management | This project aims to strengthen VFMC resilience through decommissioning data centers and expanding usage of Cloud services, delivering a modern, reliable secure and flexible Cloud Platform. | Initiated |  |  | Agile | 2025-12-01 | 2026-04-30 |  |  | 0 | [12 empty] | The project was approved to commence initiation in December 2025. Following approval, the immediate priority was to complete the Request for Proposal (RFP) process. The process has now concluded successfully, with the RFP being awarded. The project is now transitioning from procurement into contract finalisation and mobilisation for delivery.
Q3 25-26 | Department of Transport and Planning | DTP | 4230 | Workspace Management System | Transport and Vehicles | Assets/Materials Management | Deployment of DTP-wide desk booking system to reduce operational cost pressures, eliminate duplicated administrative burden and provide an easier solution for staff to book desks to help better manage office utilisation. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-06-01 | 2025-06-30 |  | 2025-06-30 | 0 |  | 2025-10-01 |  | 2026-06-30 |  | 1855000 | [5 empty] | Green | The project implementation status is tracking green.
Q3 25-26 | Department of Government Services | DGS | 4235 | DGS & DTF Digital Record and Information Management Service (DRIMS) | Government and Economy | Document Management | Enabling DRIMS for DGS and DTF to mitigate technical risk, achieve record management compliance for DGS, build a single service for the cluster, release significant annual cost savings. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2026-02-23 | 2026-06-30 |  |  | 0 | [12 empty] | Project has commenced initiation phase Project planning is in progress.
Q3 25-26 | WorkSafe Victoria | WorkSafe | 4237 | Amusement Structures Reform Implementation | Employment, Skills and Workplace | Systems Management | The project will implement the Amusement Structures Reform and the licensing management system uplift required to enable validation of compliance and collection of data to support prevention of injuries and fatalities involving amusement rides. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2025-03-05 | 2025-07-03 |  | 2025-07-03 | 0 |  | 2025-08-02 |  | 2026-11-30 |  | 1576553 | [5 empty] | Green | On track
Q3 25-26 | Department of Education | DE | 4238 | Student Insight LOOKOUT Technology Improvements Project | Culture, Sport and Recreation | Collaboration ,Customer Relationship Management | Integrate Student Insight with the Client Relationship Information System (Department of Families, Fairness and Housing) to share out-of-home care data in real time, giving schools accurate information to support student wellbeing. | Delivery | Social Improvement (Non Financial) |  | Agile | 2025-07-18 | 2025-10-21 |  | 2025-10-21 | 300000 |  | 2026-01-05 |  | 2026-06-26 |  | 1300000 | [5 empty] | Green | The project is GREEN and tracking to plan without issues.
Q3 25-26 | Department of Education | DE | 4239 | ServiceNow Human Resources Service Delivery | Education | Human Resources | Delivery of a specific Human Resources module on the ServiceNow platform to enable the end-to-end management of Human Resource cases for HR Schools HR Corporate and Early Learning Victoria. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-28 | 2025-09-25 |  | 2026-03-17 | 586363 |  | 2026-03-17 |  | 2026-07-17 |  | 1936697 | [5 empty] | Green | The project is GREEN and tracking to plan without issues.
Q3 25-26 | Department of Education | DE | 4241 | Securing Connected Learners Program - Migration - Phase 3 | Education | Development and Integration ,Security Management ,Systems Management | This project will strengthen school cyber resilience by migrating M365/Google tenancies, improving identity services, expanding authentication and deploying enhanced child safety and content controls to deliver secure digital environments. | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Waterfall | 2025-06-01 | 2025-06-30 |  | 2025-06-30 | 0 |  | 2026-01-05 |  | 2026-06-30 |  | 20950000 | [5 empty] | Amber | The Program is reporting AMBER due to replanning activities of some work streams as project resources were temporarily diverted to high level cyber security operations.
Q3 25-26 | Melbourne Water | MELB Water | 4242 | Replacement of Project Management System | Environment and Water | Management of Process | Replacement of end of life technology due to Microsoft retiring Access Control Services current system and customised modules will no longer work. Project will move to a scalable platform. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-12-09 | 2026-03-30 |  | 2026-03-30 | 0 |  | 2026-03-30 |  | 2026-07-01 |  | 2961616 | [5 empty] | Amber | As at 20260331: Amber status due to user acceptance testing being outstanding while defects are being resolved prior to production rollout.
Q3 25-26 | Melbourne Water | MELB Water | 4243 | GIS Architecture Rationalisation | Environment and Water | Systems Management | Remediate system limitations that have impacted operational efficiency and service reliability by implementing architecture improvements. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-09-06 | 2024-12-20 |  | 2024-12-20 | 0 |  | 2024-12-20 |  | 2026-07-03 |  | 1198980 | [5 empty] | Green | As at 20260331: Detailed change impact analysis is complete and project continues through delivery phase.
Q3 25-26 | Department of Families, Fairness and Housing | DFFH | 4247 | Maintenance Assurance Audit Tool | Community Services | Reporting | Implement a portable and integrated audit system to manage and report the findings of completed maintenance work of public housing by officers whilst onsite, enabling more inspections to be conducted and faster resolution of issues. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2025-11-28 | 2025-11-28 |  | 2025-11-28 | 0 |  | 2026-02-02 |  | 2026-06-30 |  | 1283018 | [5 empty] | Green | Project progressing to cost and schedule.
Q3 25-26 | Department of Families, Fairness and Housing | DFFH | 4248 | Enhancing the Victorian Emergency Management Personal Hardship Program IT System | Community Services | Customer Relationship Management | Enhance the Emergency Management Personal Hardship IT System to integrate with Department of Government Services, streamline online lodgement of hardship and emergency accommodation requests and improve finance systems processes and reporting. | Initiated |  |  | Agile | 2025-12-10 | 2026-05-29 |  |  | 195436 | [12 empty] | Planning and mobilisation activities are underway.
Q3 25-26 | WorkSafe Victoria | WorkSafe | 4249 | Domino Platform Upgrade | Employment, Skills and Workplace | Systems Management | Infrastructure Life Cycle Management to upgrade the Domino platform and Windows Server operating system, maintaining infrastructure currency, reducing operational risks, and enabling new functionality with improved performance and stability. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-06-30 | 2026-01-30 |  | 2026-03-19 | 244023 |  | 2026-03-23 |  | 2027-12-31 |  | 1225700 | [5 empty] | Green | On track
Q3 25-26 | Department of Health | DH | 4250 | Health Technology Services Data Centre Establishment | Health | Systems Management | With current data centre arrangements terminating in 2028, project will deliver new data centre infrastructure, network connectivity & firewalls to ensure continuity of critical state-wide digital health systems managed by Health Technology Services. | Initiated |  |  | PRINCE2 | 2026-01-02 | 2026-05-29 |  |  | 0 | [12 empty] | Planning and mobilisation activities are in progress.
Q3 25-26 | Department of Families, Fairness and Housing | DFFH | 4251 | Targeted Care Packages - End to End System Enhancements | Community Services | Customer Relationship Management | Implement system enhancements that support a revised end to end process to capture all work and activity required to deliver the Targeted Care Packages (TCP) program, increasing processing efficiencies. | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2026-03-31 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-08-12 | 2024-11-27 |  | 2024-11-28 | 0 |  | 2025-01-07 |  | 2026-05-31 |  | 1039930 | [5 empty] | Green | Project has successfully delivered and close out activities are underway. The project is reporting for the first time following a revision to total delivery costs that ensured adequate support for implementation.
Q3 25-26 | Department of Education | DE | 4252 | Senior Secondary Pathways Reform Division (SSPRD) Technology Roadmap 25/26 | Education | Customer Relationship Management,Forms Management | SSPR Digital Platform consists of 4 applications (Work Based Learning, School Exemptions, Industry Engagement and VET Delivered to School Students) which support schools to deliver pathway reform and increase access to career education for students. | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2025-02-01 | 2025-05-31 |  | 2025-06-24 | 0 |  | 2025-07-01 |  | 2026-12-31 |  | 10120000 | [5 empty] | Green | The project is GREEN and tracking to plan without issues.
Q3 25-26 | Greater Western Water Corporation | GW Water | 4254 | Return To Service Plan | Environment and Water | Communication,Data Management,Records Management ,Investment Management | The project will support the delivery of GWW's Return to Service Plan, enabling system enhancements to support effective, accurate, compliant and reliable customer billing. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial) |  | Waterfall | 2025-07-01 | 2025-10-30 |  | 2025-10-30 | 433129 |  | 2025-10-30 |  | 2026-03-31 | 2026-06-30 | 18091026 | [5 empty] | Red | The program is supporting GWW's Return to Service Plan. Key milestones include the rollout of the catch-up billing program in line with Essential Services Commission requirements and the re-implementation of direct debit in full services.
Q3 25-26 | Fire Rescue Victoria | FRV | 4255 | Cyber Uplift Program | Emergencies and Safety | Security Management | The Cyber Uplift Program strengthens FRV’s resilience by enhancing cybersecurity capabilities, addressing risks, and modernising systems to safeguard operations, protect critical data, and ensure community confidence in our emergency services. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - Waterfall and Agile | 2025-07-01 | 2025-12-31 |  | 2025-12-31 | 257125 |  | 2026-01-01 |  | 2028-06-30 |  | 14785796 | [5 empty] | Green | The project is tracking well against scope, budget and schedule.
Q3 25-26 | Safe Transport Victoria | STV | 4256 | Consolidated Data Platform Stage 3 | Transport and Vehicles | Data Management | The Consolidated Data Platform (CDP) delivers on ST Vic's aim to be an intelligence-led regulator by centralising all organisational data to share securely with industry partners and the Victorian Government. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-11-01 | 2024-12-06 |  | 2025-02-03 | 298 |  | 2025-04-01 |  | 2026-04-02 |  | 1421000 | [5 empty] | Green | Datasets ingested and transformed to the enterprise data model. Operational uplift commenced.
Q3 25-26 | Parks Victoria | PARKSVIC | 4257 | Data Center Infrastructure replacement | Environment and Water | Systems Management | The project will replace or remediate end-of-life IT infrastructure in Parks Victoria-managed data centres to maintain reliability, security and supportability, and reduce ageing infrastructure risks. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-11-03 | 2026-04-30 |  |  | 0 | [12 empty] | During Q3 FY25/26, project was in initiation phase. Business Case was endorsed, design and procurement will be undertaken to finalise delivery cost and timelines