## PublicDataReport
Collection Period | Department/ Agency Name | Agency Short Name | Project ID | Project Title | Government Domain | ICT Project Category | Description | Stage | Benefit Category ( Benefit Type) | Date of Closure/ Postponement | PM Methodologies | Initiation Start Date | Planned Initiation End Date | Revised Initiation End Date | Business Case Approval Date | Planned Initiation Cost | Revised initiation Cost | Planned Delivery Start Date | Revised Delivery Start Date | Planned Delivery End Date | Revised Delivery End Date | Planned Delivery Cost | Revised Delivery Cost | Q4 24-25 | Q1 25-26 | Q2 25-26 | Q3 25-26 | Q4 25-26 (Current) | Reporting Comments
Q4 25-26 | Court Services Victoria | CSV | 2452 | Courts Case Management System | Law and Justice | Tracking and Workflow | Since commencing in 2018, CMS has delivered Civil, Child Protection and Criminal functionality, with Criminal going live across both courts on 30 June 2026. eDocs enables electronic filing, with IVO due later this year to complete project scope. | Delivery | Efficiency/Productivity (Non Financial) |  | Project Management Excellence (PME) | 2016-07-01 | 2017-05-02 |  | 2017-05-02 | 0 |  | 2017-07-01 |  | 2022-06-30 | 2026-12-31 | 89200000 | 158650000 | Red | Amber | Amber | Amber | Green | Overall status moved from Amber to Green as at 30 June 2026 following successful Criminal go-live and progress on the IVO release remains on track. Readiness, governance, support and go-live activities were completed, with no material blockers to delivery during Q4.
Q4 25-26 | V/Line Corporation | V/Line | 2490 | Workforce management | Transport and Vehicles | Human Capital / Workforce Management | The Workforce management project will streamline the workforce management function and deliver an electronic rostering system that support V/Line to ensure it is able to meet daily staffing challenges to provide punctual and reliable train services | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-01-18 | 2018-02-28 | 2023-04-28 | 2023-05-01 | 250000 | 690251 | 2023-05-31 |  | 2026-07-31 | 2026-12-31 | 9680463 | 9992358 | Green | Green | Green | Green | Green | The overall health of the Project is on-track.
Q4 25-26 | South West Alliance of Rural Health | SWARH | 2597 | Barwon Health Rostering Project | Health | Management of Process ,Human Capital / Workforce Management ,Human Resources | This project will deliver a Rostering and Time & Attendance system to automate staff rostering processes, improving workforce utilisation, accuracy of resource allocation and delivery of patient care. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2017-07-19 | 2018-05-31 |  | 2018-06-08 | 110640 |  | 2018-07-11 |  | 2019-12-31 | 2026-06-30 | 3443281 | 7216360 | Red | Red | Red | Red | Red | The primary driver of the red status is the significant time investment in building and testing the award rules into Optima. This has extended the project timelines by more than 12 months. In addition, new EBA changes were introduced during the delivery period requiring Award rule rework and retesting mid-build. Delivery of the Rostering and Time & Attendance system continues with over 8500 staff now utilising the system
Q4 25-26 | Department of Justice and Community Safety | DJCS | 2851 | Digital Radio Upgrade Program - Stage 2 | Emergencies and Safety | Communication | This Program will transition Ambulance Victoria's (AV) regional comms off analogue radio system onto the State’s shared digital network and replace AV's regional radio fleet to provide secure comms and improve community safety and health outcomes. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2019-07-01 | 2019-07-02 |  | 2019-07-02 | 0 |  | 2019-07-03 |  | 2023-06-30 | 2027-04-30 | 70378000 | 117867000 | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and the revised schedule.
Q4 25-26 | South West Alliance of Rural Health | SWARH | 3003 | Barwon Health Community Electronic Medical Record | Health | Content Management,Data Management,Forms Management,Management of Process ,Security Management ,Systems Management,Tracking and Workflow | Implementation of an Electronic Health Record (EHR) solution for community nursing and community mental health to replace legacy systems | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PMBoK | 2018-03-01 | 2020-10-01 | 2022-04-07 | 2022-04-07 | 0 | 0 | 2022-04-11 |  | 2023-08-28 | 2026-08-17 | 6074206 | 10879302 | Red | Amber | Amber | Amber | Amber | Post Acute Care and Social Support modules are now live. Development of Connected Care and Mental Health Drug and Alcohol Service modules is in progress.
Q4 25-26 | Fire Rescue Victoria | FRV | 3030 | Rostering and Shift Change | Emergencies and Safety | Systems Management | Purchase and implement a contemporary off the shelf Rostering and Shift Change system to replace multiple legacy systems. | Delivery | Efficiency/Productivity (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-06-26 | 2020-12-08 | 2021-09-14 | 2021-09-14 | 0 |  | 2021-09-15 |  | 2022-11-02 | 2026-06-30 | 3760000 | 4349947 | Amber | Green | Green | Amber | Amber | FRV Division A (metropolitan fire stations) implementation of timesheet and actuals is complete. Delivery of the remaining rostering requirements for FRV Division A is in progress, with some delays expected and mitigation measures in place to minimise the risk of further delays. The project control board will meet in late July 2026 to discuss rebaselining the overall delivery end date to December 2026, which will provide additional time for the remaining deliverables to be implemented for FRV Division A. FRV Division B (regional fire stations) implementation is complete.
Q4 25-26 | Wannon Region Water Corporation | WAN Water | 3091 | Billing and Customer Relationship Management Systems | Environment and Water | Customer Relationship Management | The replacement of the organisation's Billing and Customer Relationship Management Systems | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2020-01-01 | 2021-03-31 | 2022-06-24 | 2022-06-24 | 100000 | 130000 | 2022-08-15 | 2023-01-03 | 2024-03-22 | 2026-06-30 | 8200000 | 20084484 | Amber | Green | Green | Green | Green | The project reset is proceeding well with contract negotiations now underway.
Q4 25-26 | Goulburn Valley Region Water Corporation | GVR Water | 3130 | Billing and Customer Relationship Management System | Environment and Water | Customer Relationship Management | The project will replace Goulburn Valley Water's existing legacy billing and CRM systems with a modern, efficient and customer focused system | Initiated |  |  | Internal project management methodology | 2018-10-01 | 2021-06-30 | 2027-06-30 |  | 75000 | 2700000 | [11 empty] | GVW is currently recruiting for a Project Lead to run the Procurement and finalisation of the Business Case for this project.
Q4 25-26 | Department of Justice and Community Safety | DJCS | 3168 | Post Sentence Authority Case Management System | Law and Justice | Tracking and Workflow | A case management system, crucial to sustainable operations and managing the risks associated with manual information flow, will be delivered. Real time information will be provided for informed decisions about offenders to uphold community safety. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2021-03-30 | 2021-07-15 | 2023-06-30 | 2023-06-30 | 150000 | 213455 | 2024-03-01 |  | 2025-12-31 | 2027-04-17 | 1878947 | 3556942 | Green | Green | Green | Green | Green | The project is tracking well overall. There is a minor schedule risk due to an unconfirmed schedule for one of the deliverables; However, the project remains on track for completion by April 2027. The revision to the delivery cost reflects the introduction of additional scope focused on information security, and prior project integrations have also been incorporated to provide a more accurate view of the full program of work.
Q4 25-26 | Department of Justice and Community Safety | DJCS | 3170 | Technology and resources to support Victoria’s fines system | Law and Justice | Systems Management | Delivery of next generation of fines platform by incrementally implementing functions into the business landscape to complement existing technology, ensuring better revenue collection, assistance for vulnerable Victorians and debtor-centric services. | Delivery | Customer Satisfaction (Non Financial), Increased Revenue (Financial) |  | Hybrid - Waterfall and Agile | 2021-03-10 | 2021-08-30 | 2021-12-16 | 2021-12-16 | 0 | 10367000 | 2022-01-09 | 2022-01-01 | 2025-06-30 | 2027-06-30 | 131615000 | 179961000 | Red | Red | Red | Red | Red | The project is reporting a red status due to resourcing challenges and slower than anticipated delivery. Previous adjustments to the program's delivery approach, including transitioning to shorter delivery cycles, has continued to be effective. The Revised Delivery Cost has increased by $10 million and the completion date has been revised to June 2027 reflecting increased delivery complexity. As the project progresses, the schedule is being assessed against the completion date.
Q4 25-26 | Department of Justice and Community Safety | DJCS | 3171 | Better Technology Tools Enabling Responsibility (BTTER) | Law and Justice | Development and Integration | Deliver applications to automate processes, reduce costs and risks associated with existing manual systems for safety benefits. Prison management systems will be uplifted, and rehabilitation and reintegration services will be enhanced. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2020-07-21 | 2021-02-19 |  | 2021-02-19 | 324114 |  | 2021-02-22 |  | 2023-06-30 | 2029-06-30 | 18868800 | 46682876 | Green | Green | Green | Green | Green | In conjunction with the client, the program is reviewing delivered modules, benefits realisation and enhancements to realise planned efficiencies, and planning for an initial pilot of core modules to another correctional centre. The project remains within the allocated budget and is on schedule for planned deliverables. In Q4 2024-25 the delivery cost was revised from the planned $18.86m to $46.68m due to an increase in scope to facilitate the statewide deployment of the automation technology. The delivery end date was also revised from June 2025 to June 2029 to accommodate the additional scope.
Q4 25-26 | Department of Government Services | DGS | 3199 | RTBA - Bond Management System Replacement | Community Services | Customer Relationship Management | This project will deliver an enhanced, updated solution to the Residential Tenancies Bond Authority legacy systems which are reaching end of life. The solution will ensure alignment to the business vision. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - Waterfall and Agile | 2021-04-12 | 2021-12-31 | 2021-12-31 | 2022-02-28 | 975000 | 1178280 | 2022-03-01 |  | 2023-06-30 | 2026-07-01 | 8900000 | 25030000 | Amber | Amber | Green | Green | Green | BMSR hypercare completed successfully. Project closed. New portable bonds functionality built and tested ahead of go live planned for 1 July 2026.
Q4 25-26 | Melbourne Water | MELB Water | 3214 | Strategic Relationship Management Tool Phase 1-2 | Environment and Water | Collaboration | To enhance delivery of business goals by improvement in business capabilities and relationship management tools to allow ongoing management and continuity of relationships to achieve strategic improvements in organisational goals. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2020-11-25 | 2021-08-01 |  | 2021-11-04 | 0 |  | 2021-11-04 |  | 2022-06-28 | 2026-07-31 | 3174023 | 2260484 | Green | Green | Red | Green | Green | As at 20260331: Project in closure, will be finalised in Q1 FY26/27
Q4 25-26 | Fire Rescue Victoria | FRV | 3254 | FRV Operational Station Connectivity | Emergencies and Safety | Assets/Materials Management | The implementation of the FRV network and FRV Station Turn Out systems across ex CFA stations. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-09-01 | 2021-03-23 |  | 2021-03-23 | 0 |  | 2021-03-25 |  | 2023-06-30 | 2026-08-17 | 16689890 | 18418852 | Amber | Green | Green | Green | Green | This project is entering the closure phase, during which final closure documentation will be completed and a formal handover to production will occur.
Q4 25-26 | Department of Health | DH | 3261 | Health Information Exchange (HIE) | Health | Data Management,Development and Integration | Deliver a Health Information Exchange for secure sharing of pathology information at the Point of Care, and to facilitate planning for increased scope/budget in subsequent years to cater for all key clinical domains for VPHS state-wide rollout. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-06-01 | 2021-06-30 |  | 2021-06-30 | 0 |  | 2021-07-01 |  | 2025-06-30 | 2026-06-30 | 27220000 | 36850443 | Red | Red | Amber | Amber | Amber | Project has successfully delivered all agreed project scope. Project is reporting Amber health status due to pending approval to extend the project end date to December 2026, enabling a controlled project closure.
Q4 25-26 | Peter MacCallum Cancer Centre | Peter MAC | 3278 | People and Payroll Transformation Program - Rostering Project | Health | Human Capital / Workforce Management ,Human Resources | The People Systems Program will deliver a Rostering solution which will increase efficiency and improve data security and integrity by eliminating paper time sheets and manual processes. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2021-09-01 | 2022-07-01 | 2023-08-02 | 2023-08-02 | 50000 | 500000 | 2023-08-03 |  | 2025-06-30 | 2027-12-30 | 6428267 | 11849537 | Green | Green | Red | Red | Red | The project has identified significant issues during the testing phase. PMCC has commenced work to plan and execute remediation of issues in Scope, Resources, Deployment Approach, Commercials and Financials.
Q4 25-26 | Oral Health Victoria | OHV | 3280 | Electronic Oral Health Record (EoHR) | Health | Development and Integration | The Electronic Oral Health Record (EoHR) aims to replace and consolidate the legacy solution to deliver a single state-wide oral health record to support improved dental health outcomes in Victoria | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-04-01 | 2020-10-30 |  | 2020-10-30 | 390000 |  | 2021-09-22 |  | 2023-06-30 | 2027-06-30 | 9490000 |  | Amber | Amber | Amber | Amber | Amber | R2 product development and consultation with sector representatives continued during this reporting period, with implementation planning commencing for the first activation group and development of training, support and communication materials progressing to support agency implementation readiness.
Q4 25-26 | Department of Transport and Planning | DTP | 3312 | Smarter Roads Program - Timetable Systems Uplift | Transport and Vehicles | Content Management,Data Management,Systems Management | The objective of the project is to implement public transport timetabling solution for each mode which will improve business process and data accuracy, providing Victorian commuters consistent and timely information when using public transport. | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2026-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-05-03 | 2021-12-30 | 2022-02-07 | 2022-02-07 | 0 |  | 2022-02-07 |  | 2023-03-31 | 2026-04-30 | 4739268 | 6716680 | Amber | Red | Amber | Amber | Green | The project delivery activities are completed.
Q4 25-26 | Department of Transport and Planning | DTP | 3318 | Automatic Vehicle Monitoring Sustainment (AVMS) | Transport and Vehicles | Systems Management | Address key short-term challenges affecting Melbourne’s tram network through targeted initiatives to sustain the AVM system in the short-term while the Department continues to develop options for a future Tram Monitoring and Control (TMC) system. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PTV Investment Lifecycle | 2021-07-01 | 2022-04-29 | 2023-08-30 | 2023-08-30 | 1785000 | 0 | 2023-08-31 |  | 2025-06-30 | 2026-10-28 | 32018000 |  | Green | Green | Green | Green | Green | The AVMS On Board project is tracking well with the on-board tram installations of AVMS now extending across all E-Class trams.
Q4 25-26 | Fire Rescue Victoria | FRV | 3325 | Human Resources Information System (HRIS) | Emergencies and Safety | Human Resources | HRIS Project has the primary focus this year to address foundation data issues, collaborate with the Rostering and Shift Change project and build a business case for approval. Scope includes Payroll and HR | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | FRV Project Management Framework (PMF) | 2021-12-10 | 2022-06-30 | 2023-02-28 | 2023-02-28 | 0 | 0 | 2023-03-01 |  | 2025-03-01 | 2026-09-16 | 22392000 |  | Amber | Red | Red | Red | Green | Funding to deliver the new HRIS was announced in the 2026-27 State Budget returning the project to a green status. The funding supports full implementation of the new system which is an expansion of the initial project scope to build a business case. The contract execution for system implementation is expected to be completed by the currently reported delivery end date of September 2026. Once the contract has been executed there will be a budget and schedule re-baseline to accommodate the additional scope. Reporting on the revised budget schedule and scope is expected to commence in Q1 2026-27.
Q4 25-26 | South West Alliance of Rural Health | SWARH | 3334 | Regional Electronic Health Record Upgrade (excluding Barwon Health) | Health | Customer Relationship Management,Data Management,Development and Integration ,Management of Process ,Records Management ,Systems Management,Tracking and Workflow | Upgrade to the regional Electronic Health Record (EHR) solution, that supports 11 health services across South West Victoria. The project will improve clinician and patient user experience, focusing on quality and safety of patient care. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-10-16 | 2022-03-31 | 2022-08-31 | 2022-09-01 | 180000 | 300000 | 2022-09-05 |  | 2025-06-30 | 2027-04-01 | 23495000 |  | Green | Amber | Amber | Green | Green | The project continues to progress well. User acceptance testing activities nearing completion, training development and Health Service implementation activities are in progress and in line with schedule and expectations.
Q4 25-26 | Melbourne Water | MELB Water | 3338 | Electronic Content Management Phase 1 | Environment and Water | Content Management | This project will upgrade Melbourne Waters current document storage repositories and migrate to a new Electronic Document and Records Management System (EDRMS) | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2021-10-08 | 2022-09-22 | 2026-04-01 | 2026-05-25 | 0 |  | 2026-05-25 |  | 2026-12-10 |  | 2263242 | [5 empty] | Green | As at 20260630: Business case was approved, project on track.
Q4 25-26 | Victoria Police | VicPol | 3358 | Electronic Document and Records Management System | Law and Justice | Document Management | The overall objective of the project is to implement a fully integrated, enterprise-wide Electronic Document and Records Management Solution and an Enterprise Service Management platform to uplift information management maturity. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2020-11-25 | 2021-11-25 | 2024-12-31 | 2025-12-31 | 8559000 | 8559000 | Green | Amber | Amber | Amber | Amber | The core objective of the business case has been achieved, with the Records365 system delivered in March 2025, and the supporting solutions (DekkoSecure, and Automated Briefing and Correspondence), implemented in December 2025. Whilst the EDRMS project is effectively delivered, its status remains AMBER due to ongoing ingestion of data into Records365 and progressive roll out of the briefing product. This will be continued as part of the funded BAU support and iterative enhancement activity in 2026 to enable full roll out of the EDRMS capability across the organisation.
Q4 25-26 | Victoria Police | VicPol | 3359 | Finance Systems Program (Oracle Cloud) | Law and Justice | Investment Management | Delivery of a new financial system, updating technology and business processes across finance, purchasing and supply chain functions to increase efficiency and improve access to accurate information to support decision-making. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2021-11-25 |  | 2025-06-30 |  | 32453000 |  | Red | Red | Red | Red | Amber | The project recommenced in June after a 6-month pause. Replanning and re-initiation activities have commenced, supporting a return to an overall Amber status.
Q4 25-26 | Victoria Police | VicPol | 3360 | Enterprise Rostering | Law and Justice | Human Capital / Workforce Management | The project will deliver an enterprise wide rostering and timesheet solution, consolidating disparate systems and manual processes into one integrated system to better support rostering and timesheet management. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2020-11-25 | 2021-11-24 | 2024-12-31 | 2025-09-30 | 21490000 | 21490000 | Red | Red | Red | Red | Red | The project has returned to initiation phase to validate business requirements, delivery scope and timelines The project has been re-established under the guidance of a new Project Control Board with current activities focussing on a revised delivery schedule and project approach.
Q4 25-26 | Department of Government Services | DGS | 3377 | Digital Victoria Marketplace | Government and Economy | Collaboration ,Data Management,Records Management | The Marketplace is an initiative by Digital Victoria to provide a simpler, and easier way for Government and Industry to interact through the eServices register and various other SPC's. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-10-01 | 2021-10-13 |  | 2021-10-13 | 0 | 7708 | 2022-02-01 |  | 2027-06-30 | 2026-09-30 | 16790000 |  | Green | Green | Green | Green | Green | The Digital Marketplace is finalising the program of work.
Q4 25-26 | Alfred Care Group – Bayside Health | ALFRED Care Group | 3378 | Alfred Health / Monash Health - Shared Laboratory Information System | Health | Records Management | The shared LIS program will deliver a Laboratory information system as a foundational technology for the Alfred Monash Pathology partnership supporting the DoH Pathology sector reform initiative to consolidate pathology systems and services. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2026-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-10-05 | 2022-08-31 | 2023-02-28 | 2023-02-28 | 2000000 | 2000000 | 2023-02-28 |  | 2025-06-30 | 2026-06-30 | 25000000 | 41800000 | Red | Amber | Amber | Amber | Green | The Laboratory Information System was successfully deployed across all planned health services — Bayside Health (Alfred Care Group) in January 2026 Western Health in February 2026 and Monash Health in May 2026. The Hypercare support periods for Western Health and Monash Health were extended to address solution issues identified post go-live and requiring additional resolution time. One remaining defect has a management plan in place and time for resolution with ownership transferred to the operations team.
Q4 25-26 | Department of Transport and Planning | DTP | 3399 | Victraffic Upgrade Project | Transport and Vehicles | Communication,Customer Initiated Assistance,Customer Preferences | Objective of this project is to support transport users and emergency response units to safely and confidently move around our road network during an emergency situation and improve road closure capture and uplift the user experience. | Closed - Completed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2026-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-27 | 2022-09-19 | 2023-07-10 | 2023-07-10 | 0 |  | 2023-07-10 |  | 2024-06-30 | 2026-06-30 | 22637000 |  | Green | Green | Green | Green | Green | Project delivery activities are now completed.
Q4 25-26 | Court Services Victoria | CSV | 3451 | Victorian Civil and Administrative Tribunal digital service transformation | Law and Justice | Content Management,Customer Initiated Assistance,Development and Integration ,Security Management ,Tracking and Workflow,Data Management,Document Management ,Forms Management,Knowledge Management ,Management of Process ,Records Management ,Routing and Scheduling | The project aims to upgrade digital services infrastructure including the case management system and increase process automation, to deliver more accessible and timely provision of justice to citizens and businesses | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - Waterfall and Agile | 2020-11-01 | 2021-02-04 |  | 2021-05-15 | 0 |  | 2021-07-01 | 2021-07-01 | 2024-12-01 | 2027-06-30 | 56681000 |  | Amber | Amber | Amber | Amber | Amber | The implementation of Guardianship list was completed in the quarter as planned, and remaining residential tenancies case types, achieving over 90% of VCAT's cases being managed on the CMS.
Q4 25-26 | Victorian Institute of Forensic Mental Health (Forensicare) | Forensicare | 3458 | Human Capital Management (HCM) Rostering Payroll System | Health | Human Capital / Workforce Management ,Human Capital / Workforce Management | Forensicare is implementing a new Human Capital Management system to replace and integrate its ageing payroll, rostering and recruitment systems. This system will better meet staff needs and improve capacity for better care to growing customer base | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-08-23 | 2022-09-08 | 2023-12-11 | 2023-12-11 | 0 | 221000 | 2024-01-15 |  | 2025-09-30 | 2027-02-26 | 2580000 |  | Amber | Amber | Green | Green | Green | Pre-discovery and discovery (design) is underway and the project remain on track and Green and working toward the delivery of Phase 2. Note: The schedule revision is to incorporate Phase 2 delivery timeframe.
Q4 25-26 | V/Line Corporation | V/Line | 3465 | Payroll Improvements | Transport and Vehicles | Human Capital / Workforce Management | The objective of the payroll improvement project is to improve data collection for Leave, Time & Attendance information to support V/Line’s payroll function, in creating a more robust and consistent payroll operation organisation wide. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2023-03-31 | 2024-05-31 | 2024-05-31 | 0 | 500000 | 2024-06-03 | 2024-12-09 | 2025-09-30 | 2027-06-30 | 3300000 |  | Green | Green | Green | Green | Amber | During the quarter, the project experience delays in delivering the payroll exception reports, due to resourcing constraints. The Payroll Improvement Program was integrated into the HRIS Program, creating a single governance and delivery framework for workforce management, and specialist capability was recruited to support business rule analysis and future system configuration. Despite delays to contract negotiation with the preferred Human Capital Management (HCM) vendor, preparation continued across payroll, time and attendance, leave management, integrations and data migration
Q4 25-26 | Central Highlands Region Water Corporation | CHR Water | 3466 | Digital Metering Program | Environment and Water | Customer Initiated Assistance,Customer Relationship Management | Replace analogue meters with digital, resulting in improved customer experience, reduced operational risk, improved environmental and sustainability footprint, and utilise water meter data to provide greater oversight of the water and sewer network. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Eco Improvement (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2020-07-01 | 2022-12-31 |  | 2023-01-02 | 0 |  | 2023-01-02 |  | 2026-09-30 | 2026-12-30 | 19500000 | 20708032 | Green | Green | Green | Green | Green | Project proceeding to stakeholder expectations
Q4 25-26 | Melbourne Health | Melb H | 3496 | Parkville Laboratory Information System (LIS) Program | Health | Management of Process ,Records Management ,Systems Management,Tracking and Workflow | The LIS Connect Program will procure and implement a single LIS solution for Pathology Network West across the Parkville precinct pathology services. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2022-03-01 | 2023-12-31 | 2024-07-31 | 2024-07-31 | 6047518 |  | 2024-09-23 |  | 2026-08-28 |  | 23817159 | 31572148 | Amber | Amber | Amber | Red | Red | The program continues to track Red overall. Go live remains deferred. The new go live date will be determined pending resolution of the Protected Industrial Action (PIA) and informed by the formal re-baselining exercise.
Q4 25-26 | Department of Transport and Planning | DTP | 3497 | Victorian Transport Digital Engineering Transformation Program | Transport and Vehicles | Assets/Materials Management,Content Management,Data Management,Document Management ,Visualisation | Objective of this project is to develop a roadmap to progressively move to a digital environment for engineering, design and data management. DoT and MTIA will collectively deliver the DE Transformation, Horizon 1 -3 projects over the next 2-3 years. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-04 | 2022-12-30 | 2023-02-06 | 2023-02-06 | 0 |  | 2023-02-06 |  | 2023-12-29 | 2027-06-30 | 5135000 | 47018755 | Amber | Amber | Amber | Amber | Amber | The program is reporting an amber status as it is managing challenges related to procurement, HR, and finance processes. All planned go-live activities have now been completed successfully. The project team is currently involved in planning for prioritising forward scope.
Q4 25-26 | Peninsula Care Group – Bayside Health | PEN Care Group | 3522 | Peninsula Health NHCA Smart Ward | Health | Business Intelligence | National Centre for Healthy Aging (NCHA), a Monash University (MU) and Peninsula Health (PH) collaboration, has established a program of works that includes the establishment of a Smart Ward to collect patient observations for Research. | Closed - Completed | Customer Satisfaction (Non Financial) | 2026-05-12 | PRINCE2 | 2022-11-07 | 2023-01-31 | 2024-02-29 | 2024-03-07 | 0 | 19968 | 2024-03-07 |  | 2025-07-31 | 2026-05-12 | 1222641 | 1144372 | Green | Green | Green | Green | Green | Project completed officially May 12.
Q4 25-26 | Ambulance Victoria | AVS | 3547 | Cloud & Infrastructure Program | Health | Assets/Materials Management | The program will upgrade network infrastructure and address the closure of data centres and the end-of-life of data centre assets through migrating workloads to Cloud. This program will deliver improved security and performance for our services. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-04 | 2023-01-31 |  | 2023-01-31 | 341911 | 155621 | 2023-02-01 |  | 2025-11-28 | 2027-06-30 | 18295989 | 14522917 | Green | Red | Red | Red | Red | The project remains red pending final budget confirmation. Delivery continues to progress well with key systems and a major test environment transitioned in Q4. The project will be rebaselined once the budget is confirmed.
Q4 25-26 | Royal Children's Hospital | RCH | 3551 | Identity and Access Management (IDAM) | Health | Security Management | Implementation of new identity management solution | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2022-11-28 | 2023-06-02 | 2025-01-23 | 2025-01-23 | 0 |  | 2025-01-23 |  | 2025-12-31 | 2026-12-17 | 3368053 |  | Green | Green | Green | Amber | Green | The Requirement Traceability Matrix, Design and Test Plans were reviewed and approved. All configuration was moved from Sandbox to the test environment during the last quarter.
Q4 25-26 | Loddon Mallee Rural Health Alliance | LMRHA | 3563 | Regional integrated Electronic Patient Record | Health | Records Management | Delivery of an integrated Electronic Patient Record for members of the Loddon Mallee Rural Health Alliance (excluding Bendigo Health) - this will support more connected patient care for patients region wide. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-10-03 | 2023-06-30 | 2026-10-30 |  | 70000 | 0 | [11 empty] | Planning continues, working towards finalising the contract with vendor. Upon contract signature, project initiation will be completed. Project initiation end date is tentatively expected by end of October.
Q4 25-26 | Loddon Mallee Rural Health Alliance | LMRHA | 3575 | Patient Administration System Replacement | Health | Data Management,Records Management ,Reporting | Replacement of Bendigo Health's current Patient Administration System (PAS) solution to align with the Electronic Patient Record (EPR) - moving to a single for both capabilities will ensure smoother patient care and support. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-06-06 | 2023-06-30 | 2023-09-30 | 2023-10-02 | 150231 |  | 2023-10-23 |  | 2025-07-15 | 2026-12-04 | 4930809 |  | Red | Amber | Amber | Amber | Amber | The project status is AMBER due to risks associated with the timeline to Go Live. Approach to Go Live has been approved, however there is still some risk present with the date and approach. This will be monitored closely by the project.
Q4 25-26 | Department of Health | DH | 3599 | Mental Health and Wellbeing Website | Health | Communication | This project will deliver a mental health website, addressing recommendations 6.4 and 31.3 of the Royal Commission into Victoria's Mental Health System, to help Victorians navigate the mental health system and find relevant services and supports. | Postponed |  | 2023-06-30 | Agile | 2022-09-21 | 2023-05-12 | 2023-06-30 |  | 843493 | 1185694 |  |  |  |  | 0 | [6 empty] | Project on pause due to priority being given to other mental health and wellbeing initiatives.
Q4 25-26 | South West Alliance of Rural Health | SWARH | 3602 | HR Digital Solution | Health | Human Resources | The scope of the strategic HRIS is to replace the Health Services HR applications and manual, paper-based processes with a contemporary, fit-for-purpose, strategic HRIS solution. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2023-02-24 | 2023-10-27 | 2023-12-01 | 2023-12-01 | 834297 |  | 2024-01-15 |  | 2026-04-30 |  | 13629603 |  | Red | Red | Red | Red | Red | The project has been delayed with the Rostering project now a core dependency. This has impacted schedule, scope and budget.
Q4 25-26 | Central Highlands Region Water Corporation | CHR Water | 3612 | ERP Upgrade | Environment and Water | Assets/Materials Management,Financial Management,Human Capital / Workforce Management ,Supply Chain Management | This project will upgrade the existing platform(s) due to an impending end of support timeline with a contemporary integrated solution to improve the Finance, Procurement, Commercial and Asset Management processes of CHW | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-01-02 | 2023-06-30 | 2023-09-29 | 2023-09-29 | 0 |  | 2023-10-02 |  | 2025-09-30 | 2026-12-18 | 9510000 | 11910255 | Green | Green | Green | Green | Green | The project is tracking in line with stakeholder expectations
Q4 25-26 | Eastern Health | EH | 3638 | Enable Program | Health | Human Capital / Workforce Management ,Human Resources | Enable success of our people through 3 x HR systems projects: 1. Rostering Project - Replace RosterOn with Optima 2. People Journey Project - Replace eMercury with SAP SuccessFactors 3.Initiate Payroll Project - Replace SAP Payroll with SAP SF | Closed - Completed | Cost Reduction (Financial), Risk Reduction (Non Financial) | 2026-03-31 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-10-01 | 2023-03-31 |  | 2023-06-07 | 75000 |  | 2023-06-07 |  | 2025-10-31 | 2026-04-30 | 10148335 | 10592143 | Green | Green | Green | Amber | Green | The project has closed with successful delivery of Rostering tool and Initiation of Enable Program- Success Factors ECP Payroll Project.
Q4 25-26 | WorkSafe Victoria | WorkSafe | 3642 | Digital Identity Uplift (Enterprise IDAM Uplift) | Employment, Skills and Workplace | Systems Management | Uplift the Digital Identity environment to ensure people have the right access to resources, at the right time. This will enhance the user experience and strengthen security controls. Project name was changed from Enterprise IDAM Uplift. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-02-01 | 2023-03-31 |  | 2023-04-04 | 0 |  | 2023-06-05 |  | 2025-06-30 | 2026-10-31 | 4316783 | 4224778 | Red | Red | Green | Green | Red | The program has been affected by technical complexities that have impacted the delivery timelines. A change request is in progress to extend the schedule to enable the resolution of the technical issues.
Q4 25-26 | Grampians Rural Health Alliance | GRHA | 3645 | Maryborough Hospital Redevelopment ICT Project | Health | Development and Integration ,Systems Management | The Maryborough Hospital redevelopment ICT project provides infrastructure integration of clinical equipment mobile/desktop devices to support clinical care in the new state-of-the-art healthcare facility; improving care outcomes for patients. | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-12-01 | 2021-06-01 |  | 2021-06-01 | 0 |  | 2021-06-01 |  | 2025-06-30 | 2026-12-31 | 5158000 |  | Green | Green | Green | Green | Green | ICT equipment and systems operational in new hospital. Minor project works continue to close out post Practical Completion activities; expected to complete by end of year.
Q4 25-26 | Triple Zero Victoria | TZV | 3651 | Next Generation Computer Aided Dispatch System | Emergencies and Safety | Systems Management | Implement a new enhanced, reliable and secure emergency services Computer Aided Dispatch system to support enhanced critical emergency services 000 call taking and dispatch capability. | Delivery | Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-07-01 | 2024-11-27 | 2024-12-01 | 20588172 |  | 2024-12-02 |  | 2027-06-30 | 2028-06-30 | 233301093 |  | Green | Green | Green | Amber | Amber | The project is reporting an Amber status due to increased schedule risk identified in Q3 2025-26. It continues to progress through the delivery and implementation phase including detailed design build and testing of the Next Generation CAD system. There is no change to the planned transition to operational service in June 2028 under the re-baselined schedule.
Q4 25-26 | Gippsland Health Alliance | GHA | 3654 | EMR Rural Expansion (Phase 4) | Health | Records Management | Expansion of EMR into 6 x Rural health services in the Gippsland Region | Closed - Completed | Compliance (Non Financial), Customer Satisfaction (Non Financial) | 2026-04-30 | PMBoK | 2023-03-14 | 2023-11-30 | 2024-11-22 | 2024-11-22 | 200000 | 2675777 | 2025-03-12 |  | 2025-11-11 | 2026-04-30 | 3383375 | 5319434 | Green | Green | Green | Green | Green | Primary project scope has been completed, and project closure approved by the governance committee.
Q4 25-26 | Northern Health | NH | 3666 | Patient Engagement/Entertainment System (PES) | Health | Communication | To provide patient TVs and other supported clinical workflows for better patient care at Northern Health | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-02 | 2021-12-31 |  | 2021-12-31 | 50000 |  | 2023-02-01 | 2023-08-01 | 2024-07-30 | 2026-10-31 | 3450000 |  | Amber | Green | Green | Green | Green | The new project manager has identified five televisions that were accidentally omitted during the initial migration. These units will be brought online as soon as the outstanding cabling works are finalised
Q4 25-26 | Queen Elizabeth Centre | QEC | 3667 | Client Information Management System | Health | Data Management,Document Management ,Forms Management,Management of Process ,Reporting | QEC is focused on developing a Client Information Management System (CIMS) that can accommodate growth diversity and emerging evidence; enable clinical implementation of the outcomes framework; and meet funding and reporting requirements. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-11-23 | 2023-10-18 | 2023-11-15 | 2023-11-29 | 225000 | 283153 | 2023-12-04 |  | 2025-12-30 | 2026-09-30 | 1314347 | 1413472 | Green | Green | Green | Green | Green | Project is tracking as expected.
Q4 25-26 | Grampians Rural Health Alliance | GRHA | 3688 | Ballarat Base Hospital Redevelopment - ICT Program - Stage 3 | Health | Systems Management | Stage 3 will deliver ICT systems to support the project works, improving patient and staff systems & support. | Delivery | Social Improvement (Non Financial) |  | PMBoK | 2022-01-03 | 2025-12-01 | 2026-02-27 | 2026-02-27 | 0 |  | 2026-02-27 |  | 2027-12-17 |  | 21370116 |  |  |  |  | Green | Amber | 2 major ICT packages have been awarded and works have commenced. Remaining scoping & procurement activities will continue to occur though until late 2026. Delays in additional funding approval is impacting project resourcing and timelines.
Q4 25-26 | Hume Rural Health Alliance | HRHA | 3694 | ICT transition to Hume Rural Health Alliance (KDHS) | Health | Organisational Management | The project will transition Kyabram District Health Service (KDHS) ICT from Loddon Mallee Rural Health Alliance to Hume Rural Health Alliance to provide IT oversight and support. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-03-31 |  | 2024-04-24 | 100000 | 37000 | 2024-04-24 |  | 2025-06-30 | 2026-12-31 | 3463000 |  | Amber | Amber | Amber | Amber | Amber | The KDHS telephony migration from LMSS to HRHA was successfully completed in June 2026. The primary CGN link at Stanhope was also established. The project governance group is reviewing the potential migration of additional clinical systems that are currently out of scope. Implementation approach timeline and costs for Payroll and Time & Attendance remain under review.
Q4 25-26 | Grampians Rural Health Alliance | GRHA | 3695 | MDHS ICT transition to Grampians Rural Health Alliance | Health | Organisational Management | The project will transition Maryborough District Health Service from Loddon Mallee Rural Health Alliance to Grampians Rural Health Alliance to better align with natural patient flows in the region (improved patient experience ). | Delivery | Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-11-17 | 2025-04-01 | 2025-04-01 | 0 | 150000 | 2025-04-01 |  | 2026-12-31 | 2027-04-30 | 3450000 |  | Green | Green | Amber | Red | Red | Delivery of critical path work packages are being prioritised as foundational activities. The project remains in red status due to uncertainty around end dates and dependencies for later (application transition) tranches.
Q4 25-26 | Loddon Mallee Rural Health Alliance | LMRHA | 3696 | HR Information System | Health | Human Capital / Workforce Management | Implementation of a Human Resources Information System (HRIS) for members of Loddon Mallee Rural Health Alliance -this uplift will enable resource planning and management visibility across the region. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-12-31 |  | 2023-12-31 | 65000 | 175000 | 2024-01-01 | 2025-08-28 | 2025-12-20 | 2027-04-30 | 13500000 |  | Amber | Amber | Amber | Green | Green | Project is on track with no high risks or issues. Final playbacks have been completed and received positively with stakeholders. The project is now moving into system testing and preparation for user acceptance testing, scheduled for August. Communications and training planning is underway, with a change network being established across all health services.
Q4 25-26 | Transport Accident Commission | TAC | 3698 | Digital Identity Uplift | Transport and Vehicles | Systems Management | Uplift the Digital Identity environment to ensure people have the right access to resources, at the right time. This will enhance the user experience and strengthen security controls. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-05-18 | 2023-05-18 |  | 2023-05-18 | 0 |  | 2023-06-05 |  | 2025-06-30 | 2026-10-31 | 4316783 |  | Red | Red | Green | Green | Red | The program has been affected by technical complexities that have impacted the delivery timelines. A change request is in progress to extend the schedule to enable the resolution of the technical issues.
Q4 25-26 | V/Line Corporation | V/Line | 3699 | HRIS (Human Resources Information System)​ system replacement | Transport and Vehicles | Human Capital / Workforce Management ,Human Resources | To implement a new human resource information system for V/Line, in order to improve accuracy and reliability of HR data for service delivery. | Initiated |  |  | PRINCE2 | 2023-07-01 | 2024-11-29 | 2026-07-31 |  | 900000 | 1476107 | [11 empty] | The HRIS project is at the contract negotiation stage. Negotiations with the preferred Human Capital Management (HCM) vendor remain constructive, implementation readiness activities continued, including integration and data migration planning, data mapping, and business process documentation. The Payroll Improvement Program was also integrated with the HCM Program, creating a single program of work from July 2026 to support more coordinated delivery of workforce management transformation
Q4 25-26 | Department of Health | DH | 3731 | Managed Services Provider Replacement (MSPR) | Health | Data Management,Development and Integration | Replacement of the Managed Service Provider (MSP) for the Oracle Cloud Infrastructure tenancies to better support the departments operations. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2023-06-01 | 2023-06-30 |  | 2023-06-30 | 0 |  | 2023-07-01 |  | 2025-12-31 | 2026-12-31 | 1412500 | 1088061 | Amber | Amber | Amber | Amber | Amber | Project is reporting an Amber health status due to earlier resourcing issues which have impacted the schedule. These have now been resolved, with the procurement evaluation progressing.
Q4 25-26 | Department of Health | DH | 3733 | St Vincent's Electronic Medical Record Project | Health | Analyses and Statistics ,Collaboration ,Communication,Forms Management,Organisational Management ,Records Management | Implementation of an electronic medical record (EMR) to streamline clinical documentation medication management and other clinical activities to support the provision of safer higher quality and more efficient patient care. | Initiated |  |  | PRINCE2 | 2023-09-01 | 2024-07-01 | 2026-12-01 |  | 0 | 4300000 | [11 empty] | The primary focus of the St Vincent's Hospital Melbourne Electronic Medical Record (EMR) project continues to be on procurement and contracting processes in collaboration with another Victorian health service. Organisational readiness tasks continue including development of program governance models and technical readiness.
Q4 25-26 | Lower Murray Urban and Rural Water Corporation | LMUR Water | 3749 | Technology Uplift Program (Formerly - Business Transformation Program) | Environment and Water | Customer Relationship Management,Data Management,Financial Management,Human Capital / Workforce Management ,Human Resources,Reporting ,Supply Chain Management | Enabling LMW of the Future. The program will uplift capabilities across key business functions, including customer service, billing, assets and workforce and financial management to enable improved customer service and efficiency.​ | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2024-02-02 | 2024-05-30 | 2024-05-31 | 899582 |  | 2024-06-03 |  | 2026-06-30 | 2026-10-30 | 12100105 | 16039210 | Green | Green | Green | Green | Green | Scheduled activities are proceeding as planned with minimal/no impacts for this quarter.
Q4 25-26 | Department of Families, Fairness and Housing | DFFH | 3756 | Communities and Families Transformation - Stage 1 | Community Services | Customer Relationship Management | Deliver a business case with options for strategic investment in technology platforms, underpinning delivery of care services to communities and families, to enable seamless interactions and experience for our clients and sector partners. | Closed - Completed | Social Improvement (Non Financial), Workforce Satisfaction (Non Financial) | 2026-06-30 | PRINCE2 | 2022-08-15 | 2024-01-11 | 2023-01-11 | 2023-06-19 | 0 |  | 2023-07-01 |  | 2025-06-30 | 2026-06-30 | 14429000 | 16282000 | Green | Green | Green | Green | Green | The business case setting out multiple delivery options has been completed and submitted and funding has been provided through the 2026–27 Budget process. Project is now complete.
Q4 25-26 | Yarra Valley Water | YV Water | 3762 | Enterprise Analytics Platform - Phase 2 | Environment and Water | Data Management | Replacement of YVW's data warehouse, operational data-store and business intelligence reporting technologies with a modern, scalable data and analytics platform | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2023-09-01 | 2023-09-30 |  | 2023-09-30 | 0 |  | 2023-10-01 |  | 2025-04-28 | 2026-06-30 | 6640340 | 8243140 | Amber | Amber | Amber | Amber | Amber | The project remains at Amber status due to significant schedule delays. The original vendor contract was terminated, and the procurement process for a replacement vendor is nearing completion. Subject to final vendor appointment, project delivery is expected to recommence in August 2026.
Q4 25-26 | Melbourne Polytechnic | MelbPoly | 3767 | Melbourne Polytechnic Student Management System Implementation | Employment, Skills and Workplace | Systems Management | Selection and Implementation of new Student Management System for Melbourne Polytechnic to improve student and user experience, increase digitalisation and automation, and improve functionality and compliance. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-29 | 2023-12-31 |  | 2024-01-08 | 182000 |  | 2024-01-15 |  | 2027-01-29 | 2027-07-30 | 7818000 | 13258270 | Green | Green | Green | Green | Green | Project progressing to revised plan and targets with some pressure on schedule. Further stage gate review underway with governance group decision on impact due in next period.
Q4 25-26 | Department of Transport and Planning | DTP | 3773 | Future Public Transport Ticketing System | Transport and Vehicles | Customer Initiated Assistance,Customer Preferences,Financial Management,Systems Management | The future Public Transport Ticketing (PTT) System will deliver modern customer payment features and progressively replace the current myki Ticketing System (myki System) | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-07-01 | 2021-10-18 |  | 2021-10-18 | 0 |  | 2021-10-18 |  | 2028-06-30 | 2028-12-31 | 543000000 | 680350000 | Green | Green | Green | Green | Green | The program is reporting an overall status as green. The program implementation activities are ongoing.
Q4 25-26 | Melbourne Water | MELB Water | 3807 | Network Resilience FY25-26 | Environment and Water | Assets/Materials Management | To continue investing in our IT network ensuring that we reduce the risk of unplanned network outages meet compliance requirements improve our security posture increase capacity reliability and bandwidth to accommodate future growth. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PMBoK | 2023-12-08 | 2024-02-27 |  | 2024-07-24 | 0 |  | 2024-07-24 | 2024-10-22 | 2026-06-22 | 2027-06-30 | 4966804 | 5989000 | Red | Amber | Red | Amber | Green | As at 20260630: change request approved. Project on track.
Q4 25-26 | WorkSafe Victoria | WorkSafe | 3811 | Contact Centre Capability Uplift | Employment, Skills and Workplace | Communication | WorkSafe’s telephony system is built upon ageing infrastructure and tech. The introduction of a contact-centre-as-a-service will uplift person-centred services and ensure continuity for frontline support of injured workers & the Victorian community. | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2026-06-30 | PRINCE2 | 2022-01-01 | 2023-11-26 |  | 2023-12-11 | 441569 | 326274 | 2023-12-11 |  | 2025-12-31 | 2026-06-30 | 7321441 | 3867488 | Green | Green | Green | Green | Green | On track. Project now closed.
Q4 25-26 | Grampians Rural Health Alliance | GRHA | 3812 | Grampian Health - Electronic Medical Record System | Health | Data Management | Implementation of an Electronic Medical Record system across five campuses of Grampians Health, namely Ballarat, Dimboola, Edenhope, Horsham, and Stawell. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-10-31 | 2028-06-30 | 2026-12-01 |  | 0 | [12 empty] | The Grampians Health Electronic Medical Record (EMR) Project continues to prioritise procurement and contracting activities in collaboration with another Victorian health service. Organisational readiness work remains on track, with ongoing progress across Network Uplift, Data preparation, stakeholder engagement, and supporting infrastructure to ensure readiness for implementation.
Q4 25-26 | Ports Victoria | PortsVic | 3824 | Port Management Information System (PMIS) Project | Transport and Vehicles | Routing and Scheduling | Implementation of a Port Management Information System (PMIS), directly supporting the management of maritime navigation and operational safety, providing safe, fair, and efficient access for the commercial ports of Melbourne, Geelong and Hastings. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-03 | 2024-12-20 | 2026-07-31 |  | 0 | 249990 | [11 empty] | The Blueprint and pre-contract readiness phase was completed in March 2026, providing the agreed implementation scope, cost and delivery baseline. Governance Committee approval of the final business case was obtained in late April 2026, enabling progression to commercial negotiations and contract finalisation. Contract execution is targeted for mid July 2026, with the project expected to transition into implementation mobilisation by late July 2026.
Q4 25-26 | Chisholm Institute of TAFE | Chisholm TAFE | 3825 | Chisholm Student Management System Transformation Project | Employment, Skills and Workplace | Records Management | The project will migrate legacy student management system to new technology offered by the existing vendor to minimize technology risk and maintain student experience and business continuity. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-01-09 | 2023-05-31 |  | 2023-05-31 | 0 |  | 2023-11-16 |  | 2026-09-25 | 2027-12-31 | 8000000 |  | Green | Green | Green | Amber | Amber | Following a detailed review, Chisholm is working collaboratively with the vendor to manage the timelines for the design and build of complex functionality, while ensuring adequate time is allocated for critical downstream activities required before go-live.
Q4 25-26 | Department of Transport and Planning | DTP | 3828 | Trusted and Secure Program | Transport and Vehicles | Data Management,Security Management ,Systems Management | The objective of this program is to implement cyber and information security standards, enhancing information security measures and reducing risks of cyber incidents, by embedding robust and proactive cyber security practices. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2023-10-02 |  | 2023-10-02 | 0 |  | 2023-10-03 |  | 2024-06-30 | 2027-06-30 | 6800000 | 17334852 | Amber | Amber | Amber | Green | Green | The program remains on track and reporting overall status as green with six projects in progress.
Q4 25-26 | Austin Health | AH | 3837 | CRM Statewide Project | Health | Customer Relationship Management | Make five CRM modules available to all metropolitan and some regional health agencies, improving referral management and waitlist management, providing efficiencies and improved waiting lists. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-01 | 2023-12-22 |  | 2023-12-22 | 0 |  | 2024-01-02 |  | 2024-12-31 | 2026-06-30 | 4565000 | 9509070 | Green | Green | Green | Green | Green | - Deployed Module 1 (PSA) at LaTrobe - Deployed Module 4 (SCA) at Royal Victorian Eye and Ear - Deployed Module 2 (HQM) at Barwon - Module 5 (ERM) deployment halted due to lower uptake - Commenced build of Inter Hospital Transfer (Module 3) - Complete POC in Clinical Audit module
Q4 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3839 | Biosciences Advanced Scientific Computing (BASC) Infrastructure Refresh Project | Government and Economy | Knowledge Discovery | The BASC Infrastructure Refresh project will deliver refreshed infrastructure to replace an end-of-life system that supports agricultural research. This project will be delivered in three phases over the next three years. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Eco Improvement (Non Financial), Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-09-25 | 2024-06-28 | 2024-12-31 | 2024-12-31 | 150000 | 399415 | 2025-01-01 |  | 2027-12-18 |  | 3675686 | 6394256 | Amber | Green | Green | Green | Amber | The project continues to progress with the hardware deployment, and the BASC system is operating effectively. The project status is reported as Amber due to international supply constraints and cost escalation impacting Phase 3. An order has been placed, with delivery scheduled for Q3 2026.
Q4 25-26 | Barwon Region Water Corporation | BR Water | 3841 | C1430 - Network Segmentation | Environment and Water | Security Management | The Network Segmentation project will segregate and segment the operational and corporate networks reducing the impact and recovery time of a network security breach ensuring the reduction in cyber incident risk profile and improved SOCI compliance. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-02-01 | 2023-04-14 |  | 2023-04-14 | 15000 |  | 2023-04-14 |  | 2024-11-07 | 2026-12-31 | 1477000 | 2983000 | Green | Amber | Amber | Green | Green | The IT/OT separation is on schedule. The OT Network is in production and the 7 medium to large sized Water Treatment and Reclaimation plants have been cutover to the new OT Network successfully. Planning for IT Segmentation is ongoing.
Q4 25-26 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3843 | Human Resources Information System Replacement | Education | Human Resources | Replace BKI’s ageing HR and Payroll systems with a modern cloud-based platform which will enable improved HR processes, improved user experience and significantly improved people data and reporting. | Closed - Completed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2026-04-29 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-09-01 | 2023-12-08 |  | 2023-12-08 | 370000 | 125000 | 2024-02-01 |  | 2025-03-31 | 2026-04-29 | 2643965 | 3161265 | Red | Red | Red | Red | Red | The HRIS system has been successfully implemented, with the Payroll module identified as the remaining outstanding component. The project has been formally closed, with Payroll to be delivered through the Victorian TAFE sector-led HRIS project.
Q4 25-26 | Department of Health | DH | 3844 | Security Access Modernisation | Health | Systems Management | Cloud application migration from legacy TAM6 to ISVA10 environment, and engagement with business teams to transition their onboarding process to use Departmental User Onboarding Portal V2, reducing operational risk of the unsupported TAM6 platform. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-06-28 |  | 2024-06-28 | 574077 |  | 2024-06-28 |  | 2025-06-30 | 2026-06-30 | 1413388 | 1757986 | Green | Green | Green | Amber | Amber | Project is amber due to scope change and will be extended. Schedule is currently being reviewed and will be updated in next reporting period.
Q4 25-26 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3845 | Apprentice and Trainee Management Module Implementation | Education | Systems Management | This project will deliver functionality into the core student management system to be enable apprentice and trainee student management. This will bring all BKI students management onto one platform, reducing integration and data risks | Closed - Completed | Increased Revenue (Financial) | 2026-04-29 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-30 | 2023-12-08 |  | 2023-12-08 | 200000 |  | 2024-01-08 |  | 2025-06-30 | 2026-04-29 | 3157730 | 4311828 | Red | Red | Red | Red | Red | ATMM has been formally closed as a major project following partial delivery of the original scope. Remaining priority outcomes will be delivered through future sector-aligned initiatives, leveraging solutions being implemented across the Victorian TAFE network
Q4 25-26 | Workplace Injury Commission | WIC | 3853 | Case Management System | Law and Justice | Tracking and Workflow | Implementation of a new case management system that improves efficiency and productivity, to support the resolution of workplace injury disputes for Victorian workers. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-02-14 | 2024-10-30 | 2025-05-28 | 2025-05-28 | 0 | 1900000 | 2025-05-29 |  | 2027-06-30 |  | 12000000 |  |  | Green | Green | Green | Amber | The overall status reflects the aggregation of schedule, risks, issues and resources. The planning and design phase has been extended to ensure requirements and solution design are fully validated, with increased project focus supporting the resolution of current issues and reducing delivery risk.
Q4 25-26 | Department of Health | DH | 3856 | Mental Health and Wellbeing Client Management System Implementation Project (MHWCMS) | Health | Data Management,Development and Integration | Delivery of a Mental Health and Wellbeing Client Management System to the Mental Health Sector to replace CMI/ODS and acquit recommendation 62 in the Royal Commission into Victoria’s Mental Health System. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2023-12-01 | 2023-12-22 |  | 2023-12-22 | 0 |  | 2024-01-01 |  | 2026-06-30 | 2028-06-30 | 40229527 | 64701864 | Red | Red | Red | Amber | Amber | Overall status remains Amber due to outstanding vendor dependencies and rollout planning activities. Budget is tracking well, while schedule continues to require close management.
Q4 25-26 | North East Link State Tolling Corporation | NELSTC | 3858 | Toll Collection Capability (TCC) - Roadside Systems (RSS) | Transport and Vehicles | Analyses and Statistics ,Communication,Data Management,Development and Integration ,Records Management ,Reporting | The Roadside Systems will effectively & efficiently detect vehicles and capture tag or vehicle details ensuring toll revenue is collected accurately and road users have a seamless experience while accessing North East Link. | Initiated |  |  | PMBoK | 2023-06-27 | 2025-09-26 | 2026-11-01 |  | 1117000 | [12 empty] | The TCC RSS contract was awarded in FY25 Q4 and now in the delivery phase. RSS activities are progressing to plan and in Detailed Design Phase. The project will remain in initiation until all BOS Procurement completes in 2026-27 to maintain procurement integrity. The TCC RSS and TCC BOS projects are complementary streams of the one project which share a budget. Disclosing the full cost of TCC RSS could potentially enable TCC procurement respondents to derive the BOS budget compromising procurement integrity and competitive positioning. The Revised Initiation End Date reflects this approach.
Q4 25-26 | North East Link State Tolling Corporation | NELSTC | 3859 | Toll Collection Capability (TCC) - Back Office Systems (BOS) | Transport and Vehicles | Communication,Customer Initiated Assistance,Customer Relationship Management,Management of Process ,Reporting | The Back Office Systems will efficiently manage trip formation, interoperability between Australian Toll Roads, billing and collection of toll revenue while providing road users an efficient way to pay for their travel on North East Link. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-27 | 2026-06-29 | 2026-11-01 |  | 1117000 | [12 empty] | The project will remain in initiation until procurement completes in 2026-27 to maintain procurement integrity. This includes the procurement of ancillary systems and services for the BOS package. The BOS procurement activities are progressing in line with baseline schedule and forecasted within the approved budget.
Q4 25-26 | Coliban Region Water Corporation | Coliban Water | 3860 | Core Capability Uplift | Environment and Water | Financial Management | New software implementation and business processes optimisation to uplift the Commercial and Financial Management capabilities, directly contributing to the strategic goals of ‘Financial Sustainability’ and ‘An Adaptive and Resilient Organisation’. | Delivery | Efficiency/Productivity (Non Financial) |  | PMBoK | 2023-08-08 | 2024-07-02 | 2025-07-02 | 2025-07-02 | 0 |  | 2025-07-07 |  | 2026-08-13 | 2026-11-30 | 11070000 |  |  | Amber | Green | Green | Green | The project remains on track.
Q4 25-26 | Greater Western Water Corporation | GW Water | 3863 | Asset, Works & Field Services Mgmt Consolidation (Concordia) | Environment and Water | Assets/Materials Management,Collaboration ,Data Management,Development and Integration ,Human Capital / Workforce Management ,Reporting ,Systems Management | AWFSMC serves as a foundational pillar to transform future ready Field Service mgmt & Asset & Works Mgmt capabilities . It will increase business & customer satisfaction & will be delivered in phases with budget increases reflecting each phase | Delivery | Compliance (Non Financial), Cost Avoidance (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-09-11 |  | 2023-09-11 | 760490 |  | 2023-09-11 |  | 2028-06-30 | 2026-06-30 | 3436310 | 8470976 | Green | Green | Green | Amber | Red | Revised integrated schedule complete. Delivery activities are now forecast to complete in FY27 following procurement delays with impacts to end-to-end timelines managed through the re-baselined schedule
Q4 25-26 | Greater Western Water Corporation | GW Water | 3864 | Geospatial Capability Uplift (OSO 2030) | Environment and Water | Analyses and Statistics ,Assets/Materials Management,Data Management,Visualisation | The project will enhance geospatial capability through modern standards and technologies to maximise value of spatial information in order to gain new insights for improved asset management capabilities across the organisation. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial) |  | Waterfall | 2023-07-01 | 2024-04-07 |  | 2024-04-07 | 3900000 |  | 2024-04-07 |  | 2028-06-30 |  | 20300000 |  | Green | Green | Green | Green | Green | Change to procurement approach and resource constraints were managed in Q4. FY27 activities have been realigned to the revised implementation approach, and the program continues to focus on release 2 of data remediation and consolidation activities.
Q4 25-26 | Department of Justice and Community Safety | DJCS | 3869 | Replacement DJCS Safety Incident Management System | Community Services | Reporting | Procurement, and implementation of a safety incident management system will streamline how safety incidents are reported and investigated. This system will foster a proactive safety culture where incidents are managed efficiently and effectively. | Postponed |  | 2025-06-30 | Project Management Excellence | 2023-12-19 | 2024-01-31 | 2024-01-04 |  | 0 | [5 empty] | 0 | [6 empty] | Due to resourcing constraints, the project was postponed in June 2025. The project completed the initiation phase in January 2024 and was approved to commence procurement activities for the provision of a safety incident management system. Once resources become available, the project will transition to the delivery phase, commencing with procurement activities. The delay in procurement commencement does not result in any additional risk as the project seeks to deliver a replacement system that enhances functionality and provide efficiencies beyond what the current system offers. The current system is still fully functional and operational.
Q4 25-26 | Holmesglen Institute of TAFE | Holmesglen TAFE | 3870 | Identity Governance and Administration | Employment, Skills and Workplace | Security Management | The IGA project will deliver a new Identity Governance & Administration platform. The new IGA platform will improve staff/student identity governance and security by enabling contemporary features such as attestation and hardened authentication. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-09-14 | 2023-11-15 |  | 2023-12-06 | 0 |  | 2024-03-01 |  | 2025-03-28 | 2026-07-31 | 1205132 |  | Amber | Amber | Amber | Amber | Amber | The project made significant progress during Q4 in clarifying business requirements, confirming the target architecture and evaluating the vendor's revised delivery approach. Focus has now shifted to reaching agreement on a delivery model that provides confidence in successful implementation, clear accountability and appropriate management of project risk. Once contractual arrangements are resolved, the project will be re-baselined and implementation activities will recommence.
Q4 25-26 | South East Water | SE Water | 3879 | Sample Management | Environment and Water | Assets/Materials Management,Management of Process | The project will deliver a sample management system to streamline current processes, modernising the system capability, and enabling improved reporting, faster processes and insights for customer water quality. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2026-06-30 | Waterfall | 2024-04-08 | 2024-08-01 |  | 2024-08-01 | 159445 |  | 2024-09-02 |  | 2025-07-31 | 2026-06-30 | 1937205 |  | Green | Green | Green | Green | Green | Project has now been formally closed.
Q4 25-26 | Northern Health | NH | 3880 | Active Directory Segregation from Melbourne Health | Health | Systems Management | Northern and Melbourne Health are currently sharing the same Active Directory. Segregating from this shared active directory to a more modern version will allow NH to initiate its journey into cloud and enhance cyber security across all campuses | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2022-01-01 | 2022-09-27 |  | 2022-09-27 | 0 |  | 2023-03-09 |  | 2025-09-30 | 2026-10-31 | 3200000 |  | Amber | Green | Green | Green | Green | All Cardiology services have been migrated to the new domain. The focus now shifts to get the new Citrix image ready after some connectivity issues and application rendering complications. The root cause has been identified and the team is working to get a new image ready to continue testing.
Q4 25-26 | WorkSafe Victoria | WorkSafe | 3881 | Medical Panels Capability Uplift | Employment, Skills and Workplace | Tracking and Workflow | Medical Panels technology will migrate to a modern system enabling digital record-keeping, workflow automation, and improved cyber security. This mitigates the risk of end-of-life tech, improves efficiency, and uplifts staff / stakeholder experience. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-03 | 2024-12-05 | 2025-02-24 | 2025-02-24 | 947722 | 758291 | 2025-02-25 | 2025-04-14 | 2025-10-31 | 2026-09-30 | 4999889 | 5491463 | Amber | Red | Amber | Red | Red | Following the system build assessment which identified and quantified key functional gaps and system defects an options analysis is being drafted alongside a change request to determine the preferred pathway for progressing the initiative through governance and achieving Green status.
Q4 25-26 | Melbourne Water | MELB Water | 3882 | Business Process Optimisation 24-26 | Environment and Water | Systems Management | This project aims to optimise business processes and workflows using modern process management tool, improving process efficiency & reducing reliance on manual processes. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-06-13 | 2024-10-25 |  | 2024-11-14 | 0 |  | 2024-11-14 |  | 2026-07-21 |  | 2900000 | 2800000 | Green | Amber | Red | Green | Green | As at 20260630: Change Request approved to separate scope to ensure appropriate governance. Project will be closed in Q1 26/27.
Q4 25-26 | Grampians Rural Health Alliance | GRHA | 3886 | Grampians Health Success Factors Phase 2 | Health | Human Resources | Implementation of SAP SuccessFactors, including Employee Central Payroll, refactoring of Employee Central, Recruitment, Onboarding, and implementation of Performance & Goals. Phase 2 will deliver integration with rostering, finance and IT systems. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-13 | 2023-12-15 |  | 2023-12-15 | 0 |  | 2024-08-14 |  | 2025-09-26 | 2026-09-25 | 2905553 |  | Green | Green | Green | Green | Green | From the 3rd November 2025 Employee Central Payroll Employee Central Time off and the upgrades to our existing modules of Employee Central (including concurrent employment) Recruitment and onboarding are now live. This includes integrations to our rostering system Optima. 19 full fortnightly pay processes have been completed successfully in the new system as well multiple offline cycles. There are 2 outstanding items that remain to be finalised with those being the integration with Epicor and Fit2Work. These are due to be finalised by the end of September 2026.
Q4 25-26 | Department of Government Services | DGS | 3889 | Common Corporate Platform (CCP) - VicGov People - DGS/DPC/DTF Cluster | Government and Economy | Human Capital / Workforce Management | Onboarding the Departments of Government Services, Premier and Cabinet, and Treasury and Finance on a common human capital management platform (VicGov People) to drive efficiency and productivity, enhancing employee experience and corporate services | Closed - Completed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) | 2026-05-29 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-04 | 2024-06-28 | 2024-06-01 | 2024-06-25 | 0 |  | 2024-07-01 | 2024-07-01 | 2026-06-30 | 2026-03-27 | 25000000 |  | Amber | Amber | Amber | Green | Green | The project has implemented on schedule and is complete.
Q4 25-26 | Yarra Valley Water | YV Water | 3891 | Altus PPM Tool Implementation | Environment and Water | Investment Management | Implementation of a PPM tool to centralise visibility of up-to-date program information, support consistency in the way projects get delivered, and provide insights on demand. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-08-01 | 2024-08-15 |  | 2024-08-26 | 421280 |  | 2024-09-02 |  | 2026-06-10 | 2026-08-31 | 2947600 | 3289573 | Amber | Amber | Amber | Amber | Green | Change request to extend schedule and increase costs has been approved. Project is in Hypercare and progressing towards closure
Q4 25-26 | Fire Rescue Victoria | FRV | 3893 | Asset Sustainment | Emergencies and Safety | Assets/Materials Management | This project aims to procure ICT equipment to replace components at end-of-life. This includes equipment such as network equipment and fire station switches and will ensure a safe ICT environment and ensure ongoing reliability. | Closed - Completed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2026-06-30 | FRV Project Management Framework (PMF) | 2020-07-01 | 2020-10-05 |  | 2020-10-05 | 0 |  | 2022-02-14 |  | 2024-12-31 | 2026-06-30 | 7069087 | 6967773 | Green | Green | Green | Green | Green | As at 30 June 2026, the project was completed and closed, having delivered its intended scope. This included procuring ICT equipment to replace end-of-life components, improving the safety and reliability of the ICT environment.
Q4 25-26 | Department of Education | DE | 3896 | Kindergarten Attendance Program | Education | Analyses and Statistics ,Business Intelligence,Data Management | Delivery of a digital solution to collect kindergarten attendance data to improve child outcomes and to report on performance indicators as required by the Commonwealth Preschool Reform Agreement. | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Increased Revenue (Financial) | 2026-06-30 | Agile | 2023-02-01 | 2023-07-31 |  | 2023-08-01 | 0 |  | 2023-08-01 |  | 2026-06-30 |  | 20965000 |  | Green | Green | Green | Green | Green | The project is GREEN with technical delivery completed and additional work to enable and sustain the solution within remaining budget progressing to plan.
Q4 25-26 | Department of Health | DH | 3899 | Health Technology Services Application Cloud Migration | Health | Data Management,Development and Integration | Migrate three Health Technology Services applications to the department’s ICT Cloud environments, namely Finance and Material Information System, Client Management System and HealthCollect, to improve data availability, security and reliability. | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2026-06-30 | PRINCE2 | 2024-05-01 | 2024-05-31 |  | 2024-05-31 | 0 |  | 2024-06-03 |  | 2025-06-30 | 2026-06-30 | 2715200 | 3091807 | Amber | Amber | Red | Amber | Green | Project successfully delivered in May and June as scheduled, with project closure finalised on 30 June 2026.
Q4 25-26 | Westernport Region Water Corporation | WPR Water | 3906 | Asset Management Information System Replacement | Environment and Water | Assets/Materials Management | The project will replace legacy asset management and work order management systems improving functionality and flexibility to enable more accurate, accessible and comprehensive information for decision-making. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-09-03 | 2025-06-30 | 2025-04-14 | 2025-04-14 | 200000 | 254000 | 2025-04-14 |  | 2026-10-30 |  | 1440000 |  | Green | Green | Green | Green | Green | Project remains on-track and on-budget. Go-live milestones for Phase 1A - Asset Register and Phase 1C - Asset Capitalisation have been met. Phase 1B - Works Management remains.
Q4 25-26 | Peninsula Care Group – Bayside Health | PEN Care Group | 3907 | Peninsula Health Project Phoenix (MePACS Refresh) | Health | Customer Relationship Management | A technology refresh of the core MePACS systems with a modern Customer Relationship Management System (CRM) to secure the ongoing viability of the MePACS business. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-06-03 | 2024-10-31 |  | 2024-10-31 | 340000 |  | 2024-11-04 |  | 2025-10-31 | 2026-10-30 | 2620000 | 3063676 | Green | Green | Green | Green | Amber | The application was deployed to production and subsequently rolled back following operational issues experienced during the go-live period. A post-implementation review was conducted which identified a range of remediation requirements. Resulting approved scope refinements together with the associated budget and schedule updates..
Q4 25-26 | Monash Health | Monash H | 3912 | Maternity Digital Transformation Project | Health | Management of Process | The project will implement EMR and breast milk management module onto a single EMR platform, supporting a single view of the patient's medical record, improving clinical outcomes for both mother and baby. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-10-31 | 2024-04-04 | 2024-04-04 | 0 | 0 | 2024-11-01 |  | 2026-05-27 | 2026-11-27 | 11522379 | 14563212 | Green | Green | Red | Red | Green | The project is on track, with budget approval confirmed for the planned November go-live. Design and build activities are largely complete, and the project is progressing to the testing phase as scheduled. Technical implementation activities are also underway and tracking to plan.
Q4 25-26 | Barwon Region Water Corporation | BR Water | 3915 | C1062 - Works and Asset Management | Environment and Water | Assets/Materials Management | Improve strategic and operational asset management and service delivery through the implementation of Maximo Works Management providing benefits such as, a more financially sustainable business and keeping bills affordable for all. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-01 | 2025-03-31 | 2025-07-01 | 2025-07-01 | 824310 | 2162000 | 2025-07-01 |  | 2026-12-31 | 2027-04-30 | 10208000 |  |  | Green | Amber | Amber | Amber | The program successfully cutover the Barwon Asset Solutions (BAS) Land Management team IBM Maximo work order management including integration to the Finance system for financial management and journaling of work order labour costs. Phase 2 of the program for Barwon Operations BAS Mechanical and Electrical Maintenance teams Purchasing and Inventory Management is nearing completion to commence system interface testing in Q4. Replanning completed during Q3 established new design processes and governance restructured the program into four agile delivery squads and executed a revised statement of work with the system integrator partner to provide great flexibility to Barwon Water.
Q4 25-26 | Department of Families, Fairness and Housing | DFFH | 3917 | Public Housing Maintenance Modernisation Technology Enablement Program | Community Services | Development and Integration | Uplift digital capability of Homes Victoria systems including new housing maintenance portal, improvements to HiiP system, and integration capability with Contractor Work Systems, providing greater process efficiencies and ease of use by tenants. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-10-01 | 2024-10-11 |  | 2024-10-11 | 1214790 |  | 2024-10-11 |  | 2026-06-30 | 2027-06-30 | 23066733 | 35650210 | Red | Red | Amber | Amber | Green | Program progressing to cost and schedule.
Q4 25-26 | South East Water | SE Water | 3924 | Information Management Strategy Delivery | Environment and Water | Business Intelligence,Data Management,Reporting | Program of work delivering multiple initiatives that is delivering on the Information Strategy including - Enterprise Content Management Data & Information Management Analytics & Reporting. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-06-01 | 2023-06-30 |  | 2023-09-26 | 0 |  | 2023-09-26 |  | 2025-07-31 | 2026-07-31 | 1859425 |  | Amber | Green | Green | Green | Green | The project is currently tracking GREEN with deliverables all on track as per baselined schedule.
Q4 25-26 | South East Water | SE Water | 3925 | Lentic Performance Enhancements | Environment and Water | Communication | Optimization of IoT platform to ensure scalability and optimal performance within the boundaries of the current architecture. This will ensure the IoT platform will support the mass roll out of digital meters across SEW network. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2024-03-01 | 2024-04-18 |  | 2024-06-05 | 0 |  | 2024-08-01 |  | 2025-12-31 | 2026-09-30 | 1161000 |  | Amber | Green | Green | Green | Green | Project had returned to GREEN. Phase 2 implementation successfully implemented in FY26 Q2. Work has commenced on Phase 3 and deliverables are on track to be delivered in Q1 of FY27.
Q4 25-26 | Gippsland Health Alliance | GHA | 3928 | Payroll and Talent Modernisation (HRIS) | Health | Human Capital / Workforce Management | The project involves implementing a single instance of SAP SuccessFactors across eleven agencies in Gippsland. This initiative aims to modernise processes and systems, enhancing efficiency and collaboration among the agencies. | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2022-02-18 | 2022-05-20 |  | 2023-02-17 | 180000 |  | 2023-04-10 |  | 2025-06-27 | 2026-07-31 | 1600000 | 2200000 | Amber | Green | Green | Green | Green | Completed second phase of roll out to complete all agencies in the Gippsland Health Alliance network. Focus on closure of the project and transition to operations.
Q4 25-26 | Transport Accident Commission | TAC | 3931 | Strategic Analytics Program Phase 2 | Transport and Vehicles | Business Intelligence | Build capability for both analysts & the broader enterprise in working optimally to deliver use cases from a prioritised backlog that will result in well managed & trusted data, improved customer & workforce satisfaction, platform efficiencies. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-07-01 |  | 2024-07-01 | 0 |  | 2024-07-01 |  | 2026-06-30 | 2026-12-31 | 11000000 |  | Green | Green | Green | Green | Green | With the approved Change Request now in effect, the program successfully delivered all planned Q4 FY25/26 milestones and deliverables. Delivery teams are currently working with stakeholders to review, refine, and prioritise the FY27 roadmap and delivery plans. These plans will be progressed through the formal governance and approval process during Q1 FY27.
Q4 25-26 | Melbourne Water | MELB Water | 3932 | Cyber Defence Initiatives | Environment and Water | Security Management | Redesign the existing SOC capability in line with the new Security Operations Operating Model. Deliver a better asset discovery and inventory capability, providing cyber control coverage assurance to the organisation. | Closed - Completed | Risk Reduction (Non Financial) | 2026-06-10 | PMBoK | 2024-07-26 | 2025-02-20 | 2025-07-07 | 2025-07-07 | 0 |  | 2025-07-07 |  | 2026-06-10 |  | 4868275 | 4578100 |  | Green | Green | Green | Green | As at 20260630: Project is complete.
Q4 25-26 | WorkSafe Victoria | WorkSafe | 3933 | Strategic Integration Platform | Employment, Skills and Workplace | Systems Management | Integration technology connects systems and data across platforms. This project will move existing integrations to the Strategic Integration Platform a modern cloud-based solution that reduces failures and speeds recovery benefitting all users. | Closed - Completed | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) | 2026-06-30 | Agile | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 0 |  | 2024-07-01 |  | 2025-06-30 | 2026-06-30 | 4597071 | 11384164 | Red | Green | Green | Amber | Green | Project has delivered all integrations as planned and is now closed
Q4 25-26 | Independent Broad-based Anti-corruption Commission | IBAC | 3941 | Case Management System Enhancement Project | Government and Economy | Business Intelligence,Collaboration | This project is to deliver enhancements to IBAC's case management system and improvements to data maturity in the form of analytics, reporting and dashboard outputs. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2026-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-03 | 2024-12-31 | 2025-01-31 | 2025-01-31 | 0 | 270000 | 2025-02-01 |  | 2026-06-30 |  | 2443584 | 1984500 | Amber | Amber | Green | Amber | Green | The CMS Enhancement Project successfully delivered the agreed scope across Phases 1, 2 and 3, including enhancements and configuration changes within Condor. Major project milestones and planned phase deliveries were completed broadly in line with agreed timelines and within budget. Project has closed and further support and roll-out activities transitioned to business-as-usual.
Q4 25-26 | Yarra Valley Water | YV Water | 3943 | Digital Meter Integrated Software Solution (HES/MDMS) | Environment and Water | Analyses and Statistics ,Assets/Materials Management,Knowledge Discovery ,Tracking and Workflow,Visualisation | Implementation of an integrated software solution for an Internet of Things Head End System (IoT HES) and Meter Data Management System (MDMS) to enable YVW’s digital water metering and IoT strategy which plans to deploy around one million digital met | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2022-08-01 | 2023-12-31 |  | 2024-01-09 | 1062000 |  | 2024-01-10 |  | 2025-06-30 | 2026-12-31 | 6678000 |  | Green | Green | Green | Green | Green | The project is tracking well against scope and budget, with a minor schedule delay to last milestone due to business reprioritisation. The software platform is live with over 74k meters deployed with enhanced features to identify customer leaks.
Q4 25-26 | Yarra Valley Water | YV Water | 3945 | WorksPortal System and Asset Creation Replacement | Environment and Water | Customer Relationship Management | The current WorksPortal System is reaching end of life with support expiring by July 2026. As the system relates to asset creation and revenue, a replacement is required. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-07-01 | 2025-03-31 | 2025-05-31 | 2025-06-19 | 650000 | 736000 | 2025-06-19 |  | 2026-04-30 | 2026-09-30 | 3936260 | 6549380 | Green | Green | Amber | Amber | Green | A change request extending the schedule and budget was approved during the quarter. Due to the complexity of the solution these continue to be closely monitored.
Q4 25-26 | Yarra Valley Water | YV Water | 3946 | Land Development System (easyACCESS) Replacement | Environment and Water | Customer Relationship Management | Full replacement of the current easyACCESS Land Development portal with a Salesforce solution, before the portal reaches end of life | Initiated |  |  | Agile | 2024-07-01 | 2025-06-30 | 2027-01-31 |  | 1772100 | 9074400 | [11 empty] | The Portfolio Control Board endorsed a dedicated Planning and Solution Design stage to reduce risk before full delivery commitment. YVW is progressing this work with our vendor, addressing the complexity of this highly integrated system. Early outcomes are encouraging with new innovative solutions being identified.
Q4 25-26 | Melbourne Water | MELB Water | 3948 | End User Computing Lifecycle Renewal FY24-26 | Environment and Water | Assets/Materials Management | Staff have been provided devices including laptops, tablets, heat sets and mobile phones to perform their tasks. These devices need to be regularly updated to ensure suitable performance and enabling the use of modern applications. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-09-30 | 2025-02-06 | 2026-05-01 | 2026-05-01 | 0 | 0 | 2026-05-01 |  | 2026-07-31 |  | 3381353 | [5 empty] | Green | As at 20260630: Business case approved, project on track.
Q4 25-26 | Melbourne Water | MELB Water | 3949 | Identity and Access Management Initiatives | Environment and Water | Security Management | Process uplift, technology build and onboarding to the current identity access platform. | Closed - Completed | Risk Reduction (Non Financial) | 2026-06-30 | PMBoK | 2024-07-26 | 2025-05-21 | 2024-12-11 | 2024-12-11 | 0 |  | 2024-12-11 |  | 2026-06-30 |  | 4807000 | 4205076 | Red | Green | Green | Green | Green | As at 20260630: Project is complete.
Q4 25-26 | Melbourne Water | MELB Water | 3952 | Privilege Access Management Initiatives | Environment and Water | Systems Management | This project aims to implement a comprehensive Privileged Access Management (PAM) system to enhance security by onboarding critical accounts across network and operational technology environments. The investment supports robust identity governance. | Closed - Completed | Risk Reduction (Non Financial) | 2026-06-30 | PMBoK | 2024-07-26 | 2025-03-21 | 2024-12-12 | 2024-12-12 | 0 |  | 2024-12-12 |  | 2026-06-30 |  | 2290000 | 1970170 | Red | Green | Green | Green | Green | As at 20260630: Project is complete.
Q4 25-26 | Department of Transport and Planning | DTP | 3953 | OneDigital Workplace | Transport and Vehicles | Customer Preferences,Development and Integration ,Organisational Management ,Security Management ,Systems Management | Delivering a new Standard Operating Environment and operating model for the DTP so that all users can access a modern and consistent desktop environment. Includes rationalisation of ITSM tools (ServiceNow). | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2026-06-30 | 2025-02-28 | 2025-02-28 | 10000000 | 0 | 2025-03-03 |  | 2026-06-30 | 2026-12-30 | 10000000 | 11001234 | Green | Green | Green | Green | Red | The overall program status is reporting as red due to solution implementation issues resulting in pressure on schedule, resources, and dependencies.
Q4 25-26 | Melbourne Water | MELB Water | 3954 | Standalone Server Refresh | Environment and Water | Assets/Materials Management | Standalone servers at or approaching end of life &/or end of support require upgrading to meet ongoing operational requirements. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-08-09 | 2024-10-30 |  | 2024-11-13 | 0 |  | 2024-11-13 |  | 2026-03-12 | 2026-10-30 | 1992000 |  | Green | Green | Green | Amber | Amber | As at 20260630: Hardware scope analysis complete with decision to run as a separate initiative more closely aligned with business objectives. Schedule delays due to in-scope hardware delivery lead times.
Q4 25-26 | Melbourne & Olympic Parks | M&OP | 3955 | End of Life Switch Replacement 2024/25 | Culture, Sport and Recreation | Systems Management | The project will replace end-of-life hardware to maintain support for the network switch environment, enabling the organisation to minimise legacy system risks and improve security. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2024-05-01 | 2024-07-01 |  | 2024-07-01 | 0 |  | 2024-07-15 |  | 2025-06-30 | 2026-11-30 | 2750000 |  | Amber | Amber | Amber | Amber | Amber | A delivery integrator has been appointed and Phase 2 planning is underway. Supply orders are being finalised, with delivery timeframes to be confirmed once orders are placed and accepted due to ongoing global supply chain risks. The project will remain Amber until delivery commitments are confirmed and implementation planning is validated against the Melbourne Park event schedule, after which it is expected to return to Green.
Q4 25-26 | Department of Education | DE | 3956 | Brief Connect | Education | Content Management,Data Management,Document Management ,Management of Process ,Reporting ,Tracking and Workflow | The project will deliver a workflow solution for managing all departmental briefings and correspondence. This solution will enhance the depts digital capabilities by utilising existing Cloud Service. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial) | 2026-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-12 | 2023-07-04 |  | 2023-09-05 | 0 |  | 2024-07-29 |  | 2025-03-07 | 2026-03-31 | 2657628 | 3757628 | Green | Green | Amber | Green | Green | The project was successfully implemented on 30 March 2026. Delivery was completed within the revised schedule and budget. The Project completed hyper-care April 2026 and has successfully transitioned to business-as-usual support activities.
Q4 25-26 | Department of Education | DE | 3961 | Securing Connected Learners (SCL) Program – Phase 2 | Education | Development and Integration ,Security Management ,Systems Management | Securing Connected Learners a high profile program of work creating enhanced security capabilities for schools, initially addressing child safety & security risks in schools by transitioning schools to platforms with enhanced cyber security features | Closed - Completed | Cost Avoidance (Financial), Risk Reduction (Non Financial) | 2026-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-01 | 2024-06-03 |  | 2024-06-03 | 0 |  | 2024-06-03 |  | 2025-06-30 | 2026-06-30 | 3100000 | 7574805 | Amber | Amber | Amber | Amber | Green | The Asset Discovery Tool was successfully deployed to 1,520 schools by 30 June 2026, exceeding the original scope. It was completed within the revised schedule. Project closure activities are in progress. The deployment of the Asset Discovery Tool to an additional 84 "complex schools" will be addressed in business as usual activities.
Q4 25-26 | Alfred Care Group – Bayside Health | ALFRED Care Group | 3968 | Disaster Recovery | Health | Security Management | The Disaster Recovery project will enhance ICT infrastructure for disaster recovery, prioritizing patient safety and data integrity by establishing a robust, adaptable ICT environment that maintains continuous operations during disruptions. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-10-21 |  | 2024-10-21 | 148217 | 69382 | 2024-10-28 |  | 2026-07-01 | 2026-08-31 | 1171783 | 1250618 | Green | Green | Green | Green | Green | The project is on track.
Q4 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3977 | Energy Customer Relationship Management (CRM) Project | Government and Economy | Customer Relationship Management | The Energy CRM Project will deliver a customer management system to enable DEECA's Energy Group to deliver best practice stakeholder engagement and more efficient government processes. | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) | 2026-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-04 | 2024-12-11 |  | 2024-12-11 | 150000 |  | 2024-12-12 |  | 2025-06-30 | 2026-06-30 | 1277120 | 1250822 | Green | Green | Green | Green | Green | The project successfully delivered the approved scope budget and schedule.
Q4 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3980 | FireWeb Decommissioning Project | Emergencies and Safety | Management of Process | The FireWeb Decommissioning Project will replace the legacy system FireWeb to improve the accessibility of the information. This infrastructure will be DEECA's primary source for Fire Management. | Closed - Completed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2026-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-01 | 2024-06-30 |  | 2024-06-30 | 0 |  | 2024-07-01 |  | 2028-06-30 | 2026-06-30 | 5047000 | 5800000 | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q4 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3981 | Emergency Management (EM) Deployment Project | Emergencies and Safety | Management of Process | The EM Deployment project will deliver a modern system to plan and coordinate the commitments and resources for bushfire and other emergency incidents to increase DEECA's capabilities to manage these incidents effectively and in a timely manner. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-01 | 2024-06-30 |  | 2024-06-30 | 0 |  | 2024-07-01 |  | 2026-12-31 | 2026-12-31 | 1223000 |  | Green | Green | Green | Green | Green | The project is on track for scope, budget and schedule.
Q4 25-26 | Peninsula Care Group – Bayside Health | PEN Care Group | 3985 | Peninsula Health Replacement of legacy Citrix virtual desktop environment & virtual server infrastructure | Health | Systems Management | Replacement of legacy Virtual Desktop and Converged Infrastructure at Frankston Hospital providing clinical application access to all sites, increasing usability and access for all staff to applications and data, including Video conference/telehealth | Closed - Completed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2026-05-15 | PRINCE2 | 2024-03-04 | 2024-10-18 |  | 2024-10-18 | 10000 |  | 2024-10-18 | 2024-10-21 | 2026-02-27 | 2026-05-29 | 7329269 | 7982065 | Green | Green | Green | Green | Green | Project is now completed.
Q4 25-26 | Department of Health | DH | 3987 | Donor Conception Register IT System | Health | Customer Relationship Management | Deliver a new IT system to manage Victoria's donor conception registers and allow applicants (donors, donor-conceived persons', parents, and their families) to request information under the legislation. | Postponed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial) | 2024-09-01 | Agile | 2024-01-15 | 2024-03-26 |  | 2024-03-26 | 7800 |  | 2024-04-01 |  | 2025-06-30 |  | 1522446 |  | Red | Red | Red | Red | Red | Major components of the system were delivered and the project remains on hold. Delivery will progress once the revised scope and remaining funding are confirmed.
Q4 25-26 | South East Water | SE Water | 3989 | CRUX - Stabilisation | Environment and Water | Financial Management | Uplift of ERP solution implemented in 2023. Including Finance Procurement & Project Management functions. | Delivery | Cost Reduction (Financial) |  | Waterfall | 2024-07-01 | 2024-12-20 |  | 2024-12-20 | 0 |  | 2025-01-27 |  | 2026-01-30 | 2026-07-31 | 3510000 | 3990000 | Green | Amber | Amber | Amber | Green | All major project deliverables have been completed and deployed into production ERP environment. Operational handover activities have incurred minor delay from vendor and will be completed in July.
Q4 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3991 | Victorian Water Register (VWR) Evolve Project | Environment and Water | Development and Integration | The VWR Evolve Project will uplift the Victorian Water Register to a supported platform to improve the integrity security and reliability of Victoria's water market and enable future improvements in service delivery and information sharing. | Initiated |  |  | PRINCE2 | 2024-07-01 | 2025-05-31 | 2026-08-31 |  | 4233990 | [12 empty] | Procurement was initiated in the September 2025 quarter and progressed in the June 2026 quarter to secure a suitable Implementation Partner to support project execution. The Initiation End Date has been revised to end of August 2026 in order to take further de-risking activities through the procurement phase. The project business case was approved in 2024-25. Prior to undertaking procurement phase, a proof of concept was successfully completed.
Q4 25-26 | Melbourne Water | MELB Water | 3992 | Routine Telecommunications Upgrades FY24-26 | Environment and Water | Assets/Materials Management | Upgrade and replacement of degrading IT network cabling and devices - including microwave dishes 4G boosters WAPs and GWIP services. | Closed - Completed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2026-06-30 | PMBoK | 2024-10-04 | 2025-02-13 | 2026-01-29 | 2026-01-29 | 0 |  | 2026-01-29 |  | 2026-07-02 |  | 2253368 |  |  |  |  | Green | Green | As at 20260630: Project is complete.
Q4 25-26 | Eastern Health | EH | 3994 | Eastern Health EMR and Digitisation in the home | Health | Development and Integration | This project implements the EMR workflows across Care@Home services at Eastern Health alongside new integrated electronic logistics and fleet management applications to improve the coordination and delivery of care outside the hospital walls. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-28 | 2023-06-28 |  | 2023-06-28 | 420139 |  | 2024-12-06 |  | 2025-08-31 | 2026-09-30 | 4832935 |  | Amber | Amber | Green | Amber | Green | During the period the EDITH project progressed both its Logistics Management and AutoML streams. Logistics Management completed planning training testing and user acceptance activities for Phase 2 culminating in the June go-live. The AutoML stream finalised requirements commenced data extraction and model development for predictive analytics reporting and pilot development
Q4 25-26 | Eastern Health | EH | 3996 | Eastern Health EMR Mobility and Enterprise Extension (Acute) | Health | Development and Integration | The EMR Mobility and Extension (Acute) Program aims to expand EMR footprint at Angliss and Maroondah Hospitals, simplify clinician workflows and patient information access, and implement EMR Mobility solutions while decommissioning legacy systems. | Closed - Completed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2026-05-29 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-01 | 2025-02-28 |  | 2025-02-28 | 0 |  | 2025-03-01 |  | 2025-12-15 | 2026-04-10 | 9979000 |  | Green | Amber | Green | Green | Green | The EMR Mobility and Enterprise Extension changes have successfully gone live across Eastern Health Acute sites. The final Eastern Health acute site Angliss Hospital has gone live on the 10th March 2026 and successfully exited from Hypercare. Handover to operational support teams is complete with continued efforts to work with the vendors to provide a resolution for outstanding warranty items.
Q4 25-26 | Eastern Health | EH | 4000 | Advancing Cancer Services through Digital Chemotherapy Project | Health | Development and Integration | This project implements the EMR Oncology modules to all Eastern Health sites where Cancer Services are delivered providing electronic cancer medication prescription and management for more safe and timely care. | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-11-01 | 2025-02-28 |  | 2025-02-28 | 0 | 511021 | 2025-03-31 |  | 2026-05-31 | 2026-08-31 | 3438979 |  | Green | Green | Amber | Amber | Green | The project continues to track well on the revised timeline with all activities on schedule to go live in August 2026.
Q4 25-26 | WorkSafe Victoria | WorkSafe | 4003 | Return to Work Product Pipeline Implementation | Employment, Skills and Workplace | Analyses and Statistics ,Business Intelligence,Data Management | Deployment of a production-grade Return to Work (RTW) Dashboard Product to business users including operational support processes user training and change management. As well as automated ingestion of Australian Bureau of Statistics data. | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2026-04-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-23 | 2024-10-31 |  | 2024-10-31 | 60290 |  | 2025-01-02 |  | 2025-12-31 | 2026-04-30 | 1318806 | 1479682 | Green | Amber | Red | Red | Amber | Project approved for early closure in Q4 as completion of full scope would require significant increase to budget.
Q4 25-26 | Department of Health | DH | 4005 | Enterprise Operational Workforce Management System | Community Services | Human Capital / Workforce Management | Replace end-of-life Rostering, Time and Attendance systems for disability residential services, child protection, emergency response and maternal child health divisions across DFFH and DH to enhance workforce management and improve service delivery. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2023-12-14 | 2024-09-30 |  | 2024-09-30 | 239974 |  | 2024-10-01 |  | 2026-06-30 |  | 3518876 | 3519676 | Green | Green | Green | Green | Amber | Project is Amber due to system and process issues identified during testing. Project will be extended. Impact to schedule is being assessed and will be updated in the next reporting period.
Q4 25-26 | CenITex | CenITex | 4009 | DC Exit Network Establishment – Phase 2 | Government and Economy | Assets/Materials Management | To establish a network extension from Burwood to Equinix ME2 using VicTrack colocation service at Equinix and then execute the base network infrastructure required at the data centre to start migrating Cenitex workloads out of Burwood to Equinix. | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2024-11-01 | 2024-11-30 |  | 2024-11-30 | 0 |  | 2024-12-01 |  | 2025-10-30 | 2026-10-30 | 1993326 | 3436585 | Green | Green | Green | Green | Amber | Additional requirements have been discovered following the define phase. The project is reviewing the impact of these requirements to inform next phases of the project.
Q4 25-26 | Goulburn Valley Region Water Corporation | GVR Water | 4011 | SCADA System Replacement | Environment and Water | Assets/Materials Management,Communication,Data Management,Systems Management | Replacement of the Supervisory Control and Data Acquisition (SCADA) System to ensure GVW's core operational monitoring and automation system remains fit for purpose and reduce business continuity risk. | Initiated |  |  | PMBoK | 2023-05-01 | 2025-04-30 | 2026-07-31 |  | 200000 | 1183262 | [11 empty] | GVW is finalising procurement for this project and is in the process of awarding the contracts for: System Integrator; Hardware, radio and RTU; and Software Licensing. Implementation is on track to commence by August 2026.
Q4 25-26 | Hume Rural Health Alliance | HRHA | 4012 | Hume Regional EMR Preparation Project | Health | Customer Relationship Management,Records Management | The project will develop and deliver a series of business readiness activities prior to the full implementation of a whole of Hume Rural Health Alliance Electronic Medical Record (EMR), ensuring all IT environments are ready for the roll-out | Delivery | Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-13 | 2025-12-31 | 2025-03-31 | 2025-04-30 | 0 | 200000 | 2025-05-01 |  | 2026-06-30 |  | 4200000 |  | Green | Green | Green | Green | Green | Assessment of electronic medical record (EMR) solutions against regional requirements has been completed. The technical deliverables to support EMR readiness are being finalised, as well as the identification of other supporting digital health initiatives.
Q4 25-26 | Peninsula Care Group – Bayside Health | PEN Care Group | 4046 | Patient Flow Management Solution | Health | Organisational Management | Electronic Patient Flow Management streamlines patient movement, enhances collaboration, optimises access and demand management, reduces length of stay, improves communication, and increases workplace satisfaction and providing bed visibility. | Closed - Completed | Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) | 2026-05-29 | PRINCE2 | 2023-09-08 | 2024-06-10 |  | 2024-08-07 | 50000 |  | 2024-12-20 |  | 2026-01-29 | 2026-04-30 | 2440404 |  | Green | Green | Green | Green | Green | The application went live on 29 April and a coordinated Hypercare period was undertaken from go-live through to 13 May with official closure 29 May.
Q4 25-26 | Victorian Legal Services Board & Commissioner | VLSBC | 4049 | Regulatory Management System | Law and Justice | Customer Relationship Management | A Regulatory Management System will be delivered. Replacement of legacy systems will improve delivery of service and modernisation of legal regulatory systems will support legal regulation in Victoria. | Postponed | Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2025-02-25 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-11-10 | 2023-08-22 |  | 2023-08-22 | 330680 |  | 2023-11-27 |  | 2026-05-01 |  | 18400000 |  | Amber | Amber | Amber | Amber | Amber | Project delivery remains postponed. The Proof of Concept (PoC) to assess vendor capability and ways of working has concluded with the final selection of preferred delivery partner underway. Revised delivery dates and budget and subject to confirmation with the preferred delivery partner once selected.
Q4 25-26 | Liquor Control Victoria | LCV | 4050 | Liquor Control Victoria ICT relocation and support for hardware and software | Law and Justice | Systems Management | The project will relocate on-premises servers to Richmond, decommission legacy hardware, and improve software and hardware support to enable business continuity | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-04-01 | 2024-12-01 | 2025-03-31 | 2025-03-31 | 0 |  | 2025-06-27 |  | 2026-01-31 | 2026-08-31 | 4373050 |  | Green | Green | Green | Green | Green | The transition of systems and support from Victorian Gambling and Casino Control Commission (VGCCC) to LCV is complete. There is one remaining ICT contract to be novated with an expected completion date of 31 August 2026.
Q4 25-26 | Liquor Control Victoria | LCV | 4051 | New liquor platform for Liquor Control Victoria (delivered by Service Victoria) | Law and Justice | Customer Initiated Assistance | The project will deliver online licence application forms and a digital proof of age card. Efficiency and data quality will be enhanced, resulting in an improved user experience. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2022-07-01 |  | 2022-07-01 | 0 |  | 2022-10-01 | 2023-06-01 | 2026-06-30 | 2027-06-30 | 4580000 | 6835000 | Green | Green | Green | Green | Green | Ten digital application forms are live on the Service Victoria website. An internal delivery partner is planning to launch a new digital proof of age card by the end of FY2026-27. The Revised Delivery End Date has been revised to accommodate this.
Q4 25-26 | South West Alliance of Rural Health | SWARH | 4053 | PACS Replacement | Health | Systems Management | Raplace the existing medial imaging Picture Archiving Communication System (PACS) used by Barwon Health Medical Imaging services. The current system is old and now unsupported with no capacity to upgrade to a new version. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2026-06-30 | Waterfall | 2024-09-01 | 2025-01-16 |  | 2025-01-16 | 5000 |  | 2025-02-01 |  | 2025-10-30 | 2026-04-30 | 2295508 |  | Green | Red | Red | Green | Green | The Project was delivered successfully and is now closed
Q4 25-26 | Department of Jobs, Skills, Industry and Regions | DJSIR | 4055 | TAFE Customer Relationship Management (CRM) tool phase 2 | Education | Customer Relationship Management | The Office of TAFE Coordination and Delivery and the TAFE Network work to improve student experiences and industry outcomes. This phase launches a modern CRM to streamline enrolments at two TAFEs and boost industry engagement across six. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-17 | 2024-11-30 |  | 2025-02-19 | 1 |  | 2025-03-24 |  | 2025-11-30 | 2026-08-28 | 4718530 | 5000000 | Green | Amber | Amber | Amber | Green | The project resumed on 29 April and continues to progress strongly with all core Salesforce development QA testing and SIT now completed. The immediate focus for the program is to complete UAT and establish final PROD environment and the final integration checks, undertake production deployment dependency analysis and prepare for technical deployment training and business readiness activities.
Q4 25-26 | Department of Transport and Planning | DTP | 4056 | Two-way radio | Transport and Vehicles | Communication | The project will leverage the state emergency radio network to implement two-way radio communication system, enabling enhanced safety of roadside operations through real-time location monitoring, duress alarm capability, and broader coverage. | Closed - Completed | Increased Quality (Non Financial) | 2026-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-01-01 | 2024-12-31 |  | 2025-01-06 | 0 |  | 2025-01-13 |  | 2025-12-01 | 2026-06-05 | 1507000 | 1663000 | Green | Green | Green | Green | Green | Project delivery activities are now completed.
Q4 25-26 | Department of Transport and Planning | DTP | 4058 | Transport Victoria website Release 2 and Release 3 | Transport and Vehicles | Development and Integration | The project will consolidate existing digital channels, delivering an enhanced customer experience that integrates all modes of transport, and enables longer term operational efficiencies by simplifying the underlying technical infrastructure. | Closed - Completed | Customer Satisfaction (Non Financial) | 2026-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-08-01 | 2025-01-06 |  | 2025-01-06 | 0 |  | 2025-01-13 |  | 2026-06-30 |  | 8119044 |  | Amber | Amber | Green | Green | Green | Project delivery activities are now completed.
Q4 25-26 | Department of Transport and Planning | DTP | 4059 | Pay Portal for Public Transport Ticketing (PTT) | Transport and Vehicles | Development and Integration | The project will roll out a digital pay portal, enabling commuters to interact with the new public transport ticketing (PTT) system, providing faster and easier ticketing transactions for Victorian commuters. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-12-02 | 2025-02-28 |  | 2025-03-03 | 0 |  | 2025-03-03 |  | 2027-05-13 | 2027-06-30 | 16700000 |  | Amber | Amber | Green | Green | Green | The project is reporting as green and is tracking well with its budget, scope, and key milestones.
Q4 25-26 | WorkSafe Victoria | WorkSafe | 4062 | Claims Systems Modernisation Initiative - Phase 1 | Employment, Skills and Workplace | Customer Relationship Management | The project will deliver a new claim management solution based on the already established CRM platform uplifting both usability & functionality to improve claims management. Phase 1 will roll out the functionality to WorkSafe's internal claims team. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-02-24 | 2025-02-24 |  | 2025-02-24 | 0 |  | 2025-02-25 |  | 2025-12-31 | 2027-06-30 | 36083436 | 69493807 | Amber | Red | Amber | Red | Green | Project back to Green since the approval of change request in April 2026 and project re-baselined its schedule and tracking to plan.
Q4 25-26 | South East Water | SE Water | 4065 | Enterprise Telephony Uplift | Environment and Water | Communication | Replacement and uplift of SEW's enterprise telephony solution across the organisation. | Closed - Completed | Cost Reduction (Financial), Increased Quality (Non Financial) | 2026-06-01 | Waterfall | 2025-01-06 | 2025-02-28 |  | 2025-03-03 | 0 |  | 2025-03-03 |  | 2025-11-30 | 2026-05-29 | 1220000 |  | Green | Green | Green | Green | Green | All core project deliverables have been completed and project successfully closed in FY26 Q4.
Q4 25-26 | CenITex | CenITex | 4066 | Software Defined Datacentre (SDDC) Migration | Government and Economy | Assets/Materials Management | To design configure and consume an alternate VMWare based Private Cloud platform, and migrate Cenitex and customer applications from the current platform to the Multicloud solutions including a new IaaS Platform with built-in backup capability. | Closed - Completed | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Revenue (Financial) | 2026-06-30 | PRINCE2 | 2025-02-21 | 2025-04-01 | 2025-02-27 | 2025-02-27 | 0 |  | 2025-11-30 | 2025-03-10 | 2025-11-30 | 2026-06-30 | 1431025 | 1677929 | Green | Green | Green | Green | Green | Project Completed.
Q4 25-26 | Peter MacCallum Cancer Centre | Peter MAC | 4069 | High Performance Compute and Storage infrastructure refresh and upgrade (HPC) | Health | Assets/Materials Management,Systems Management | The project will deliver a refreshed and upgraded High Performance Compute (HPC) and Storage infrastructure for Peter Mac Research, replacing outdated hardware with advanced, high-performance equipment. | Initiated |  |  | PRINCE2 | 2024-10-01 | 2025-11-28 | 2026-06-30 |  | 0 | 0 | [11 empty] | Business case has been presented to the Board and funding has been approved. Project to kick off in Q1 2026-27.
Q4 25-26 | Peter MacCallum Cancer Centre | Peter MAC | 4070 | Network Infrastructure Refresh | Health | Assets/Materials Management,Systems Management | The project will deliver a comprehensive refresh of Peter Mac's network infrastructure, including all physical components and the provision of layer 2 and layer 3 services across the WAN, LAN, and WLAN. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-10-01 | 2025-10-31 | 2025-07-23 | 2025-07-23 | 0 |  | 2025-10-01 | 2025-12-10 | 2026-12-31 | 2026-12-04 | 6773270 | 2525426 |  |  | Green | Green | Green | The project is tracking against agreed timelines and milestones with financial performance remaining on budget.
Q4 25-26 | Western Health | WH | 4073 | Network Switches Asset Replacement 23/24 | Health | Development and Integration | End of life replacement of network switches at Sunshine Hospital to ensure network reliability, supportability and security, enabling WH to deliver services for the future, high quality connected care and better health outcomes for our community. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2024-01-02 | 2024-02-23 |  | 2024-02-26 | 0 |  | 2024-11-18 |  | 2025-08-26 | 2026-11-30 | 4156643 |  | Green | Green | Green | Green | Green | Proceeding in accordance with the schedule approved by the Steering Committee.
Q4 25-26 | Melbourne Water | MELB Water | 4076 | Mobile Device Management | Environment and Water | Assets/Materials Management | Enhance support for flexible remote working arrangements for staff improving management of corporate devices by implementing a system that effectively addresses the challenges of remote device management and supports Bring your own device policies. | Postponed |  | 2025-09-08 | PMBoK | 2024-08-21 | 2025-05-21 | 2026-09-12 |  | 0 | [5 empty] | 0 | [6 empty] | As at 20260331: The project has been deferred and is scheduled for delivery in FY2027.
Q4 25-26 | Department of Education | DE | 4078 | Academy Customer Relationship Management_Course Management | Education | Customer Relationship Management,Data Management,Reporting | The project will improve business processes focusing on the Victorian Academy of Teaching and Leadership’s relationship management and enables the effective marketing management delivery and reporting of professional learning to Victorian educators. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-01 | 2024-08-16 |  | 2024-08-30 | 0 |  | 2025-01-28 |  | 2026-08-13 | 2026-10-16 | 9649702 | 10116117 | Green | Amber | Amber | Amber | Green | The Project returned to GREEN through internal reallocation of an additional $500K.
Q4 25-26 | Yarra Valley Water | YV Water | 4080 | IT Systems Monitoring & Logging | Environment and Water | Security Management ,Systems Management,Visualisation | Implement a platform which will encompass comprehensive monitoring, logging, synthetic monitoring, and a unified monitoring dashboard to enhance security, improve reliability, and visibility into our IT infrastructure and application performance. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-02 | 2025-01-31 |  | 2025-02-04 | 48000 |  | 2025-02-04 |  | 2027-02-28 |  | 1334300 |  | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q4 25-26 | Victorian Fisheries Authority | VFA | 4088 | Licensing Quota Management System | Business and Industry | Customer Initiated Assistance,Data Management,Management of Process ,Reporting ,Systems Management | The project will digitise the commercial quota management, licencing and permit application process, by delivering a self-service mobile application for commercial fishers and permit holders, improving access to data and support from VFA. | Closed - Completed | Compliance (Non Financial), Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2026-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-06-01 | 2022-11-14 |  | 2024-07-14 | 0 |  | 2025-01-14 |  | 2026-06-30 |  | 1450000 |  | Green | Green | Green | Green | Green | The project successfully delivered LQMS on 27 May 2026
Q4 25-26 | Victorian Rail Track | VicTrack | 4090 | Cyber Security Roadmap | Transport and Vehicles | Security Management | To uplift the cyber-security maturity of VicTrack, fulfil our regulatory obligations under VPDSS and the Essential 8, and secure critical assets against cyber threats. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-01-31 | 2025-03-19 |  | 2025-03-19 | 0 |  | 2025-03-19 |  | 2028-06-30 |  | 12530000 | 12531600 | Amber | Green | Green | Green | Green | The Cyber Security Uplift Program continues to make solid progress, staying relatively on track and within the allocated budget
Q4 25-26 | Victorian Rail Track | VicTrack | 4091 | Project Backup Server & Storage Replacement | Transport and Vehicles | Data Management | Refresh of the current storage and backup solution to improve storage capacity, introduce additional security features, uplift to provide better resilience against modern cyber-attacks. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-01-06 | 2025-06-27 |  | 2025-06-27 | 0 |  | 2025-06-27 |  | 2026-06-30 | 2026-09-30 | 1594439 | 1398439 | Amber | Green | Green | Green | Amber | Schedule delays due to issues with data centre rack suitability constraints, hardware installation issues and unexpected software upgrade complications.
Q4 25-26 | Victorian Public Sector Commission | VPSC | 4102 | Cloud Migration and Transformation | Government and Economy | Analyses and Statistics | Modernising VPSC’s analytics by migrating to a secure cloud platform using Microsoft Fabric, Power Platform, and Entra ID to streamline reporting, improve data quality, and enable scalable, AI-driven workforce insights. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-08-29 | 2024-12-19 |  | 2024-12-19 | 0 |  | 2025-03-21 |  | 2026-06-30 |  | 1773267 | 2097607 | Green | Green | Green | Green | Green | There is no update for this period.
Q4 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4103 | Common Technology Platform (CTP) Program - Phase 3 | Government and Economy | Security Management | The CTP Program was established to deliver the technology strategy via a 3-year phased approach. Phase 3 will uplift the 2 remaining platforms (spatial and digital) and enhance platforms established during previous phases. | Closed - Completed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2026-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-02-03 | 2024-12-12 |  | 2025-03-21 | 0 |  | 2025-03-21 |  | 2026-06-30 |  | 1798000 |  | Green | Green | Green | Green | Green | All planned deliverables have been completed as per the baseline project delivery plan.
Q4 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4104 | Cyber Security Uplift Program | Government and Economy | Security Management | Cyber Security program will deliver a set of controls, processes and education that aligns with the Victorian Cyber Security Strategy and leverages the WoVG capabilities to reduce and address cyber security risks. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-02-01 | 2024-12-12 |  | 2025-03-21 | 0 |  | 2025-03-21 |  | 2027-06-30 | 2026-09-30 | 6034000 |  | Green | Green | Green | Green | Amber | Overall, the program has delivered to scope, schedule, and budget. However, two deliverables have been delayed and are now expected to be completed in August due to unforeseen implementation issues.
Q4 25-26 | Hume Rural Health Alliance | HRHA | 4106 | Cyber Security Maturity Uplift implementation | Health | Security Management | The purpose of this project is to ensure a regional uplift in Cybersecurity through reducing risks uplifting governance and risk management practices and alignment to the Department of Health's Cyber Security Assurance Framework. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-10-02 | 2024-02-12 |  | 2024-02-12 | 0 |  | 2024-07-01 |  | 2027-06-30 |  | 1950000 |  | Green | Green | Green | Green | Green | Project activities remain on track.
Q4 25-26 | WorkSafe Victoria | WorkSafe | 4107 | Claims Management System Uplift for Workplace Injury and Rehabilitation Compensation (WIRC) Amendment Act | Employment, Skills and Workplace | Systems Management | This project will operationalise the proposed WIRC Act Amendment Bill (now WIRC Amendment Act 2025) and uplift existing claims management systems to ensure high-quality service and improve support to users of Victoria’s workers compensation scheme. | Delivery | Compliance (Non Financial), Increased Quality (Non Financial), Social Improvement (Non Financial) |  | Waterfall | 2024-11-25 | 2025-03-05 |  | 2025-03-05 | 0 |  | 2025-03-05 |  | 2026-12-15 | 2027-09-30 | 1728437 |  | Amber | Green | Green | Amber | Green | Approval of schedule extension has returned the project to Green.
Q4 25-26 | South East Water | SE Water | 4108 | Service Management System Implementation | Environment and Water | Systems Management | Replacement and transformation of SEW's internal Service Management solution used across multiple business functions. This project will deliver uplift in internal capabilities and deliver efficiencies through streamlining service management processes | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial) |  | Waterfall | 2024-10-01 | 2025-03-28 |  | 2025-04-01 | 0 |  | 2025-04-01 |  | 2026-01-30 | 2026-09-30 | 1380500 |  | Green | Amber | Green | Red | Amber | Project reporting AMBER due to vendor resourcing issues, as well as an unplanned version upgrade that was required which delayed the project 1 week. Project has been rescheduled and re-baselined as a result.
Q4 25-26 | WorkSafe Victoria | WorkSafe | 4111 | Cheques Migration Strategy | Employment, Skills and Workplace | Financial Management | This project will operationalise the Victorian Government directive to cease cheque payments and will implement complex system changes to ensure faster payments for injured workers and providers and reduce administration costs. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial) |  | Waterfall | 2024-10-08 | 2025-05-27 |  | 2025-05-28 | 0 |  | 2025-05-28 |  | 2027-12-31 |  | 2143701 | 2632494 | Green | Green | Green | Red | Green | Work is progressing as planned. Change request for additional funding has been approved, returning the project to Green.
Q4 25-26 | Department of Transport and Planning | DTP | 4112 | Records Management Uplift - Stage 2b | Transport and Vehicles | Records Management | The project will review and refine the records management environment and consolidate organisational data into Records365, standardising and uplifting the records management solution & practices across the DTP. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-07 | 2025-07-10 | 2025-12-01 | 2025-12-01 | 0 |  | 2025-12-01 |  | 2026-06-30 | 2026-07-31 | 3400000 |  |  |  | Amber | Amber | Green | The project is tracking green and nearing closure.
Q4 25-26 | Melbourne Water | MELB Water | 4117 | Data Lake | Environment and Water | Data Management | Build a data warehouse solution that is scalable, secure and evolves to meet growing business insights and reporting needs of Melbourne Water. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2026-05-15 | PMBoK | 2024-02-01 | 2024-04-02 |  | 2024-04-02 | 0 |  | 2024-04-02 |  | 2026-05-15 |  | 3301197 | 3212274 | Amber | Green | Green | Green | Green | As at 20260630: Project is complete.
Q4 25-26 | CenITex | CenITex | 4118 | Cenitex Office Relocation | Government and Economy | Assets/Materials Management | Make 35C fit for Cenitex purpose to undertake its core role in providing support and technology solutions for customers across WoVG. With a lease end of Jun’25 at 80C, the timeline to undertake this work is tight with a early June relocation target. | Closed - Completed | Cost Reduction (Financial), Customer Satisfaction (Non Financial) | 2026-06-30 | PRINCE2 | 2025-03-20 | 2025-03-20 |  | 2025-03-20 | 0 |  | 2025-03-20 |  | 2025-10-31 | 2026-06-30 | 2570677 | 2567674 | Green | Green | Green | Green | Green | Project Completed.
Q4 25-26 | Victorian Rail Track | VicTrack | 4120 | HCI Replacement Project | Transport and Vehicles | Systems Management | Hyper-converged infrastructure (HCI) utilises physical servers to create a software-defined IT environment that virtualises all components of traditional hardware-based systems. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-01 | 2025-05-16 |  | 2025-05-16 | 0 |  | 2025-05-16 |  | 2026-12-31 | 2027-06-30 | 9000000 | 9511000 | Green | Green | Green | Amber | Amber | Of the two projects supporting this initiative one is currently Green with no significant issues. The second project is rated Amber due to delays and risks associated with market engagement and procurement activities.
Q4 25-26 | Department of Families, Fairness and Housing | DFFH | 4121 | Replacement Document and Records Management System | Community Services | Records Management | Replace the existing out-of-support records management system (Housing TRIM) with a new, supported record keeping system that uses cloud storage and provides staff with improved business functionality. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-11-29 | 2025-04-09 |  | 2025-04-09 | 351860 |  | 2025-04-09 |  | 2026-03-31 | 2026-08-31 | 5898928 | 4934376 | Amber | Amber | Green | Amber | Amber | Project has successfully delivered core functionality. Project is Amber due to delays in deployment of new back up retention design. Cost and schedule revised and project expected to complete in next reporting period.
Q4 25-26 | Melbourne Water | MELB Water | 4127 | Asset Maintenance application upgrade | Environment and Water | Tracking and Workflow | Upgrade of our asset management system to a modern platform that enhances scalability, security, and usability. Ensuring ongoing support beyond 2025, reduces operational risk, and provides advanced features and improved reporting. | Initiated |  |  | Waterfall | 2023-10-09 | 2026-04-09 | 2026-08-31 |  | 0 | [12 empty] | As at 20260630: Post Functional Review the approach has now been defined, next steps is to progress through second internal stage gate and submit tender to market.
Q4 25-26 | Melbourne Water | MELB Water | 4128 | SCADA For Our Future | Environment and Water | Assets/Materials Management | A next-generation system to enhance real-time monitoring, decision-making, and automation across our water, sewerage, & drainage networks. Providing advance alarm and incident management to meet growing service complexity and performance expectations | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2019-10-25 | 2025-11-25 |  | 2025-11-25 | 0 |  | 2025-11-25 |  | 2028-08-28 |  | 39352377 |  |  |  | Red | Red | Red | As at 20260630: Independent assurance team currently working with project team to ensure set up for success for continued detail design over the coming quarter. Project red due to outstanding resource requirements in specialist skillsets (currently recruiting) and anticipated to resolve.
Q4 25-26 | Melbourne Water | MELB Water | 4129 | Dam Surveillance Information System | Environment and Water | Management of Process | Replacement of an outdated system with a modern, fully supported solution that brings enhanced automation, smarter features, and improved reporting—empowering the Water Control teams to work more efficiently and make better-informed decisions | Delivery | Risk Reduction (Non Financial) |  | Agile | 2023-05-10 | 2024-12-10 |  | 2024-12-10 | 0 |  | 2024-12-10 |  | 2026-10-05 | 2027-04-01 | 3340950 |  | Amber | Green | Green | Green | Green | As at 20260630: Project is on track
Q4 25-26 | Treasury Corporation of Victoria | TCV | 4130 | Infrastructure IT Refresh | Government and Economy | Systems Management | Deployment of a resilient IT infrastructure with cloud-based disaster recovery and secure remote access. It will enhance system uptime, disaster recovery speed and secure remote work capabilities whilst ensuring continuity of TCV’s critical systems. | Closed - Completed | Compliance (Non Financial), Cost Avoidance (Financial) | 2026-06-30 | Waterfall | 2025-04-01 | 2025-04-22 |  | 2025-04-22 | 0 |  | 2025-06-20 |  | 2025-11-30 | 2026-05-31 | 1476000 | 1536000 | Green | Green | Green | Green | Green | Implementation of the Working from Anywhere capability was completed during the reporting period, including pilot testing, disaster recovery and business continuity planning and testing, user acceptance testing, and full deployment. All activities were completed successfully, contributing to the achievement of the project's objectives. The project is now closed.
Q4 25-26 | Western Health | WH | 4132 | Workstation on Wheels (WoW) replacement | Health | Systems Management | This project will replace end-of-life hardware for Workstations on Wheels (WoW) with updated hardware and software, enabling patient record access and update for doctors and nurses to provide quality patient care. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2025-02-24 | 2025-06-05 |  | 2025-06-06 | 0 |  | 2025-06-23 |  | 2025-11-28 | 2026-06-30 | 2400000 |  | Green | Green | Green | Green | Green | Implementation date extended to 30 June 2026 due to implementation resources being diverted to urgent work following WH migration to the new Footscray Hospital. Approved by Steering Committee.
Q4 25-26 | Western Health | WH | 4134 | Network Switches Asset Replacement 24/25 | Health | Systems Management | End of life replacement of network switches across WH sites to ensure network reliability, supportability and security, enabling WH to deliver services for the future, high quality connected care and better health outcomes for our community. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2024-01-02 | 2025-04-23 |  | 2025-04-24 | 0 |  | 2025-08-04 |  | 2026-05-25 | 2026-09-25 | 2353000 |  |  | Green | Green | Green | Green | Detailed implementation schedule finalised and approved by the Steering Committee.
Q4 25-26 | Holmesglen Institute of TAFE | Holmesglen TAFE | 4135 | ICT Infrastructure (Servers, LAN, Wifi, Telephony) & Data Centre Refresh | Employment, Skills and Workplace | Systems Management | The project will replace and upgrade the end-of-life ICT infrastructure and data centre with enhanced cyber security protection, minimising security risks and enabling faster, advanced technology access for students and staff at Holmesglen. | Delivery | Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2025-03-26 | 2025-07-28 | 2025-09-30 | 2025-10-07 | 0 |  | 2025-10-17 |  | 2027-12-17 |  | 32000000 |  |  |  | Green | Green | Green | The ICT Infrastructure Refresh Program remains On Track with strong progress achieved across infrastructure deployment network modernisation telephony and collaboration technologies. During the quarter major infrastructure deliveries were completed and infra hardware installed at NextDC data centre readied for implementation activities. Detailed design work for network security and data centre platforms is nearing completion while deployment of network switches Wi-Fi infrastructure and Webex technologies commenced. Governance vendor management and delivery oversight remain effective with no material risks or issues requiring escalation. The program will progress in Q1 into implementation and migration readiness activities.
Q4 25-26 | Western Health | WH | 4136 | Automatic Dispensing Cabinets (ADC) | Health | Systems Management | Implementation of automated medication cabinets replacing manual shelving for electronically tracked & secure storage of Imprest medications, enabling timely & safe medication access for staff at new Footscray Hospital delivering quality patient care | Closed - Completed | Risk Reduction (Non Financial) | 2026-06-28 | PRINCE2 | 2019-05-14 | 2019-09-04 |  | 2020-01-06 | 0 |  | 2024-03-04 |  | 2026-06-28 |  | 2502072 |  | Green | Green | Green | Green | Green | Project Closed
Q4 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4140 | Permissions Application Project | Environment and Water | Collaboration ,Customer Initiated Assistance,Customer Relationship Management,Tracking and Workflow | The project will deliver a new system to replace the current Wildlife Licence System, which is now at end-of-life. The new system will feature a self-service portal designed to improve user experience, streamline processes, and enhance compliance. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-01 | 2026-04-30 | 2026-05-11 | 2026-05-11 | 390151 | 711666 | 2026-05-12 |  | 2027-06-30 |  | 2853895 | [5 empty] | Green | The project remains on track and is progressing in line with the agreed scope, budget, and schedule. The development phase has commenced, with 2 of 13 planned working cycles currently in progress.
Q4 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4142 | Emergency Resource Management System (ERMS) Project | Emergencies and Safety | Customer Initiated Assistance,Human Capital / Workforce Management | The project will deliver a fit-for-purpose ERMS to reduce the impact of bio-security, agriculture, and other emergencies on the Victorian community and environment through timely and effective preparedness, response, relief, and recovery services. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - Waterfall and Agile | 2025-07-01 | 2026-01-30 | 2025-12-08 | 2025-12-08 | 240000 |  | 2025-12-09 |  | 2027-05-30 |  | 2534323 |  |  |  |  | Green | Green | The project is progressing as planned. Release 1 configuration is currently under development, the Integration Solution Design is being finalised for approval, and change management activities have commenced.
Q4 25-26 | Court Services Victoria | CSV | 4147 | VCAT Long Term Accommodation (LTA ) - Technology Component | Law and Justice | Assets/Materials Management,Development and Integration | The objective of the project requires the preparation of the new VCAT Long Term Accommodation site to be a member of the Cenitex GSP INTERNAL Network for use by CSV/VCAT Staff and Customers. | Closed - Completed | Customer Satisfaction (Non Financial) | 2026-04-30 | Waterfall and Agile | 2025-05-06 | 2025-05-06 |  | 2025-05-06 | 0 |  | 2025-07-01 |  | 2026-04-30 |  | 1178028 |  |  | Green | Green | Green | Green | All project deliverables met, Project closure report received.
Q4 25-26 | Barwon Region Water Corporation | BR Water | 4148 | C1419 - Smart Networks Water - Proof of Value (POV) | Environment and Water | Assets/Materials Management | The Smart Networks Water Project will procure, implement and monitor Digital Meters in a series of locations within the Barwon region to capture the benefits, costs, resourcing and effort to inform a Mass Rollout Business Case for PS28. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-10 | 2023-11-21 |  | 2023-11-21 | 376900 |  | 2024-03-04 |  | 2028-06-30 |  | 9490000 |  |  | Amber | Amber | Amber | Amber | The Smart Networks Water project delivery commenced in March 2024. The project has continued to progress with the required process and guideline changes to support the Digital Meter deployment having been completed and the digital dependencies being finalised. Digital Meter testing is being finalised and Barwon Water are continuing to currently monitor international delivery lead times with suppliers and potential impacts.
Q4 25-26 | Barwon Region Water Corporation | BR Water | 4149 | C1441 - Smart Networks Sewer - Proof of Value (POV) | Environment and Water | Assets/Materials Management | The Smart Networks Sewer Project will trial, implement and monitor a series of Sewer Sensors and an analytics capability to capture the benefits, costs, resourcing and effort to inform a Mass Rollout Business Case for PS28. | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-10 | 2023-11-23 |  | 2023-11-23 | 251300 |  | 2024-03-04 |  | 2028-06-30 |  | 7170000 |  |  | Green | Green | Green | Green | The Smart Networks Sewer Proof of Value project commenced in March 2024. The trials and analytical insights gained to date have highlighted further opportunities to leverage the proposed solution to deliver additional benefit to Barwon Water moving forward. These scenarios will be trialled and evaluated over the coming year but need to be balanced with achieving the initial project outcomes.
Q4 25-26 | Transport Accident Commission | TAC | 4151 | Continuous Delivery 2026 | Transport and Vehicles | Systems Management | The project will deliver enhancement to TAC’s Claims Management system to uplift performance, reduce risk, and improve user experience, ensuring sustained business value and responsiveness to priorities | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2026-06-30 | Agile | 2025-07-01 | 2025-07-01 |  | 2025-07-01 | 0 |  | 2025-07-01 |  | 2026-06-30 |  | 5404953 |  |  | Green | Green | Green | Green | The Continuous Delivery team successfully delivered key solutions supporting the Protocols OT Model Onboarding Optimisation and Payments Optimisation projects. Delivery remained on track with changing priorities and minor sprint spillover managed without impacting overall milestones. Scope budget and schedule remain aligned to plan with next quarter focused on completing Protocols and NIDS deliverables while supporting ongoing business priorities and future Claims Platform alignment.
Q4 25-26 | Transport Accident Commission | TAC | 4152 | Microsoft Program of Work for Enterprise Readiness (M-POWER) | Transport and Vehicles | Systems Management | This project will establish a dedicated Microsoft tenancy & cloud infrastructure for TAC, streamlining enterprise systems using a modern platform & minimising the risks associated with legacy technologies to enable more efficient services to clients. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-07-01 |  | 2025-07-01 | 0 |  | 2025-07-01 |  | 2027-12-31 |  | 20000000 |  |  | Green | Green | Green | Green | The program delivered a strong quarter achieving major build and testing milestones across all platform streams including the first dress rehearsal and successful development environment migration. Assurance activities identified a support readiness gap early demonstrating the effectiveness of program governance and providing time to address the issue before go-live. As a result Executive Leadership Team approval was secured to move the go-live date to October 2026. This measured risk-based approach supports a stable transition and maintains strong confidence in a successful and sustainable implementation.
Q4 25-26 | Melbourne Water | MELB Water | 4153 | Web Enhancements | Environment and Water | Content Management | Additional features to be added to MW website to deliver core functions. | Closed - Completed | Customer Satisfaction (Non Financial), Workforce Satisfaction (Non Financial) | 2026-06-18 | Agile | 2025-02-25 | 2026-11-10 | 2026-01-29 | 2026-01-29 | 0 |  | 2026-01-29 |  | 2026-06-09 |  | 1507806 |  |  |  |  | Amber | Green | As at 20260630: Project is complete.
Q4 25-26 | Yarra Valley Water | YV Water | 4154 | Finance Transformation | Environment and Water | Financial Management | Implementation of a new Finance system with integrations, including uplift to operating model. Key outcomes being risk reduction achieved by replacing EoL system plus aligning to business priorities of operational efficiencies and UX improvements. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-09-01 | 2026-08-28 | 2026-11-30 |  | 1760200 | [12 empty] | The project is progressing well in the Tender Evaluation stage, including scoring and clarification with support from the Probity Advisor. Currently, four preferred tenderers are selected to progress to the next stage of the tender for demo activity for further evaluation. The project aims to have the preferred tenderer selected end of July and commence on drafting Statement of work for approval for Nov.
Q4 25-26 | Melbourne Water | MELB Water | 4155 | OS Upgrade | Environment and Water | Systems Management | Upgrading all laptops and PC's to a new operating system. | Closed - Completed | Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) | 2026-05-01 | PRINCE2 | 2024-10-24 | 2025-07-25 |  | 2025-07-25 | 0 |  | 2025-07-25 |  | 2026-02-27 | 2026-05-01 | 1308000 | 1260625 |  | Green | Green | Amber | Green | As at 20260630: Project is complete.
Q4 25-26 | Yarra Valley Water | YV Water | 4156 | Customised Collections | Environment and Water | Financial Management | This project will deliver a Customised Collections solution in Oracle CC&B, uplifting YVW’s ability to segment customers and tailor debt management. It will reduce bad debt and improve outcomes for customers and the organisation. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Agile | 2020-08-01 | 2025-09-17 |  | 2025-09-18 | 888100 |  | 2025-09-18 |  | 2026-05-18 |  | 1119197 |  |  | Green | Amber | Amber | Amber | Reestimation and replanning has been completed with assumptions and open risks. Project has delivered first release into production being the base functionality. A change request to extend the schedule and costs is underway.
Q4 25-26 | Yarra Valley Water | YV Water | 4157 | Digital Metering – Customer Solutions for New Segments | Environment and Water | Communication,Content Management,Customer Relationship Management,Development and Integration | The project will enable the implementation of the more complex customer journeys inclusive of the process uplifts required to facilitate the installation of digital meter to more complex and larger scale customer types. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-06-01 | 2025-08-31 |  | 2025-09-01 | 270000 |  | 2025-09-01 |  | 2026-06-30 | 2027-06-30 | 2169620 | 2207420 |  | Green | Green | Green | Green | New scope items uncovered during development stages for 2 critical packages of work, requiring rework and redesign. The rest of project is on track
Q4 25-26 | WorkSafe Victoria | WorkSafe | 4158 | Safety CRM (Customer Relationship Management) | Employment, Skills and Workplace | Customer Relationship Management | This project will modernise safety inspection and notification systems to improve frontline efficiency and stakeholder experience. | Closed - Completed | Compliance (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) | 2026-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-14 | 2025-05-28 |  | 2025-05-28 | 0 |  | 2025-07-01 |  | 2026-06-30 |  | 4863898 | 4994037 |  | Green | Green | Green | Green | Project has delivered all integrations as planned and is now closed
Q4 25-26 | Department of Government Services | DGS | 4159 | Children's Digital Program | Government and Economy | Development and Integration | Developing an end-to-end digital experience from birth to school that provides parents with a digital family organiser to manage key information about their child. | Delivery | Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-06-03 | 2025-06-24 |  | 2025-06-24 | 0 |  | 2025-06-25 |  | 2026-09-30 | 2027-06-30 | 17003000 |  |  | Amber | Amber | Amber | Green | The program has returned to Green status following the successful completion and public launch of Phase 1. Phase 2 activities are progressing as planned and are on track.
Q4 25-26 | Department of Health | DH | 4160 | Data Loss Prevention Phase 1 | Health | Security Management | Conduct detailed current state analysis of DH and DFFH Data Loss Protection (DLP) capability for emails classified as 'Protected' and 'Cabinet-in-Confidence' and implement improved DLP controls to emails, reducing risk of accidental data loss. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-10-27 | 2025-10-22 | 2025-10-22 | 74200 | 96525 | 2025-10-23 |  | 2026-06-30 |  | 1407475 |  |  |  | Amber | Amber | Amber | Pilot successfully completed. Project remains Amber while future implementation activities and associated cost and schedule impacts are being assessed and will be updated in next reporting period.
Q4 25-26 | V/Line Corporation | V/Line | 4161 | TrackR Stabilisation | Transport and Vehicles | Systems Management | The objective of the project is to stabilise V/Line’s critical train and fleet operations system (TrackR). Stabilisation of TrackR will result in increase in reliability and performance of the system’s key workflows, and improve service delivery. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-09-30 |  | 2025-10-01 | 57000 |  | 2025-10-01 |  | 2027-12-31 |  | 3230000 |  |  |  | Green | Green | Green | Project is on track, with no major roadblocks or issues to date.
Q4 25-26 | Goulburn-Murray Rural Water Corporation | GMR Water | 4162 | PC/Laptop Replacement | Environment and Water | Assets/Materials Management | This project will deliver 550 new PCs and laptops, enhancing Goulburn Murray Water’s IT capability by improving performance and reliability, enabling a more productive, digitally enabled workforce for better service delivery. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2025-03-25 | 2025-09-02 |  | 2025-09-02 | 0 |  | 2025-09-02 |  | 2028-06-30 |  | 1300000 |  |  | Green | Green | Green | Green | The project has commenced with planning and procurement activities now underway. Initial assessments of staff requirements have been completed and deployment scheduling and coordination with relevant departments are in progress.
Q4 25-26 | Melbourne Health | Melb H | 4164 | Computer Assisted Coding Solution | Health | Management of Process | Computer-assisted coding software, for the entire clinical coding process- to streamline processes, capture complexity, optimise reimbursement, ensure data compliance and make data-informed decisions. | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | PRINCE2 | 2025-03-03 | 2025-06-19 |  | 2025-06-19 | 0 |  | 2026-01-01 | 2026-02-17 | 2026-12-31 | 2027-04-30 | 1007474 | 1078000 |  |  |  | Green | Green | The project is on track.
Q4 25-26 | Melbourne Health | Melb H | 4165 | E-referral for outpatient specialist clinics | Health | Development and Integration | Implementing an Electronic Medical Record integrated e-Referral system across the 4 Parkville Precinct hospitals, which enhances management of external GP/Specialists referrals to outpatient specialist clinics and improves patient data quality | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2025-03-03 | 2025-03-05 |  | 2025-03-05 | 0 |  | 2025-09-01 |  | 2026-08-31 |  | 1180854 |  |  | Green | Green | Green | Green | Project is on track.
Q4 25-26 | Barwon Region Water Corporation | BR Water | 4167 | C1073 - Information & Records Management (IRM) | Environment and Water | Content Management | This initiative aims to enhance Barwon Water Group's Information Records Management (IRM) capability through a phased maturity uplift. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-01 | 2025-09-08 |  | 2025-09-08 | 537000 |  | 2025-09-08 |  | 2026-10-31 | 2026-12-31 | 580000 |  |  | Green | Green | Red | Amber | Objective Gov365 has been successfully deployed and is being progressively implemented. The project control group has requested a project change request to defer the implementation of Objective 3Sixty
Q4 25-26 | Bendigo Kangan Institute of TAFE | BKI TAFE | 4168 | Artificial Intelligence for Recognition of Prior Learning | Employment, Skills and Workplace | Development and Integration | On behalf of the Victorian TAFE Network, BKI will pilot an artificial intelligence (AI) solution to uplift the assessment capability in the Recognition of Prior Learning (RPL), enabling a more efficient processing time for assessors and applicants. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-08-28 | 2025-12-31 | 2026-04-30 | 2026-04-30 | 180000 | 300000 | 2026-04-30 |  | 2027-01-31 |  | 2700000 | [5 empty] | Amber | The project remains achievable within its approved scope and funding; however, dependencies between requirements, procurement, technology selection and pilot development create schedule pressure. Some key activities are progressing later than originally anticipated and require active management.
Q4 25-26 | South East Water | SE Water | 4170 | Acumen Phase 3 | Environment and Water | Business Intelligence | Acumen Phase 3 will deliver remaining data sources into new Acumen platform. A subset of Data Modelling will be undertaken to support the report development required to decommission the legacy data warehouse and reporting environment. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2025-05-01 | 2025-07-28 |  | 2025-07-30 | 0 |  | 2025-07-30 |  | 2026-12-18 |  | 8220471 |  |  | Green | Green | Amber | Amber | Project continues to report AMBER due to some ongoing challenges with data ingestion from internal ERP system. This is further impacted by key SME resource availability.
Q4 25-26 | Department of Health | DH | 4173 | Maternal and Child Health IT System | Health | Customer Relationship Management | Deliver a new statewide IT system to support the delivery of Maternal Child Health services, providing additional functions as well as accommodating future growth in service delivery and customer base. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Agile | 2025-03-03 | 2025-05-02 |  | 2025-05-02 | 163733 |  | 2025-05-02 |  | 2027-06-30 |  | 12286267 | 12286267 |  | Green | Amber | Amber | Green | Project progressing to cost and schedule.
Q4 25-26 | Ambulance Victoria | AVS | 4174 | Mobile Data Network Rural (MDNR) | Health | Communication | The project will upgrade and expand communication services for emergency responders in rural Victoria, improving real-time data access to enable dispatch efficiency, enhancing paramedic safety and better patient care. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-10-08 | 2022-10-21 |  | 2022-10-21 | 24043 |  | 2024-11-14 |  | 2027-05-30 |  | 24971040 |  |  | Green | Red | Red | Red | Project status remains Red pending formal approval of the revised schedule. The delays were driven by a series of testing related issues. Extensive testing activites during Q4 have increased confidence in the stability and quality of the solution supporting readiness for deployment and recommencement of training development. A return to Green status is anticipated next quarter.
Q4 25-26 | South East Water | SE Water | 4175 | Portfolio & Project Management Uplift | Environment and Water | Financial Management | South East Water is uplifting its ERP environment to enable enterprise-wide project and portfolio management. This project will enhance planning execution reporting and data integration across capital and operational projects. | Initiated |  |  | Waterfall | 2025-07-01 | 2026-02-28 | 2026-06-30 |  | 1388000 | [12 empty] | Project continues to report GREEN. The business case for the delivery of this work has now been completed and will be presented to the board in July for approval.
Q4 25-26 | Emergency Services Superannuation Scheme | ESS SUPER | 4177 | NetSuite General Ledger Implementation | Business and Industry | Financial Management | ESSSuper is implementing Oracle NetSuite to replace its SunGL general ledger. The new cloud‑based system will enhance efficiency, improve resilience, and provide a secure, scalable platform that better supports the Fund's future requirements. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2025-07-01 | 2025-10-31 | 2025-10-24 | 2025-10-24 | 50000 | 42538 | 2025-11-03 |  | 2026-10-15 |  | 1282333 |  |  |  | Green | Green | Green | Project tracking to plan.
Q4 25-26 | State Revenue Office | SRO | 4178 | Emergency Services Volunteers Fund | Government and Economy | Development and Integration | This project implements changes to collect the Emergency Services Volunteers Fund (ESVF) from 1 July 2025, ESVF supports a broader range of emergency services such as floods, storms and other emergencies, replacing the Fire Services Property Levy. | Closed - Completed | Cost Reduction (Financial), Customer Satisfaction (Non Financial) | 2026-06-30 | Agile | 2025-04-02 | 2025-06-30 |  | 2025-06-30 | 208928 |  | 2025-07-01 |  | 2026-06-30 |  | 2208201 |  |  | Green | Green | Green | Green | Project successfully completed in May 2026.
Q4 25-26 | State Revenue Office | SRO | 4179 | Enterprise Service Management | Government and Economy | Development and Integration | The State Revenue Office is procuring a modern Enterprise Service Management tool to provide better business outcomes with automation and self-service capabilities. This initiative procures and integrates the tool and implements the required workflow | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2025-03-05 | 2025-06-30 |  | 2025-06-30 | 29739 |  | 2025-07-01 |  | 2027-06-30 |  | 3643630 | 2672589 |  | Green | Amber | Amber | Green | Requirements gathering and other project activities continue. Vendor mobilisation on project activities.
Q4 25-26 | State Electricity Commission (SEC) Victoria Pty Ltd | SECV | 4180 | One-stop shop project | Energy and Resources | Customer Initiated Assistance | Deliver a one-stop shop digital platform to enable Victorian households to be supported by information and access to SEC endorsed installers manage home electrification. | Closed - Completed | Customer Satisfaction (Non Financial) | 2026-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-01 | 2025-07-31 |  | 2025-07-31 | 248955 |  | 2025-08-01 |  | 2026-06-30 |  | 7417752 |  |  | Green | Amber | Amber | Green | Project has been completed on time with successful launch of Easy Electric platform and closure of hyper-care period.
Q4 25-26 | State Revenue Office | SRO | 4181 | Data Lakehouse Utilisation | Government and Economy | Development and Integration | Establishing a cloud-based Data Lakehouse is a key element of the SRO's data and analytics strategy to uplift the organisation's data and analytics capacity, capability, operational efficiency and reporting. This project includes 2 use cases. | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | Agile | 2025-02-03 | 2025-06-30 |  | 2025-06-30 | 429284 |  | 2025-07-01 |  | 2026-06-30 | 2026-10-30 | 2327800 | 2809983 |  | Green | Green | Amber | Green | Project is on track.
Q4 25-26 | Department of Health | DH | 4183 | Victorian Patient Transport Assistance Scheme (VPTAS) System Replacement | Health | Customer Initiated Assistance | Implement a new VPTAS claims system that leverages the DFFH-DH Enterprise Payments Platform, enabling digitising of the current paper based claimant forms, providing greater efficiencies in the response to and management of claims. | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2026-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-07-31 |  | 2025-07-31 | 89154 |  | 2025-08-01 |  | 2026-04-30 | 2026-04-30 | 1710846 |  |  | Amber | Amber | Amber | Green | Project has successfully delivered and closeout activities are underway.
Q4 25-26 | East Gippsland Regional Water Corporation | EGR Water | 4187 | Enterprise Asset Management | Environment and Water | Assets/Materials Management | It is a modern solution for managing the entire asset lifecycle supporting functions such as commissioning maintenance optimization planning reporting and analytics. The system aims to deliver operational cost savings and efficiency improvements. | Closed - Completed | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2026-06-30 | PRINCE2 | 2024-10-29 | 2025-01-31 |  | 2025-01-31 | 0 |  | 2025-05-01 |  | 2026-06-30 |  | 1993000 | 1747083 |  | Green | Green | Green | Green | Project was completed on time and slight 6% underspend from projected budget.
Q4 25-26 | Department of Education | DE | 4191 | Student Travel System | Education | Management of Process | The project will digitise Student Travelling applications and centralise information, reducing administrative effort and improving accuracy and timeliness of school bus program. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-02-03 | 2025-03-21 |  | 2025-09-08 | 0 |  | 2025-09-08 |  | 2026-03-20 | 2026-07-10 | 4242287 | 5438770 |  | Amber | Amber | Green | Amber | The department is currently resolving some minor defects identified during user acceptance testing.
Q4 25-26 | Department of Education | DE | 4192 | School Sport Victoria Website Redevelopment | Education | Management of Process | The project will deliver a modern, secure website to centralise all school sports program information, delivering a comprehensive school sport program information portal to primary and secondary students across Victoria | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-21 | 2025-09-15 |  | 2025-09-15 | 0 |  | 2025-09-30 |  | 2026-04-24 | 2026-07-01 | 1200000 |  |  | Green | Green | Green | Green | The project is GREEN and is tracking to plan, ready for delivery on 1 July 2026. End date amended and approved by Governance group to meet business requirements and support successful implementation.
Q4 25-26 | WorkSafe Victoria | WorkSafe | 4196 | Information Security and Management Uplift | Employment, Skills and Workplace | Records Management ,Security Management | WorkSafe Victoria is improving its information management security and cyber security maturity to strengthen governance, clarify ownership, uplift capability and reduce risk through targeted improvements and formal assessment. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-10-30 |  | 2025-10-30 | 189460 | 125073 | 2025-11-03 |  | 2026-11-30 |  | 1548186 | 1612573 |  |  | Green | Green | Green | On track
Q4 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4200 | Procurement @ DEECA – Digital Enablement | Business and Industry | Management of Process | This project will deliver a new technology solution to optimise procurement processes. The primary goal is to implement procurement forms to meet evolving requirements and ensure that updated framework elements are enabled through technology. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid – Waterfall and Agile | 2025-04-07 | 2025-04-07 |  | 2025-08-06 | 0 |  | 2025-08-06 |  | 2026-08-31 |  | 3176852 |  |  |  | Green | Green | Amber | The launch of the technical procurement solution was successfully completed. However, technical issues uncovered following go-live have impacted the delivery schedule and are currently being addressed.
Q4 25-26 | Court Services Victoria | CSV | 4201 | County Court of Victoria Audio-Visual (in-court technology) systems upgrade (2025-29) | Law and Justice | Collaboration ,Communication | Upgrading Audio Visual systems across the County Court of Victoria to deliver modern, integrated solutions for video conferencing, evidence display, and remote participation in 100 spaces, including 53 courtrooms and 39 jury rooms. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial) |  | Waterfall and Agile | 2023-11-03 | 2024-10-01 |  | 2024-10-01 | 14530 |  | 2024-10-01 |  | 2029-10-16 |  | 17039154 |  |  |  | Green | Green | Green | Working with internal and external stakeholders on courtroom rollout.
Q4 25-26 | Court Services Victoria | CSV | 4202 | Case and List Management System (CLMS) Stabilisation Project | Law and Justice | Development and Integration | The project will stabilise and upgrade the existing technology for CLMS and its associated systems, while consolidating and enhancing critical functionalities across County Court of Victoria (CCV) digital infrastructure. | Initiated |  |  | PMBoK | 2024-09-01 | 2026-03-31 | 2026-09-30 |  | 0 | 580000 | [11 empty] | Further analysis is ongoing for the CLMS project and will continue into the next quarter.
Q4 25-26 | Yarra Valley Water | YV Water | 4203 | STP Firewalls Replacement and SD-WAN Implementation | Environment and Water | Security Management ,Systems Management | This project replaces EOL firewalls at remote sites and modernises our IT/OT network with SD WAN, delivering a more secure, reliable, high performance network that improves business continuity and simplifies management. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-10-06 | 2026-02-12 | 2025-11-20 | 2025-11-20 | 60000 |  | 2026-02-12 |  | 2026-10-30 |  | 1403000 |  |  |  |  | Green | Green | Extensive prep work and dependencies requiring a revised rollout schedule. Current projections show completion of firewalls replacement by mid-October 2026 instead of the desired mid-August date.
Q4 25-26 | Yarra Valley Water | YV Water | 4206 | MAINTENANCE SERVICES MOBILISATION | Environment and Water | Development and Integration | This project delivers the digital and system integration foundations required to enable the safe, effective, and coordinated transition to the new Maintenance Services Contracts with new Delivery Partners. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-01-01 | 2025-12-31 | 2025-12-22 | 2025-12-22 | 2125163 |  | 2026-01-01 |  | 2026-11-30 |  | 3158037 |  |  |  |  | Green | Green | Overall project is on track with a slight increase to budget forecasted. Commenced end-to-end system integration testing with delivery partners
Q4 25-26 | Melbourne Water | MELB Water | 4208 | AV Upgrade | Environment and Water | Communication | This project aims to deliver AV upgrades at operational sites across Melbourne Water. | Closed - Completed | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) | 2026-06-30 | PMBoK | 2025-11-07 | 2026-02-02 |  | 2026-03-27 | 0 |  | 2026-03-27 |  | 2026-07-01 |  | 1546982 |  |  |  |  | Amber | Green | As at 20260630: Project is complete.
Q4 25-26 | Melbourne Water | MELB Water | 4210 | IT Storage Refresh | Environment and Water | Data Management | Current data centre storage and connectivity are end of life in 2026. Project will deliver upgraded storage infrastructure that meets current needs and can scale to support future growth. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2025-10-08 | 2026-02-16 | 2026-05-01 | 2026-05-26 | 0 |  | 2026-05-26 |  | 2026-08-07 |  | 3223797 | [5 empty] | Green | As at 20260630: Business case was approved, project on track.
Q4 25-26 | Melbourne Water | MELB Water | 4211 | Telemetry Network | Environment and Water | Systems Management | Current network services will be decommissioned in 2027, this project is to upgrade to scale and support future growth. | Initiated |  |  | PMBoK | 2025-12-08 | 2026-04-08 | 2026-09-09 |  | 0 | [12 empty] | As at 20260331: Business Case to be submitted.
Q4 25-26 | Department of Health | DH | 4212 | Data Centre Exit | Health | Systems Management | Exit the Burwood and Ballarat Data Centres by migrating workloads to alternate data centres, including network establishment, VMware to IaaS migration and SAN/Oracle relocation, to meet June 2026 exit objectives, avoiding increased hosting costs. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-11-10 | 2026-02-27 | 2026-03-31 | 2026-03-31 | 0 |  | 2026-03-31 |  | 2026-06-25 | 2026-11-30 | 2420000 |  |  |  |  | Amber | Green | Project progressing to cost and revised schedule.
Q4 25-26 | Melbourne Water | MELB Water | 4213 | Enterprise WAN Refresh | Environment and Water | Systems Management | SD‑WAN integrates all network connections to optimise bandwidth and improve performance. This pilot will validate the technology before a full roll-out that will replace outdated hardware and enhance network management. | Initiated |  |  | PMBoK | 2025-10-23 | 2026-05-29 | 2026-08-03 |  | 0 | [12 empty] | As at 20260630: Business Case under development
Q4 25-26 | Melbourne Water | MELB Water | 4214 | GIS Platform Upgrade | Environment and Water | Systems Management | Major upgrade of Melbourne Waters Geographic Information System to the latest supported version. | Initiated |  |  | PMBoK | 2025-10-25 | 2026-09-30 |  |  | 0 | [12 empty] | As at 20260630: Project uncovered a key dependency and has been paused, CR approved and will re-mobilise Oct 26.
Q4 25-26 | Department of Education | DE | 4220 | Student Insight Platform Establishment and Digital Enrolment Product - Phase 3 | Education | Customer Relationship Management | Student Insight is a centralised enrolment and student administration platform, replacing paper-based processes for schools and families. The project will enhance and implement the Digital Enrolment Product across mainstream schools in the SEV & NEV | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2026-06-30 | Hybrid - Waterfall and Agile | 2025-07-01 | 2025-10-30 |  | 2025-10-30 | 0 |  | 2025-11-01 |  | 2026-06-30 |  | 11450000 |  |  |  | Green | Green | Amber | This project phase will formally close at the end of June 2026 with the technical deployment and change activities successfully supporting enrolment processes across North East & South East regions. The AMBER status reflects the ongoing work in integrating data systems. Support for foundation enrolment expansion into North West & South West regions will continue through operational and service delivery teams.
Q4 25-26 | Department of Education | DE | 4221 | Justice Education System Portal | Education | Analyses and Statistics ,Systems Management,Tracking and Workflow | This Portal brings together various systems and platforms to create a scalable system for justice education. This is to create a well-connected Portal to track and monitor young people at risk or involved in youth justice & those presenting to police | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - Waterfall and Agile | 2025-05-01 | 2025-05-30 |  | 2025-06-25 | 267000 |  | 2025-11-01 | 2026-05-11 | 2027-06-30 |  | 2500000 | 4333100 |  |  | Green | Green | Green | The project is GREEN and tracking to plan. Detailed design for the Portal solution was approved to commence in May 2026, with the delivery partner in preparation for deployment in Financial Year 2026-27.
Q4 25-26 | Department of Education | DE | 4222 | VRQA Victorian Home Schooling Register Replacement | Education | Customer Relationship Management | The VRQA is redeveloping the Home Schooling Register to meet current technology and security standards to better support our business needs and improve efficiency across the organisation. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - Waterfall and Agile | 2025-05-16 | 2025-11-25 |  | 2025-11-25 | 0 |  | 2026-01-12 |  | 2027-05-31 |  | 1780000 |  |  |  |  | Green | Green | The project is GREEN and tracking to plan. Currently in the build phase, with user acceptance testing planned in Q1 2026-27.
Q4 25-26 | Development Victoria | Development Vic | 4223 | HRIS & Payroll solution | Property and Planning | Human Capital / Workforce Management | Human Resources and Payroll System implementation to improve operational efficiencies, improve data and reporting quality, reduce risk and improve the employee experience. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-08-18 |  | 2025-08-18 | 0 |  | 2025-08-18 |  | 2027-03-31 | 2027-08-31 | 2551166 | 1383000 |  |  | Green | Amber | Green | The project baseline has been updated following contract execution, with implementation mobilisation now in progress.
Q4 25-26 | Department of Health | DH | 4224 | Briefings Solution Implementation | Health | Communication,Management of Process ,Tracking and Workflow | The DH & DFFH Briefings Solution will manage ministerial & secretarial briefings/correspondence, parliamentary questions, executive memos & other materials requiring executive approval, improving collaboration & efficiency in correspondence approval. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-01 | 2025-10-10 |  | 2025-10-10 | 684600 |  | 2025-10-13 |  | 2026-06-30 | 2026-07-31 | 2509210 | 2694500 |  |  | Green | Green | Amber | Initial release of the Briefing solution, BriefConnect, was successfully delivered in March 2026. Project is amber as final release has been delayed. Project is expected to complete in the next reporting period.
Q4 25-26 | Department of Government Services | DGS | 4225 | Working With Children Check Employer Platform and Training | Government and Economy | Development and Integration | Provide an improved online and offline experience that supports the revised regulatory framework and further strengthens the Working with Children Check. | Delivery | Compliance (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-10-08 | 2026-03-04 | 2026-04-20 | 2026-04-20 | 200000 | 540000 | 2026-04-20 |  | 2026-09-30 |  | 3585000 | [5 empty] | Green | Business Case approved with the project moved into execution in April 2026.
Q4 25-26 | Barwon Region Water Corporation | BR Water | 4226 | C1069 - TechOne CiA Transition | Environment and Water | Financial Management | This project aims to maximise the value of the TechnologyOne platform by migrating the remaining Supply Chain Management (SCM) module from Ci to CiA platform. | Closed - Completed | Risk Reduction (Non Financial) | 2026-06-30 | Waterfall | 2024-06-02 | 2025-09-30 |  | 2025-10-30 | 400877 |  | 2025-11-09 |  | 2026-04-30 |  | 781253 | 887329 |  |  | Green | Green | Green | Project has successfully implemented and closed.
Q4 25-26 | Victorian Funds Management Corporation | VFMC | 4229 | E28 ¦ Modern Cloud Infrastructure | Business and Industry | Systems Management | This project aims to strengthen VFMC resilience through decommissioning data centers and expanding usage of Cloud services, delivering a modern, reliable secure and flexible Cloud Platform. | Delivery | Cost Reduction (Financial) |  | Agile | 2025-12-01 | 2026-04-30 |  | 2026-04-30 | 0 |  | 2026-06-01 |  | 2028-06-30 |  | 1500000 | [5 empty] | Green | On track
Q4 25-26 | Department of Transport and Planning | DTP | 4230 | Workspace Management System | Transport and Vehicles | Assets/Materials Management | Deployment of DTP-wide desk booking system to reduce operational cost pressures, eliminate duplicated administrative burden and provide an easier solution for staff to book desks to help better manage office utilisation. | Closed - Completed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) | 2026-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-06-01 | 2025-06-30 |  | 2025-06-30 | 0 |  | 2025-10-01 |  | 2026-06-30 |  | 1855000 |  |  |  |  | Green | Green | The project is tracking green and the delivery is now complete.
Q4 25-26 | Department of Government Services | DGS | 4235 | DGS & DTF Digital Record and Information Management Service (DRIMS) | Government and Economy | Document Management | Enabling DRIMS for DGS and DTF to mitigate technical risk, achieve record management compliance for DGS, build a single service for the cluster, release significant annual cost savings. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2026-02-23 | 2026-06-30 |  |  | 0 | [12 empty] | Project finalising initiation
Q4 25-26 | WorkSafe Victoria | WorkSafe | 4237 | Amusement Structures Reform Implementation | Employment, Skills and Workplace | Systems Management | The project will implement the Amusement Structures Reform and the licensing management system uplift required to enable validation of compliance and collection of data to support prevention of injuries and fatalities involving amusement rides. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2025-03-05 | 2025-07-03 |  | 2025-07-03 | 0 |  | 2025-08-02 |  | 2026-11-30 |  | 1576553 |  |  |  |  | Green | Green | On track
Q4 25-26 | Department of Education | DE | 4238 | Student Insight LOOKOUT Technology Improvements Project | Culture, Sport and Recreation | Collaboration ,Customer Relationship Management | Integrate Student Insight with the Client Relationship Information System (Department of Families, Fairness and Housing) to share out-of-home care data in real time, giving schools accurate information to support student wellbeing. | Delivery | Social Improvement (Non Financial) |  | Agile | 2025-07-18 | 2025-10-21 |  | 2025-10-21 | 300000 |  | 2026-01-05 |  | 2026-06-26 |  | 1300000 |  |  |  |  | Green | Amber | The project is AMBER and is being re-baselined to incorporate expanded data sharing requirements.
Q4 25-26 | Department of Education | DE | 4239 | ServiceNow Human Resources Service Delivery | Education | Human Resources | Delivery of a specific Human Resources module on the ServiceNow platform to enable the end-to-end management of Human Resource cases for HR Schools HR Corporate and Early Learning Victoria. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-28 | 2025-09-25 |  | 2026-03-17 | 586363 |  | 2026-03-17 |  | 2026-07-17 |  | 1936697 |  |  |  |  | Green | Green | Implementation on track as per the project plan.
Q4 25-26 | Department of Education | DE | 4241 | Securing Connected Learners Program - Migration - Phase 3 | Education | Development and Integration ,Security Management ,Systems Management | This project will strengthen school cyber resilience by migrating M365/Google tenancies, improving identity services, expanding authentication and deploying enhanced child safety and content controls to deliver secure digital environments. | Closed - Completed | Cost Avoidance (Financial), Risk Reduction (Non Financial) | 2026-06-30 | Waterfall | 2025-06-01 | 2025-06-30 |  | 2025-06-30 | 0 |  | 2026-01-05 |  | 2026-06-30 |  | 20950000 | 21658556 |  |  |  | Amber | Amber | The project has migrated M365/Google tenancies to the identified tranche of schools, improved identity services, authentication processes and other controls. The Network and Identity improvement projects delivering uplifted capability have been moved into the next phase of the program commencing July 2026, which has resulted in the AMBER assessment.
Q4 25-26 | Melbourne Water | MELB Water | 4242 | Replacement of Project Management System | Environment and Water | Management of Process | Replacement of end of life technology due to Microsoft retiring Access Control Services current system and customised modules will no longer work. Project will move to a scalable platform. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-12-09 | 2026-03-30 |  | 2026-03-30 | 0 |  | 2026-03-30 |  | 2026-07-01 | 2026-07-27 | 2961616 |  |  |  |  | Amber | Amber | As at 20260630: user acceptance testing approved in June, project to complete post verification testing. Amber status due to risks around outstanding technical items to be approved before final business sign off to go live in Q1 FY26/27
Q4 25-26 | Melbourne Water | MELB Water | 4243 | GIS Architecture Rationalisation | Environment and Water | Systems Management | Remediate system limitations that have impacted operational efficiency and service reliability by implementing architecture improvements. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-09-06 | 2024-12-20 |  | 2024-12-20 | 0 |  | 2024-12-20 |  | 2026-07-03 |  | 1198980 |  |  |  |  | Green | Green | As at 20260630: Overall project remains on track with delays to phase completion affecting EOFY forecasting. Whole of life budget is not impacted.
Q4 25-26 | Department of Families, Fairness and Housing | DFFH | 4247 | Maintenance Assurance Audit Tool | Community Services | Reporting | Implement a portable and integrated audit system to manage and report the findings of completed maintenance work of public housing by officers whilst onsite, enabling more inspections to be conducted and faster resolution of issues. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2025-11-28 | 2025-11-28 |  | 2025-11-28 | 0 |  | 2026-02-02 |  | 2026-06-30 | 2026-07-31 | 1283018 |  |  |  |  | Green | Green | Project progressing to cost and revised schedule.
Q4 25-26 | Department of Families, Fairness and Housing | DFFH | 4248 | Enhancing the Victorian Emergency Management Personal Hardship Program IT System | Community Services | Customer Relationship Management | Enhance the Emergency Management Personal Hardship IT System to integrate with Department of Government Services, streamline online lodgement of hardship and emergency accommodation requests and improve finance systems processes and reporting. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2025-12-10 | 2026-06-02 |  | 2026-06-02 | 185403 |  | 2026-06-02 |  | 2028-06-30 |  | 3743597 | [5 empty] | Amber | Project is progressing but is Amber due to resource constraints placing pressure on schedule.
Q4 25-26 | WorkSafe Victoria | WorkSafe | 4249 | Domino Platform Upgrade | Employment, Skills and Workplace | Systems Management | Infrastructure Life Cycle Management to upgrade the Domino platform and Windows Server operating system, maintaining infrastructure currency, reducing operational risks, and enabling new functionality with improved performance and stability. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-06-30 | 2026-01-30 |  | 2026-03-19 | 244023 |  | 2026-03-23 |  | 2027-12-31 |  | 1225700 |  |  |  |  | Green | Green | On track
Q4 25-26 | Department of Health | DH | 4250 | Health Technology Services Data Centre Establishment | Health | Systems Management | With current data centre arrangements terminating in 2028, project will deliver new data centre infrastructure, network connectivity & firewalls to ensure continuity of critical state-wide digital health systems managed by Health Technology Services. | Initiated |  |  | PRINCE2 | 2026-01-02 | 2026-05-29 | 2026-08-31 |  | 0 | 240000 | [11 empty] | Planning and mobilisation activities are in progress.
Q4 25-26 | Department of Education | DE | 4252 | Senior Secondary Pathways Reform Division (SSPRD) Technology Roadmap 25/26 | Education | Customer Relationship Management,Forms Management | SSPR Digital Platform consists of 4 applications (Work Based Learning, School Exemptions, Industry Engagement and VET Delivered to School Students) which support schools to deliver pathway reform and increase access to career education for students. | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2025-02-01 | 2025-05-31 |  | 2025-06-24 | 0 |  | 2025-07-01 |  | 2026-12-31 | 2026-07-17 | 10120000 |  |  |  |  | Green | Amber | The project is AMBER with one subcomponent tracking behind schedule.
Q4 25-26 | Greater Western Water Corporation | GW Water | 4254 | Return To Service Plan | Environment and Water | Communication,Data Management,Records Management ,Investment Management | The project will support the delivery of GWW's Return to Service Plan, enabling system enhancements to support effective, accurate, compliant and reliable customer billing. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial) |  | Waterfall | 2025-07-01 | 2025-10-30 |  | 2025-10-30 | 433129 |  | 2025-10-30 |  | 2026-03-31 | 2026-06-30 | 18091026 |  |  |  |  | Red | Amber | During FY26, significant progress was made in restoring billing services, strengthening customer support, improving compliance capability and establishing the foundations for longer-term operational improvement. Key achievements in Q4 includes reinstating direct debit in full functionality and bringing the majority of customers back to a regular billing cycle. While progress has been made, we are continuing to work through technical and system issues while also revising the scope of work, which has resulted in some delays. Remediation work will continue into FY27.
Q4 25-26 | Fire Rescue Victoria | FRV | 4255 | Cyber Uplift Program | Emergencies and Safety | Security Management | The Cyber Uplift Program strengthens FRV’s resilience by enhancing cybersecurity capabilities, addressing risks, and modernising systems to safeguard operations, protect critical data, and ensure community confidence in our emergency services. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - Waterfall and Agile | 2025-07-01 | 2025-12-31 |  | 2025-12-31 | 257125 |  | 2026-01-01 |  | 2028-06-30 |  | 14785796 |  |  |  |  | Green | Green | The project is tracking well against scope, budget and schedule.
Q4 25-26 | Safe Transport Victoria | STV | 4256 | Consolidated Data Platform Stage 3 | Transport and Vehicles | Data Management | The Consolidated Data Platform (CDP) delivers on ST Vic's aim to be an intelligence-led regulator by centralising all organisational data to share securely with industry partners and the Victorian Government. | Closed - Completed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2026-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-11-01 | 2024-12-06 |  | 2025-02-03 | 298 |  | 2025-04-01 |  | 2026-04-02 | 2026-06-30 | 1421000 | 1228495 |  |  |  | Green | Green | Project closed and transition to BAU data platform team complete.
Q4 25-26 | Parks Victoria | PARKSVIC | 4257 | Data Center Infrastructure replacement | Environment and Water | Systems Management | The project will replace or remediate end-of-life IT infrastructure in Parks Victoria-managed data centres to maintain reliability, security and supportability, and reduce ageing infrastructure risks. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-11-03 | 2026-04-30 | 2026-09-15 |  | 0 | [12 empty] | During Q4 FY25/26, the project was in the initiation stage. Purchasing activities were undertaken, and vendor discussions commenced to inform the project's direction and priorities.
Q4 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4258 | Digital Program - Phase 1 | Community Services | Communication,Content Management,Document Management ,Records Management | The program will deliver enhancements to DEECA’s digital products that increase the adoption and maturity of digital technologies, processes, and practices, enabling better service experiences for both the community and DEECA staff. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2026-04-01 | 2026-10-30 |  |  | 0 | 250000 | [11 empty] | The project is currently in the planning phase, with delivery expected to commence in Q2 FY2026-27.
Q4 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4259 | DEECA Network Uplift | Employment, Skills and Workplace | Communication | The project aims to modernise DEECA’s site connectivity through the implementation of next-generation Wi-Fi and switching services, improving network resilience across critical locations and supporting cloud adoption and data centre exit strategies. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2026-03-02 | 2026-08-31 |  |  | 1030000 | [12 empty] | The project is currently in the planning phase, with delivery expected to commence in Q1 FY 2026-27.
Q4 25-26 | CenITex | CenITex | 4265 | Cloud Migrations labour FY25-26 | Government and Economy | Development and Integration | To support migrations to AWS Cloud that Cenitex have invested and built as part of the Multi Cloud Roadmap, and support Cenitex to make use of the AWS funding for professional services to migrate workloads to cloud. | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | PRINCE2 | 2026-05-14 | 2026-05-14 |  | 2026-05-14 | 0 |  | 2026-05-21 |  | 2026-08-31 |  | 1342183 | [5 empty] | Green | Project is tracking to plan and schedule.
Q4 25-26 | Victorian Convention and Event Trust | VCET | 4266 | ICT Server Environment Refresh | Business and Industry | Assets/Materials Management | This project will implement new server hardware and software to monitor the environment. By replacing obsolete infrastructure it will reduces the risk of system outages It will support planned system growth to enable efficient business processes. | Delivery | Cost Avoidance (Financial), Increased Quality (Non Financial) |  | Waterfall | 2026-05-03 | 2026-06-01 |  | 2026-06-09 | 0 |  | 2026-06-15 |  | 2026-10-05 |  | 1892161 | [5 empty] | Green | Hardware has been purchased and technical design complete
Q4 25-26 | Austin Health | AH | 4268 | Ambulatory Services Alignment Project (ASAP) | Health | Document Management ,Records Management | Transition of ambulatory, community mental health, and specialist clinic documentation from paper/SMR into Cerner to establish a single, integrated patient record and reduce hybrid workflow risks. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2026-04-06 | 2026-07-19 |  |  | 0 | [12 empty] | - Business Case completed and funding secured. - Scoping undertaken. - Recruitment into technical roles completed. - Governance established and scheduled. - Project plan and timelines established
Q4 25-26 | Yarra Valley Water | YV Water | 4269 | SharePoint Online intranet upgrade | Environment and Water | Collaboration ,Content Management,Document Management ,Knowledge Management ,Search | Implement SharePoint Online intranet, replacing the legacy platform. The project will enhance content management, collaboration & search capabilities, providing staff with improved access to information. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-30 | 2026-04-03 |  | 2026-04-07 | 411480 |  | 2026-04-07 |  | 2026-09-25 |  | 749020 | [5 empty] | Green | The project is tracking well against scope, budget and schedule.
Q4 25-26 | Department of Education | DE | 4271 | InductEd 2.0 | Education | Customer Relationship Management | InductEd 2.0 is a Salesforce application supporting the Career Start program, improving early career teacher induction through onboarding, mentor allocation, interaction tracking, and event management to strengthen professional practice, mentoring an | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2025-10-20 | 2026-04-20 |  | 2026-04-20 | 0 |  | 2026-05-11 |  | 2026-10-02 |  | 2471905 | [5 empty] | Green | The project is GREEN and tracking to plan without issues.
Q4 25-26 | Department of Education | DE | 4272 | Securing Connected Learners Program - Migration - Phase 4 | Education | Data Management | This project will strengthen school cyber resilience by migrating M365/Google tenancies, improving identity services, expanding authentication and deploying enhanced child safety and content controls to deliver secure digital environments. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2026-05-05 | 2026-05-05 |  |  | 0 | [12 empty] | Project is in initiation stage.
Q4 25-26 | Department of Education | DE | 4282 | Grants Management Solution | Education | Financial Management | Delivery of a digital solution to manage and administer all departmental Grants. This project will significantly improve business processes and reduce risk as it seeks to unify disparate systems and processes. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2026-03-02 | 2026-04-16 |  |  | 385000 | [12 empty] | This Project is in initiation stage.
Q4 25-26 | Department of Education | DE | 4283 | VCAA Digital Transformation Program | Education | Customer Relationship Management | The project will deliver a detailed technology roadmap and commence IT reform by upgrading critical infrastructure and improving security. This will lay the foundation to enable future investments to deliver a modern application suite. | Initiated |  |  | Agile | 2026-02-01 | 2026-05-20 |  |  | 50000 | [12 empty] | This Project is in initiation stage.
Q4 25-26 | Eastern Health | EH | 4285 | EMR Mobility and Enterprise Extension (Subacute) | Health | Development and Integration | The EMR Mobility and Extension (Subacute) Program aims to expand the EMR footprint at Peter James Centre, Wantirna Health, Healesville Hospital and Yarra Ranges Health, to consistent and secure patient data across Eastern Health | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2026-04-01 | 2026-05-29 |  | 2026-05-29 | 0 |  | 2026-05-29 |  | 2026-10-30 |  | 4098875 | [5 empty] | Green | EMR Mobility and Enterprise Extension program has embarked on extending EMR capabilities across Sub Acute Eastern Health Sites. Currently completing EMR rollout at Peter James Centre and Wantirna Health while in parallel preparing remaining site rollout later this year
Q4 25-26 | WorkSafe Victoria | WorkSafe | 4287 | Authorised Assessor and Compliance Unit (AACU) Customer Relationship Management (CRM) Build | Employment, Skills and Workplace | Customer Relationship Management | This project will deliver a digital end-to-end audit management tool with guided compliance assessment for Registered Training Organisations and Independent Assessors that will enable WorkSafe to track and monitor assessments. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-11-04 | 2026-04-03 |  |  | 150949 | [12 empty] | Business case approved on 30 June 2026. Delivery kicking off in Q1 2026-27.
Q4 25-26 | WorkSafe Victoria | WorkSafe | 4288 | Licensing Payments Review | Employment, Skills and Workplace | Customer Relationship Management | This project will implement a payment solution to process replacements of lost, stolen or damaged High Risk Work Licences, ensuring compliance with regulatory requirements, improving financial sustainability and creating a seamless user experience. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2026-01-27 | 2026-06-29 |  |  | 152654 | [12 empty] | Business case approved on 30 June 2026. Delivery kicking off in Q1 2026-27.
Q4 25-26 | WorkSafe Victoria | WorkSafe | 4289 | Source to Contract Software Solution | Employment, Skills and Workplace | Financial Management | This project will procure and implement a fully hosted and managed Source to Contract software solution to automate the procurement process from sourcing, supplier management, and contract management to reporting and dashboards. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-10-06 | 2026-04-30 |  | 2026-05-15 | 213266 |  | 2026-05-15 |  | 2027-07-30 |  | 2642328 | [5 empty] | Green | On track
Q4 25-26 | South East Water | SE Water | 4290 | Project SAFE | Environment and Water | Customer Relationship Management | This project focuses on enhancing customer identity verification and strengthening the security of customer interactions across digital and service channels. Key initiatives include improvements to customer authentication processes, the introduction | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2025-10-01 | 2025-10-31 |  | 2025-10-31 | 0 |  | 2025-11-03 |  | 2026-10-09 |  | 3347068 | [5 empty] | Green | Project is reporting GREEN following several major uplifts to the mySEW customer portal including Multi-Factor Authentication (MFA) and increase in password complexity. This will improve the customer's registration experience while increasing the security of the portal.
Q4 25-26 | Transport Accident Commission | TAC | 4295 | Statutory Insurance Core Platform - Claims Platform Modernisation | Transport and Vehicles | Systems Management | The program will deliver a modern cloud-based claims platform, replacing TAC’s end-of-life Avanti system and ensuring service continuity, operational resilience, improved stakeholder experience, and reduced compliance and cyber risk. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2026-06-30 |  |  | 0 | [12 empty] | The program formally commenced following Board approval of the Business Case in April. Since then, a dedicated executive leadership team has been appointed and key program resources mobilised, establishing the governance, leadership and delivery capability required to support successful program execution.
Q4 25-26 | Department of Health | DH | 4296 | Health Technology Services Clinical EMR Data Centre Exit | Health | Systems Management | Migrate the Electronic Medical Record (EMR) to a cloud hosting service for five Victorian Public Health Services to ensure continuity of service post current data centre arrangements terminating in 2028. | Initiated |  |  | PRINCE2 | 2026-05-29 | 2026-09-30 |  |  | 0 | [12 empty] | Planning and mobilisation activities are in progress.
Q4 25-26 | Eastern Health | EH | 4298 | SuccessFactors EC Payroll and Performance & Goals Management implementation | Health | Human Capital / Workforce Management ,Human Resources | Implement SF EC Payroll -for integration between HR and Payroll operations resulting in more automation and less manual intervention with single source of truth for business reporting. Significant ongoing savings to ongoing HR systems licensing. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-12-02 | 2025-10-31 |  | 2025-10-31 | 0 |  | 2026-04-01 |  | 2027-06-30 |  | 3111615 | [5 empty] | Green | Project works commenced with 1st iteration of payroll system now having been tested. Iteration 2 build commencing with partner.
Q4 25-26 | Workplace Injury Commission | WIC | 4299 | Microsoft Platform Project | Law and Justice | Systems Management | Implement WIC's own Microsoft 365 platform to enable autonomy and support the new case management system improving efficiency in resolving workplace injury disputes for Victorian workers. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2026-01-12 | 2026-06-30 |  |  | 429000 | [12 empty] | Business Case developed and expected approval at end of Q4 FY25/26. Currently evaluating responses to the RFP for implementation, ongoing support and licensing services, with a decision anticipated early FY27.
Q4 25-26 | State Revenue Office | SRO | 4300 | Identity Management | Government and Economy | Development and Integration | The project will deliver a centralised way to manage user access across key business systems, streamlining and securing access to internal applications and external portals and ensuring the right people have the right access at the right time. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2026-05-01 | 2026-07-30 |  |  | 331913 | [12 empty] | Initiation phase tasks are on track
Q4 25-26 | Department of Health | DH | 4301 | Victorian Medicines Formulary – Digital Formulary Platform | Health | Content Management | The VMF Digital Platform will publish statewide formulary content, and manage formulary and Individual Patient Use (IPU) submissions and decisions to support safer, consistent, value-based medicines use. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2026-04-01 | 2026-12-31 |  |  | 0 | [12 empty] | As at 30 June 2026, initiation is progressing with governance and funding arrangements in place. Requirements, worfklows, concept brief and benefits planning have been drafted.
Q4 25-26 | Goulburn Valley Region Water Corporation | GVR Water | 4302 | ESRI ARC GIS | Environment and Water | Assets/Materials Management | Modification of the GIS ESRI system - taking it from its legacy functionality used for the MyData and Focus systems and integrating it with Maximo . Follows the decision by the Vendor to remove support for and access to and retire MyData. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-09-25 | 2026-03-10 |  | 2026-03-10 | 92374 |  | 2026-03-11 |  | 2026-08-31 |  | 1315551 | [5 empty] | Green | Project is on track to deliver the required benefits as scheduled.
Q4 25-26 | Goulburn Valley Region Water Corporation | GVR Water | 4303 | MyData Decommissioning | Environment and Water | Assets/Materials Management | Decommissioning of the MyData system. Replacement of the MyData system and modification to other dependant systems following the decision by the Vendor to remove support for and access to and retire MyData. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-09-29 | 2026-03-10 |  | 2026-03-10 | 92374 |  | 2026-03-11 |  | 2026-08-31 |  | 1116648 | [5 empty] | Green | The project is on track to deliver benefits according to schedule.
Q4 25-26 | Yarra Valley Water | YV Water | 4304 | Migration to Multicloud | Environment and Water | Systems Management | Migrating workloads to a new cloud platform will reduce annual operating costs by approximately 22% while improving resilience through a multi-zone architecture with automated failover, data replication, and continuous service during outages. | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2026-04-01 | 2026-04-17 |  | 2026-04-17 | 0 |  | 2026-05-01 |  | 2027-12-31 |  | 1126200 | [5 empty] | Green | Project has commenced delivery
Q4 25-26 | Yarra Valley Water | YV Water | 4305 | GIS Suite Replacement | Environment and Water | Assets/Materials Management,Development and Integration | The project aims to implement a modern GIS platform that delivers enhanced security, improved usability, stronger integration capabilities, and a product roadmap aligned with industry standards and the organisation's future business objectives. | Initiated |  |  | PRINCE2 | 2025-09-01 | 2027-06-30 |  |  | 3471860 | [12 empty] | The project has successfully completed the initial assessment to evaluate the viability of the current state GIS platform and identify the options for the future-state solution. The program is now progressing through governance and internal endorsement activities, including architecture review, and investment planning, while undertaking preliminary project planning.
Q4 25-26 | Yarra Valley Water | YV Water | 4306 | HR System & Payroll Solution | Environment and Water | Human Capital / Workforce Management | Implement a new Human Resources system with position-based architecture and migrate on-prem payroll platform to online service, uplifting operating model to deliver future-ready workforce, operational efficiencies and enhanced user experience. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-11-01 | 2026-09-30 |  |  | 1395775 | [12 empty] | Project has successfully achieved delivery of Stream1: Strategic Workforce Planning, Stream:2: Service Journeys design and Stream5: Migration of Payroll Online. These milestones are foundational elements in preparation to Core HR Delivery Business Case.
Q4 25-26 | Goulburn Valley Region Water Corporation | GVR Water | 4307 | Asset Management Information System Phase 2.1 | Environment and Water | Assets/Materials Management | Implement Service Delivery functionality within GVW's Asset Management Information System. Modernisation of GVW’s service delivery processes through implementing a new operating model supported by IBM Maximo. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-05-05 | 2026-03-10 |  | 2026-03-10 | 272359 |  | 2026-03-11 |  | 2026-08-31 |  | 1924180 | [5 empty] | Green | The project is on track to deliver benefits according to schedule.
Q4 25-26 | Greater Western Water Corporation | GW Water | 4310 | Growth & Development Capability Uplift | Environment and Water | Customer Relationship Management,Development and Integration ,Management of Process ,Tracking and Workflow | Modernisation of GWW's Development Services by replacing legacy systems with a cloud-based platform that enables straight-through processing customer serlf-service real-time applicationt tracking and a more scalabvle operating model | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-11-28 | 2025-09-30 |  | 2025-09-30 | 1119103 |  | 2025-09-30 |  | 2026-06-30 |  | 867217 | 3498422 |  |  |  |  | Red | Overall status is red due to delays in procurement following a revised procurement approach. The revised strategy is progressing through approvals. Budget remains on track with procurement expected to recommence minimising impacts to overall delivery
Q4 25-26 | Greater Western Water Corporation | GW Water | 4311 | PPM (PMO365) Capability Consolidation | Environment and Water | Data Management,Management of Process ,Tracking and Workflow | Implement a single Project Management platform across assets and technology to strengthen project governance, reporting, assurance and data quality, supporting end-to-end portfolio management and improved delivery across GWW. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-27 | 2023-09-27 |  | 2023-09-27 | 261331 |  | 2023-09-27 |  | 2027-06-30 |  | 2440234 | [5 empty] | Green | The project continued to expand on the Phase 1 solution, delivering self-hosting capability and progressing planned customisations. These enhancements improve platform resilience, operational efficiency and readiness for future capability growth.
Q4 25-26 | Greater Western Water Corporation | GW Water | 4312 | Enterprise Security Program | Environment and Water | Security Management ,Systems Management | Implement an enterprise cyber security program to strengthen GWW's security posture, improve cyber resilience, ensure alignemnt to the SOCI act and enhance the ability to detect, respond to and recover from evolving cyber threats. | Delivery | Cost Avoidance (Financial), Reputation (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-20 | 2024-09-24 |  | 2024-09-24 | 478666 |  | 2024-09-24 |  | 2028-06-30 |  | 1932694 | [5 empty] | Amber | The program has delivered 85% of ML1 controls aligning with the SOCI compliance assessment. Remaining ML1 controls are progressing, with ML2 planning underway. Delivery timeframes have been temporarily impacted due to complexities with the regular patching cycle.
Q4 25-26 | Greater Western Water Corporation | GW Water | 4313 | Network Communications Technology Uplift | Environment and Water | Routing and Scheduling,Security Management | Modernise GWW's network communications infrastructure to improve resilience, security and performance by consolidating network environments, replacing end-of-life infrastructure, improving remote site connectivity and supporting future business growt | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Waterfall | 2024-06-21 | 2024-10-10 |  | 2024-10-10 | 430872 |  | 2024-10-10 |  | 2026-06-30 |  | 1869228 | 2538665 |  |  |  |  | Amber | Replaced end-of-life firewalls and network infrastructure, consolidating OT and corporate networks to improve resilience, security and operational efficiency. Delivery experiences a temporary delay due to technical integration issues.
Q4 25-26 | Greater Western Water Corporation | GW Water | 4314 | Technology Platform Enhancements | Environment and Water | Routing and Scheduling,Systems Management | Modernise GWWs technology platforms and uplifting end of life hardware and improving resilience compliance and operational sustainability | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Waterfall | 2024-06-12 | 2024-07-31 |  | 2024-07-31 | 374663 |  | 2024-08-07 |  | 2028-06-30 |  | 1589327 | [5 empty] | Green | Completed consolidation of Western Region servers strengthened security between GWW and Western networks and decommissioned 2012 servers to align with Essential Eight requirements
Q4 25-26 | Parks Victoria | PARKSVIC | 4315 | End User Computing Refresh | Environment and Water | Assets/Materials Management | Replace end of life iPhone devices across the organisation. As per current staff data, a total of 1050 devices are requiring replacing. ​Replace end of life Laptop fleet across the organisation, including replacing all desktops with laptops (1100) | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-12-19 | 2026-04-09 |  | 2026-04-10 | 0 |  | 2026-04-20 |  | 2026-10-30 |  | 2802662 | [5 empty] | Green | The Mobile Devices and Laptop Refresh projects are progressing well and remain on track. Significant milestones have been achieved, including funding approvals, procurement activities, stakeholder engagement, and deployment planning. Rollout and deployment activities are underway, with ongoing efforts focused on completing delivery, supporting user adoption, and ensuring a smooth transition to new devices.
Q4 25-26 | State Revenue Office | SRO | 4318 | Digital Experience | Government and Economy | Development and Integration | The Digital Experience program will progressively enhance customer-facing services and communication channels, focusing on improved accessibility, consistency and self service. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2026-05-01 | 2026-06-30 |  |  | 887000 | [12 empty] | Initiation phase tasks are on track.
Q4 25-26 | Southern Rural Water | SR Water | 4320 | Finance and Billing Project | Environment and Water | Business Intelligence,Financial Management,Reporting ,Security Management | Deploy an integrated cloud finance and billing platform with Dynamics 365 Business Central, strengthening internal finance, billing and analytics capabilities, while improving governance, efficiency and readiness for future digital transformation. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2026-03-13 | 2026-11-30 |  |  | 1033140 | [12 empty] | The project is in Initiation, focused on establishing successful delivery foundations. Key activities include planning, stakeholder engagement, procurement preparation, and assessment of potential vendor. Tender preparations are underway, with market release expected in July 2026 to support vendor selection and progression to the next phase.
Q4 25-26 | Department of Transport and Planning | DTP | 4321 | Project BEDROCK | Transport and Vehicles | Organisational Management | Project BEDROCK delivers the I&T outcomes of the VIDA Community Safety Integration Program enabling the transition of former Community Safety Building Authority systems and data into VIDA through six projects across two coordinated workstreams. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2026-04-01 | 2026-06-30 |  |  | 118116 | [12 empty] | The program remained in the discovery and planning phase during this reporting period. Key activities focused on validating business needs, refining scope and requirements. The program plan and budget are being finalised for approval to support program commencement and progression into the delivery phase.