## PublicDataReport
Collection Period | Department/ Agency Name | Agency Short Name | Project ID | Project Title | Government Domain | ICT Project Category | Description | Stage | Benefit Category ( Benefit Type) | Date of Closure/ Postponement | PM Methodologies | Initiation Start Date | Planned Initiation End Date | Revised Initiation End Date | Business Case Approval Date | Planned Initiation Cost | Revised initiation Cost | Planned Delivery Start Date | Revised Delivery Start Date | Planned Delivery End Date | Revised Delivery End Date | Planned Delivery Cost | Revised Delivery Cost | Q2 24-25 | Q3 24-25 | Q4 24-25 | Q1 25-26 | Q2 25-26 (Current) | Reporting Comments
Q2 25-26 | Country Fire Authority | CFA | 2151 | CFA Mobile Data Capability and Short Status Messaging (SSM) | Emergencies and Safety | Communication | Development and deployment of the Mobility Data Capability (MDC) platform, incorporating Short Status Messaging, will deliver operational efficiency and safety benefits to members and the community. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2010-10-01 | 2012-07-01 | 2020-06-30 | 2020-07-01 | 0 | 45000 | 2020-07-01 |  | 2021-06-30 | 2027-06-30 | 2850000 |  | Amber | Amber | Amber | Amber | Amber | Due to escalated operational activity from the January 2026 Victorian Bushfires, CFA’s ICT team is prioritising the support of fire operations. A project status update will be provided for the following reporting period (Q3 2025-26).
Q2 25-26 | Court Services Victoria | CSV | 2452 | Courts Case Management System | Law and Justice | Tracking and Workflow | The CMS Project aims to procure and implement a new case management system for Magistrates’ Court and Children’s Court. The system will enable better information sharing between courts and other agencies, and provide better access to case information | Delivery | Efficiency/Productivity (Non Financial) |  | Project Management Excellence (PME) | 2016-07-01 | 2017-05-02 |  | 2017-05-02 | 0 |  | 2017-07-01 |  | 2022-06-30 | 2026-06-30 | 89200000 | 158650000 | Red | Red | Red | Amber | Amber | Criminal Release business readiness planning and deployment activities are continuing in the lead up to Go-Live in FY26 Q3.
Q2 25-26 | V/Line Corporation | V/Line | 2490 | Workforce management | Transport and Vehicles | Human Capital / Workforce Management | The Workforce management project will streamline the workforce management function and deliver an electronic rostering system that support V/Line to ensure it is able to meet daily staffing challenges to provide punctual and reliable train services | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-01-18 | 2018-02-28 | 2023-04-28 | 2023-05-01 | 250000 | 690251 | 2023-05-31 |  | 2026-07-31 | 2026-12-31 | 9680463 | 9992358 | Green | Green | Green | Green | Green | The overall health of the Project is on-track.
Q2 25-26 | South West Alliance of Rural Health | SWARH | 2597 | Barwon Health Rostering Project | Health | Management of Process ,Human Capital / Workforce Management ,Human Resources | This project will deliver a Rostering and Time & Attendance system to automate staff rostering processes, improving workforce utilisation, accuracy of resource allocation and delivery of patient care. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2017-07-19 | 2018-05-31 |  | 2018-06-08 | 110640 |  | 2018-07-11 |  | 2019-12-31 | 2026-06-30 | 3443281 | 3883649 | Amber | Amber | Red | Red | Red | Delivery of the Rostering and Time & Attendance system continues, enhancing workforce planning and operational efficiency, with over 3,000 staff onboarded in this period.
Q2 25-26 | Department of Justice and Community Safety | DJCS | 2851 | Digital Radio Upgrade Program - Stage 2 | Emergencies and Safety | Communication | This Program will transition Ambulance Victoria's (AV) regional comms off analogue radio system onto the State’s shared digital network and replace AV's regional radio fleet to provide secure comms and improve community safety and health outcomes. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2019-07-01 | 2019-07-02 |  | 2019-07-02 | 0 |  | 2019-07-03 |  | 2023-06-30 | 2026-06-30 | 70378000 | 117867000 | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q2 25-26 | South West Alliance of Rural Health | SWARH | 3003 | Barwon Health Community Electronic Medical Record | Health | Content Management,Data Management,Forms Management,Management of Process ,Security Management ,Systems Management,Tracking and Workflow | Implementation of an Electronic Health Record (EHR) solution for community nursing and community mental health to replace legacy systems | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PMBoK | 2018-03-01 | 2020-10-01 | 2022-04-07 | 2022-04-07 | 0 | 0 | 2022-04-11 |  | 2023-08-28 | 2026-08-17 | 6074206 | 10879302 | Amber | Red | Red | Amber | Amber | The rollout of the Community Electronic Medical Record solution continues, with the next phase focused on collaborative planning for Mental Health services.
Q2 25-26 | Fire Rescue Victoria | FRV | 3029 | Fire Rescue Portal | Emergencies and Safety | Systems Management | The project aims replace the existing operational applications that operate in silos to create an enterprise Fire Rescue Portal. This will provide a system to support an efficient and effective Operational Response System. | Closed - Terminated | Compliance (Non Financial) | 2024-03-31 | FRV Project Management Framework (PMF) | 2020-06-26 | 2020-12-16 |  | 2020-12-16 | 0 |  | 2020-12-17 |  | 2022-04-30 | 2025-06-30 | 2109000 |  | Amber | Amber | Red | Red | Red | The Fire Rescue Portal is awaiting administrative closure. No further work is currently underway, and future direction will be determined through ongoing strategic planning. Project reporting will now cease, as there will be no further project delivery activities.
Q2 25-26 | Fire Rescue Victoria | FRV | 3030 | Rostering and Shift Change | Emergencies and Safety | Systems Management | Purchase and implement a contemporary off the shelf Rostering and Shift Change system to replace multiple legacy systems. | Delivery | Efficiency/Productivity (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-06-26 | 2020-12-08 | 2021-09-14 | 2021-09-14 | 0 |  | 2021-09-15 |  | 2022-11-02 | 2026-06-30 | 3760000 | 4349947 | Amber | Amber | Amber | Green | Green | The project is tracking well against scope, budget and schedule.
Q2 25-26 | Wannon Region Water Corporation | WAN Water | 3091 | Billing and Customer Relationship Management Systems | Environment and Water | Customer Relationship Management | The replacement of the organisation's Billing and Customer Relationship Management Systems | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2020-01-01 | 2021-03-31 | 2022-06-24 | 2022-06-24 | 100000 | 650000 | 2022-08-15 | 2023-01-03 | 2024-03-22 | 2026-06-30 | 8200000 | 10251000 | Amber | Amber | Amber | Green | Green | The project reset is proceeding well with contract negotiations now underway.
Q2 25-26 | Goulburn Valley Region Water Corporation | GVR Water | 3130 | Billing and Customer Relationship Management System | Environment and Water | Customer Relationship Management | The project will replace Goulburn Valley Water's existing legacy billing and CRM systems with a modern, efficient and customer focused system | Initiated |  |  | Internal project management methodology | 2018-10-01 | 2021-06-30 | 2026-09-30 |  | 75000 | 487457 | [11 empty] | GVW has engaged a consultant to update and revise the Business Case and revisit the Sourcing Strategy for this project which is expected to be presented to The Board by 4th Quarter FY 25/26.
Q2 25-26 | Department of Justice and Community Safety | DJCS | 3168 | Post Sentence Authority Case Management System | Law and Justice | Tracking and Workflow | A case management system, crucial to sustainable operations and managing the risks associated with manual information flow, will be delivered. Real time information will be provided for informed decisions about offenders to uphold community safety. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2021-03-30 | 2021-07-15 | 2023-06-30 | 2023-06-30 | 150000 | 213455 | 2024-03-01 |  | 2025-12-31 | 2027-03-09 | 1878947 | 3274857 | Amber | Amber | Green | Green | Green | The project has undergone several iterations to ensure alignment with the overall organisational IT strategy and architecture. The completion of the latest discovery phase has resulted in a proposal variation. This included a re-baselined schedule, scope, and budget. Delivery activities for the latest iteration are planned to commence on 12 January 2026, with completion forecast for 9 March 2027.
Q2 25-26 | Department of Justice and Community Safety | DJCS | 3170 | Technology and resources to support Victoria’s fines system | Law and Justice | Systems Management | Delivery of next generation of fines platform by incrementally implementing functions into the business landscape to complement existing technology, ensuring better revenue collection, assistance for vulnerable Victorians and debtor-centric services. | Delivery | Customer Satisfaction (Non Financial), Increased Revenue (Financial) |  | Hybrid - Waterfall and Agile | 2021-03-10 | 2021-08-30 | 2021-12-16 | 2021-12-16 | 0 | 10367000 | 2022-01-09 | 2022-01-01 | 2025-06-30 | 2026-06-30 | 131615000 | 169961000 | Amber | Amber | Red | Red | Red | The project has continued its analysis for more efficient, alternative delivery approaches to meet the current timelines. The project is reporting a Red status due to schedule pressure, with the program's delivery velocity trailing forecast outcomes. The program has made some interim delivery approach adjustments, transitioning to shorter delivery cycles to improve throughput while the more detailed analysis continues.
Q2 25-26 | Department of Justice and Community Safety | DJCS | 3171 | Better Technology Tools Enabling Responsibility (BTTER) | Law and Justice | Development and Integration | Deliver applications to automate processes, reduce costs and risks associated with existing manual systems for safety benefits. Prison management systems will be uplifted, and rehabilitation and reintegration services will be enhanced. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2020-07-21 | 2021-02-19 |  | 2021-02-19 | 324114 |  | 2021-02-22 |  | 2023-06-30 | 2029-06-30 | 18868800 | 46682876 | Green | Green | Green | Green | Green | The program is tracking well against budget, schedule and scope. The adjusted budget profile reflects the system's ongoing development and plans to deploy it statewide to maximise the efficiency gains from increased workflow and process automation.
Q2 25-26 | Department of Government Services | DGS | 3199 | RTBA - Bond Management System Replacement | Community Services | Customer Relationship Management | This project will deliver an enhanced, updated solution to the Residential Tenancies Bond Authority legacy systems which are reaching end of life. The solution will ensure alignment to the business vision. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - Waterfall and Agile | 2021-04-12 | 2021-12-31 | 2021-12-31 | 2022-02-28 | 975000 | 1178280 | 2022-03-01 |  | 2023-06-30 | 2026-03-31 | 8900000 | 23850720 | Amber | Amber | Amber | Amber | Green | BMSR implementation was completed successfully. Enhancements and continuous improvement activity is underway as user feedback is being collected. New portable bonds functionality is in development and testing.
Q2 25-26 | Melbourne Water | MELB Water | 3214 | Strategic Relationship Management Tool Phase 1-2 | Environment and Water | Collaboration | To enhance delivery of business goals by improvement in business capabilities and relationship management tools to allow ongoing management and continuity of relationships to achieve strategic improvements in organisational goals. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2020-11-25 | 2021-08-01 |  | 2021-11-04 | 0 |  | 2021-11-04 |  | 2022-06-28 | 2026-05-28 | 3174023 |  | Green | Green | Green | Green | Red | As at 20251231: Business Case to be submitted post tender activity at which point the schedule will be rebaselined.
Q2 25-26 | Fire Rescue Victoria | FRV | 3254 | FRV Operational Station Connectivity | Emergencies and Safety | Assets/Materials Management | The implementation of the FRV network and FRV Station Turn Out systems across ex CFA stations. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-09-01 | 2021-03-23 |  | 2021-03-23 | 0 |  | 2021-03-25 |  | 2023-06-30 | 2026-08-17 | 16689890 | 18418852 | Green | Green | Amber | Green | Green | The project is tracking well against scope, budget and schedule.
Q2 25-26 | Department of Health | DH | 3261 | Health Information Exchange (HIE) | Health | Data Management,Development and Integration | Deliver a Health Information Exchange for secure sharing of pathology information at the Point of Care, and to facilitate planning for increased scope/budget in subsequent years to cater for all key clinical domains for VPHS state-wide rollout. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-06-01 | 2021-06-30 |  | 2021-06-30 | 0 |  | 2021-07-01 |  | 2025-06-30 | 2026-06-30 | 27220000 | 34850442 | Amber | Red | Red | Red | Amber | Project is progressing to a revised scope, cost and schedule. Steering Committee approved an increased scope that includes additional health services and clinical data. Project is reporting an Amber status due to earlier constraints in accessing required services.
Q2 25-26 | Melbourne Water | MELB Water | 3270 | Audio Visual Remediation | Environment and Water | Collaboration | Melbourne Water has a requirement to update Audio-Visual solutions in meeting rooms across multiple sites in Victoria that will provide a consistent experience for all users and allow for enhanced collaboration. | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2025-11-25 | PMBoK | 2021-07-08 | 2021-12-03 | 2022-01-20 | 2022-01-20 | 0 |  | 2022-01-20 |  | 2023-01-10 | 2025-11-05 | 2424764 | 1226338 | Green | Green | Amber | Amber | Amber | As at 20251231: Project is complete
Q2 25-26 | Peter MacCallum Cancer Centre | Peter MAC | 3278 | People and Payroll Transformation Program - Rostering Project | Health | Human Capital / Workforce Management ,Human Resources | The People Systems Program will deliver a Rostering solution which will increase efficiency and improve data security and integrity by eliminating paper time sheets and manual processes. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2021-09-01 | 2022-07-01 | 2023-08-02 | 2023-08-02 | 50000 | 500000 | 2023-08-03 |  | 2025-06-30 | 2026-06-30 | 6428267 | 11849537 | Green | Green | Green | Green | Red | System Integration Testing is continuing whilst missing functionality solutions are worked through, approved and delivered. Timeline currently remains as end of June 2026 but may be revised depending upon outcomes.
Q2 25-26 | Oral Health Victoria | OHV | 3280 | Electronic Oral Health Record (EoHR) | Health | Development and Integration | The Electronic Oral Health Record (EoHR) aims to replace and consolidate the legacy solution to deliver a single state-wide oral health record to support improved dental health outcomes in Victoria | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-04-01 | 2020-10-30 |  | 2020-10-30 | 390000 |  | 2021-09-22 |  | 2023-06-30 | 2027-06-30 | 9490000 |  | Amber | Amber | Amber | Amber | Amber | R2 planning and development of training and engagement plan has continued with the business and sector. Product development has commenced and recruitment of additional project resources was initiated.
Q2 25-26 | Department of Transport and Planning | DTP | 3312 | Smarter Roads Program - Timetable Systems Uplift | Transport and Vehicles | Content Management,Data Management,Systems Management | The objective of the project is to implement public transport timetabling solution for each mode which will improve business process and data accuracy, providing Victorian commuters consistent and timely information when using public transport. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-05-03 | 2021-12-30 | 2022-02-07 | 2022-02-07 | 0 |  | 2022-02-07 |  | 2023-03-31 | 2026-03-31 | 4739268 | 6716680 | Amber | Green | Amber | Red | Amber | The project status is reported as amber due to the delay against the initial schedule completion of end of September 2025. The project schedule has now been re-baselined and is now tracking completion against March 2026 end.
Q2 25-26 | Department of Transport and Planning | DTP | 3318 | Automatic Vehicle Monitoring Sustainment (AVMS) | Transport and Vehicles | Systems Management | Address key short-term challenges affecting Melbourne’s tram network through targeted initiatives to sustain the AVM system in the short-term while the Department continues to develop options for a future Tram Monitoring and Control (TMC) system. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PTV Investment Lifecycle | 2021-07-01 | 2022-04-29 | 2023-08-30 | 2023-08-30 | 1785000 | 0 | 2023-08-31 |  | 2025-06-30 | 2026-03-30 | 32018000 |  | Green | Green | Green | Green | Green | The AVMS On Board project is tracking well with the on-board tram installations of AVMS now extending across more than 40% of the E Class fleet.
Q2 25-26 | Fire Rescue Victoria | FRV | 3325 | Human Resources Information System (HRIS) | Emergencies and Safety | Human Resources | HRIS Project has the primary focus this year to address foundation data issues, collaborate with the Rostering and Shift Change project and build a business case for approval. Scope includes Payroll and HR | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | FRV Project Management Framework (PMF) | 2021-12-10 | 2022-06-30 | 2023-02-28 | 2023-02-28 | 0 | 0 | 2023-03-01 |  | 2025-03-01 | 2026-09-16 | 22392000 |  | Amber | Green | Amber | Red | Red | Tender evaluation is currently underway and progressing as planned. The funding for the program is being finalised through a business case, resulting in a red cost status until the funding has been resolved. The funding position is posing a significant risk to the schedule, resulting in an red overall status rating.
Q2 25-26 | South West Alliance of Rural Health | SWARH | 3334 | Regional Electronic Health Record Upgrade (excluding Barwon Health) | Health | Customer Relationship Management,Data Management,Development and Integration ,Management of Process ,Records Management ,Systems Management,Tracking and Workflow | Upgrade to the regional Electronic Health Record (EHR) solution, that supports 11 health services across South West Victoria. The project will improve clinician and patient user experience, focusing on quality and safety of patient care. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-10-16 | 2022-03-31 | 2022-08-31 | 2022-09-01 | 180000 | 300000 | 2022-09-05 |  | 2025-06-30 | 2027-04-01 | 23495000 |  | Red | Red | Green | Amber | Amber | Work continues on the regional electronic health upgrade to improve usability and support quality care across South West Victoria. Delivery time frames have been adjusted to address technical remediation activities.
Q2 25-26 | Melbourne Water | MELB Water | 3338 | Electronic Content Management Phase 1 | Environment and Water | Content Management | This project will upgrade Melbourne Waters current document storage repositories and migrate to a new Electronic Document and Records Management System (EDRMS) | Initiated |  |  | PMBoK | 2021-10-08 | 2022-09-22 | 2026-04-01 |  | 0 | [12 empty] | As at 20251231: Business Case has been submitted.
Q2 25-26 | Victoria Police | VicPol | 3358 | Electronic Document and Records Management System | Law and Justice | Document Management | The overall objective of the project is to implement a fully integrated, enterprise-wide Electronic Document and Records Management Solution and an Enterprise Service Management platform to uplift information management maturity. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2020-11-25 | 2021-11-25 | 2024-12-31 | 2025-12-31 | 8559000 | 8559000 | Green | Green | Green | Amber | Amber | The core objective of the business case has been achieved with the Records365 delivered in March 2025 and the supporting solutions (DekkoSecure and Automated Briefing and Correspondence) implemented in December 2025. Whilst the EDRMS project is effectively delivered its status remains AMBER due to ongoing ingestion of data into Records365 and progressive roll out of the briefing product. This will be continued as part of the funded BAU support and iterative enhancement activity into 2026 to fully roll out the EDRMS capability organisation wide.
Q2 25-26 | Victoria Police | VicPol | 3359 | Finance Systems Program (Oracle Cloud) | Law and Justice | Investment Management | Delivery of a new financial system, updating technology and business processes across finance, purchasing and supply chain functions to increase efficiency and improve access to accurate information to support decision-making. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2021-11-25 |  | 2025-06-30 |  | 32453000 |  | Red | Red | Red | Red | Red | Detailed Design activities with the Systems Integrator are on hold pending agreement on plan, resources and commercials. Additional funding is required to complete the Build, Test and Deployment activities. A request for additional project budget has been submitted.
Q2 25-26 | Victoria Police | VicPol | 3360 | Enterprise Rostering | Law and Justice | Human Capital / Workforce Management | The project will deliver an enterprise wide rostering and timesheet solution, consolidating disparate systems and manual processes into one integrated system to better support rostering and timesheet management. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2020-11-25 | 2021-11-24 | 2024-12-31 | 2025-09-30 | 21490000 | 21490000 | Red | Red | Red | Red | Red | Path to GREEN requires confirmation of project budget and/or re-cashflow. Schedule can then be re-baselined with confirmed scope and project schedule dates beyond September 2025 as per current schedule.
Q2 25-26 | Country Fire Authority | CFA | 3369 | CFA Radio Replacement Program | Emergencies and Safety | Communication | CFA’s current Tait 9100 series radios are no longer manufactured and are approaching the end of their practical life for operational purposes. These will be replaced across Victoria and will introduce a technology refresh with enhanced functionality. | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2021-07-01 | 2022-03-31 | 2022-03-31 | 2022-03-31 | 235465 | 235465 | 2022-04-01 |  | 2024-06-30 | 2025-12-31 | 138595535 | 136247000 | Green | Green | Green | Green | Green | Due to escalated operational activity from the January 2026 Victorian Bushfires, CFA’s ICT team is prioritising the support of fire operations. A project status update will be provided for the following reporting period (Q3 2025-26).
Q2 25-26 | Department of Government Services | DGS | 3377 | Digital Victoria Marketplace | Government and Economy | Collaboration ,Data Management,Records Management | The Marketplace is an initiative by Digital Victoria to provide a simpler, and easier way for Government and Industry to interact through the eServices register and various other SPC's. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-10-01 | 2021-10-13 |  | 2021-10-13 | 0 | 7708 | 2022-02-01 |  | 2027-06-30 |  | 16790000 |  | Green | Green | Green | Green | Green | The Digital Marketplace is meeting agreed timelines for releasing functionality into the production version of Digital Marketplace which aligns with the expected benefit delivery
Q2 25-26 | Alfred Health | ALFRED | 3378 | Alfred Health / Monash Health - Shared Laboratory Information System | Health | Records Management | The shared LIS program will deliver a Laboratory information system as a foundational technology for the Alfred Monash Pathology partnership supporting the DoH Pathology sector reform initiative to consolidate pathology systems and services. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-10-05 | 2022-08-31 | 2023-02-28 | 2023-02-28 | 2000000 | 2000000 | 2023-02-28 |  | 2025-06-30 | 2026-06-30 | 25000000 | 41800000 | Amber | Red | Red | Amber | Amber | Amber status reflects fixed project timelines and the management of solution defects. Appropriate mitigations are in place to limit impacts to clinical go-live. The solution will go-live as scheduled, with Alfred Health to commence from 22 January 2026. Western Health and Melbourne Health go-lives are scheduled for February and April 2026.
Q2 25-26 | Department of Transport and Planning | DTP | 3399 | Victraffic Upgrade Project | Transport and Vehicles | Communication,Customer Initiated Assistance,Customer Preferences | Objective of this project is to support transport users and emergency response units to safely and confidently move around our road network during an emergency situation and improve road closure capture and uplift the user experience. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-27 | 2022-09-19 | 2023-07-10 | 2023-07-10 | 0 |  | 2023-07-10 |  | 2024-06-30 | 2026-06-30 | 22637000 |  | Green | Green | Green | Green | Green | The overall status is green, and the project is on track with all implemented systems in the process of being transitioned to operations.
Q2 25-26 | Court Services Victoria | CSV | 3451 | Victorian Civil and Administrative Tribunal digital service transformation | Law and Justice | Content Management,Customer Initiated Assistance,Development and Integration ,Security Management ,Tracking and Workflow,Data Management,Document Management ,Forms Management,Knowledge Management ,Management of Process ,Records Management ,Routing and Scheduling | The project aims to upgrade digital services infrastructure including the case management system and increase process automation, to deliver more accessible and timely provision of justice to citizens and businesses | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - Waterfall and Agile | 2020-11-01 | 2021-02-04 |  | 2021-05-15 | 0 |  | 2021-07-01 | 2021-07-01 | 2024-12-01 | 2026-06-30 | 56681000 |  | Amber | Amber | Amber | Amber | Amber | Program formalised baseline plans for the Guardianship List (GL) and Residential Tenancies (RT) List implementations. Schedules are extended compared to original estimates as: - Guardianship List Discovery revealed more complexity and risk. - Both list delivery plans are constrained by a change moratorium in place during VCAT's headquarters relocation in early 2026.
Q2 25-26 | Victorian Institute of Forensic Mental Health (Forensicare) | Forensicare | 3458 | Human Capital Management (HCM) Rostering Payroll System | Health | Human Capital / Workforce Management ,Human Capital / Workforce Management | Forensicare is implementing a new Human Capital Management system to replace and integrate its ageing payroll, rostering and recruitment systems. This system will better meet staff needs and improve capacity for better care to growing customer base | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-08-23 | 2022-09-08 | 2023-12-11 | 2023-12-11 | 0 | 221000 | 2024-01-15 |  | 2025-09-30 | 2027-02-26 | 2580000 |  | Green | Green | Amber | Amber | Green | Phase 2 planning including pre-discovery and discovery (design) have commenced subsequently the project is now Green and working toward the delivery of Phase 2. Note: The schedule revision is to incorporate Phase 2 delivery timeframe.
Q2 25-26 | V/Line Corporation | V/Line | 3465 | Payroll Improvements | Transport and Vehicles | Human Capital / Workforce Management | The objective of the payroll improvement project is to improve data collection for Leave, Time & Attendance information to support V/Line’s payroll function, in creating a more robust and consistent payroll operation organisation wide. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2023-03-31 | 2024-05-31 | 2024-05-31 | 0 | 500000 | 2024-06-03 | 2024-12-09 | 2025-09-30 | 2027-06-30 | 3300000 |  | Amber | Green | Green | Green | Green | The project has delivered the initial release of the payroll reporting tool, with reports now available for user acceptance testing. The focus will now shift to Workstream 2 - time and attendance solutions. To identify fit‑for‑purpose enterprise solutions, the project has completed a Request for Information (RFI) process to assess the market and recommend suitable options. The project schedule has been updated to include Workstream 2 delivery timeframes and to align with dependencies on the HRIS project.
Q2 25-26 | Central Highlands Region Water Corporation | CHR Water | 3466 | Digital Metering Program | Environment and Water | Customer Initiated Assistance,Customer Relationship Management | Replace analogue meters with digital, resulting in improved customer experience, reduced operational risk, improved environmental and sustainability footprint, and utilise water meter data to provide greater oversight of the water and sewer network. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Eco Improvement (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2020-07-01 | 2022-12-31 |  | 2023-01-02 | 0 |  | 2023-01-02 |  | 2026-09-30 | 2026-12-30 | 19500000 | 20708032 | Green | Green | Green | Green | Green | Project proceeding to stakeholder expectations
Q2 25-26 | Melbourne Health | Melb H | 3496 | Parkville Laboratory Information System (LIS) Program | Health | Management of Process ,Records Management ,Systems Management,Tracking and Workflow | The LIS Connect Program will procure and implement a single LIS solution for Pathology Network West across the Parkville precinct pathology services. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2022-03-01 | 2023-12-31 | 2024-07-31 | 2024-07-31 | 6047518 |  | 2024-09-23 |  | 2026-08-28 |  | 23817159 | 31572148 | Green | Amber | Amber | Amber | Amber | Project continues in User and System Readiness phase with a focus on application testing. All resources have been recruited to the project with good progress seen in all portfolios this quarter. Several testing phases are behind schedule, but contingencies are in place.
Q2 25-26 | Department of Transport and Planning | DTP | 3497 | Victorian Transport Digital Engineering Transformation Program | Transport and Vehicles | Assets/Materials Management,Content Management,Data Management,Document Management ,Visualisation | Objective of this project is to develop a roadmap to progressively move to a digital environment for engineering, design and data management. DoT and MTIA will collectively deliver the DE Transformation, Horizon 1 -3 projects over the next 2-3 years. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-04 | 2022-12-30 | 2023-02-06 | 2023-02-06 | 0 |  | 2023-02-06 |  | 2023-12-29 | 2026-06-30 | 5135000 | 45000518 | Green | Green | Amber | Amber | Amber | The program is reporting an amber status as it is experiencing budget pressure on several potential pilots with re-planning occurring to ensure value is obtained from the pilots. The build activities continue across all initiatives and are tracking relatively well.
Q2 25-26 | Fire Rescue Victoria | FRV | 3505 | Implementing Protective Marking and Information Protection | Emergencies and Safety | Data Management | Implementing processes for managing protective markings on official or higher classified content (documents and emails) in line with the Office of the Victorian Information Commissioner : Victorian Protective Data Security Standards. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2022-02-11 | 2022-06-30 |  | 2022-06-30 | 0 |  | 2022-07-01 |  | 2024-06-30 | 2026-06-30 | 1512000 |  | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q2 25-26 | Peninsula Health | PEN Health | 3522 | Peninsula Health NHCA Smart Ward | Health | Business Intelligence | National Centre for Healthy Aging (NCHA), a Monash University (MU) and Peninsula Health (PH) collaboration, has established a program of works that includes the establishment of a Smart Ward to collect patient observations for Research. | Delivery | Customer Satisfaction (Non Financial) |  | PRINCE2 | 2022-11-07 | 2023-01-31 | 2024-02-29 | 2024-03-07 | 0 | 19968 | 2024-03-07 |  | 2025-07-31 | 2026-02-12 | 1222641 | 1423459 | Green | Green | Green | Green | Green | The Smart Ward project remains on track and scheduled to complete on time and on budget. Outstanding work is required for completion of the 4D Radar application and improving accuracy of the wristband location tracking.
Q2 25-26 | Ambulance Victoria | AVS | 3547 | Cloud & Infrastructure Program | Health | Assets/Materials Management | The program will upgrade network infrastructure and address the closure of data centres and the end-of-life of data centre assets through migrating workloads to Cloud. This program will deliver improved security and performance for our services. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-04 | 2023-01-31 |  | 2023-01-31 | 341911 | 155621 | 2023-02-01 |  | 2025-11-28 | 2027-06-30 | 18295989 | 14522917 | Green | Green | Green | Red | Red | The project reported a red status due to project budget confirmation in progress. Delivery is progressing well with migrations to Azure and the first Private Cloud physical platform build at the data centre successfully completed. The project will be rebaselined once the budget is confirmed.
Q2 25-26 | Royal Children's Hospital | RCH | 3551 | Identity and Access Management (IDAM) | Health | Security Management | Implementation of new identity management solution | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2022-11-28 | 2023-06-02 | 2025-01-23 | 2025-01-23 | 0 |  | 2025-01-23 |  | 2025-12-31 | 2026-07-31 | 3368053 |  |  | Green | Green | Green | Green | The IDAM environment is currently being configured and undergoing testing activities. Integration with SAP has been completed and is now in Test phase. Configuration work with ServiceNow integration is in progress.
Q2 25-26 | Melbourne Water | MELB Water | 3557 | HR Modernisation | Environment and Water | Human Resources | Implement new Human Resources Information System (HRIS) technology to provide a sustainable, efficient and contemporary solution for people and payroll management, people performance and learning organisation goals. | Postponed | Compliance (Non Financial), Efficiency/Productivity (Non Financial) | 2025-06-30 | PMBoK | 2022-10-05 | 2023-08-31 | 2023-11-13 | 2023-12-13 | 0 |  | 2023-12-13 |  | 2024-11-19 | 2025-08-15 | 2722712 | 6892613 | Green | Green | Red | Red | Green | As at 20251231: Project postponed to reassess approach to ensure we achieve business benefits.
Q2 25-26 | Melbourne Water | MELB Water | 3559 | Network Architecture Improvements SDWAN | Environment and Water | Security Management | Network Architecture improvement to SD WAN / Zero trust Model | Closed - Completed | Cost Avoidance (Financial), Risk Reduction (Non Financial) | 2025-12-18 | PMBoK | 2021-08-26 | 2023-01-16 |  | 2023-01-25 | 0 |  | 2023-01-26 |  | 2023-10-10 | 2026-12-09 | 1189517 | 3470123 | Red | Red | Red | Amber | Green | As at 20251231: Project has been closed.
Q2 25-26 | Loddon Mallee Rural Health Alliance | LMRHA | 3563 | Regional integrated Electronic Patient Record | Health | Records Management | Delivery of an integrated Electronic Patient Record for members of the Loddon Mallee Rural Health Alliance (excluding Bendigo Health) - this will support more connected patient care for patients region wide. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-10-03 | 2023-06-30 | 2026-01-30 |  | 70000 | 600000 | [11 empty] | Work has continued to progress on the finalisation of project approach, scope, schedule and cost. Project remains on target for this to be approved in Q3 2025 - 2026.
Q2 25-26 | Loddon Mallee Rural Health Alliance | LMRHA | 3575 | Patient Administration System Replacement | Health | Data Management,Records Management ,Reporting | Replacement of Bendigo Health's current Patient Administration System (PAS) solution to align with the Electronic Patient Record (EPR) - moving to a single for both capabilities will ensure smoother patient care and support. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-06-06 | 2023-06-30 | 2023-09-30 | 2023-10-02 | 150231 |  | 2023-10-23 |  | 2025-07-15 | 2026-04-30 | 4930809 |  | Amber | Amber | Red | Amber | Amber | The project status is AMBER due to condensed timelines and a number of items on the critical path at risk. Timeline will be reviewed to mitigate risks.
Q2 25-26 | Loddon Mallee Rural Health Alliance | LMRHA | 3585 | Regional Community Care Coordination Platform | Health | Records Management ,Tracking and Workflow | Delivery of a digital medical record for all the Community health care provided by members of the Loddon Mallee Rural Health Alliance to support connected patient care across the region (and between health services). | Closed - Completed | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2025-10-03 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-07-01 | 2019-04-01 |  | 2019-04-10 | 0 |  | 2019-04-11 |  | 2021-03-31 | 2025-10-03 | 1330000 | 4528817 | Green | Green | Amber | Green | Green | All project deliverables have been completed. Transition to operational support teams complete. Project has been closed.
Q2 25-26 | CenITex | CenITex | 3596 | Enterprise platforms renewal program | Government and Economy | Customer Relationship Management | Upgrade existing Dynamics 365 platform and implement a system that integrates & meets stakeholder requirements for Customer Engagement Project Services and Finance. Also, mitigate support issues due to end of life of the current platform. | Closed - Completed | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2025-10-31 | PRINCE2 | 2023-01-04 | 2023-01-12 |  | 2023-01-12 | 0 |  | 2023-02-03 |  | 2024-06-28 | 2025-10-31 | 1652000 | 1798319 | Green | Green | Green | Green | Green | Project completed
Q2 25-26 | Department of Health | DH | 3599 | Mental Health and Wellbeing Website | Health | Communication | This project will deliver a mental health website, addressing recommendations 6.4 and 31.3 of the Royal Commission into Victoria's Mental Health System, to help Victorians navigate the mental health system and find relevant services and supports. | Postponed |  | 2023-06-30 | Agile | 2022-09-21 | 2023-05-12 | 2023-06-30 |  | 843493 | 1185694 |  |  |  |  | 0 | [6 empty] | Project on pause due to priority being given to other mental health and wellbeing initiatives.
Q2 25-26 | South West Alliance of Rural Health | SWARH | 3602 | HR Digital Solution | Health | Human Resources | The scope of the strategic HRIS is to replace the Health Services HR applications and manual, paper-based processes with a contemporary, fit-for-purpose, strategic HRIS solution. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2023-02-24 | 2023-10-27 | 2023-12-01 | 2023-12-01 | 834297 |  | 2024-01-15 |  | 2026-04-30 |  | 13629603 |  | Amber | Red | Red | Red | Red | Implementation of the Strategic HR Digital Solution is progressing. System integration testing is complete, with rollout sequencing linked to the Rostering project.
Q2 25-26 | Department of Premier and Cabinet | DPC | 3608 | Workflow Management System for Office of Chief Parliamentary Counsel (OCPC) | Government and Economy | Development and Integration ,Tracking and Workflow | WMS project will provide workflow for managing legal projects to improve management of the projects as per the OCPC standards and timely and accurate reporting to internal and external users to ensure timely publishing on the legislation website. | Closed - Terminated | Cost Avoidance (Financial), Customer Satisfaction (Non Financial) | 2025-11-10 | Agile | 2021-06-18 | 2021-07-01 |  | 2021-07-01 | 0 |  | 2023-02-24 |  | 2024-07-13 | 2025-11-10 | 2500000 |  | Green | Red | Red | Red | Green | On 10/11/2025 the State and the vendor mutually agreed, by deed, to terminate the replacement Work Management and Legislative Database System (WMS) contract and project.
Q2 25-26 | Central Highlands Region Water Corporation | CHR Water | 3612 | ERP Upgrade | Environment and Water | Assets/Materials Management,Financial Management,Human Capital / Workforce Management ,Supply Chain Management | This project will upgrade the existing platform(s) due to an impending end of support timeline with a contemporary integrated solution to improve the Finance, Procurement, Commercial and Asset Management processes of CHW | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-01-02 | 2023-06-30 | 2023-09-29 | 2023-09-29 | 0 |  | 2023-10-02 |  | 2025-09-30 | 2026-12-18 | 9510000 | 11910255 | Green | Green | Green | Green | Green | The project is tracking in line with stakeholder expectations
Q2 25-26 | Eastern Health | EH | 3638 | Enable Program | Health | Human Capital / Workforce Management ,Human Resources | Enable success of our people through 3 x HR systems projects: 1. Rostering Project - Replace RosterOn with Optima 2. People Journey Project - Replace eMercury with SAP SuccessFactors 3. Payroll Project - Replace SAP Payroll with SAP SuccessFactors | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-10-01 | 2023-03-31 |  | 2023-06-07 | 75000 |  | 2023-06-07 |  | 2025-10-31 | 2027-02-01 | 10148335 | 10592143 | Green | Green | Green | Green | Green | Phase 1 & 2 completed. Phase 3 Payroll System now under way. Note the schedule revision is to incorporate phase 3 delivery schedule.
Q2 25-26 | WorkSafe Victoria | WorkSafe | 3642 | Digital Identity Uplift (Enterprise IDAM Uplift) | Employment, Skills and Workplace | Systems Management | Uplift the Digital Identity environment to ensure people have the right access to resources, at the right time. This will enhance the user experience and strengthen security controls. Project name was changed from Enterprise IDAM Uplift | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-02-01 | 2023-03-31 |  | 2023-04-04 | 0 |  | 2023-06-05 |  | 2025-06-30 | 2026-10-31 | 4316783 | 4224778 | Green | Green | Red | Red | Green | On track
Q2 25-26 | Grampians Rural Health Alliance | GRHA | 3645 | Maryborough Hospital Redevelopment ICT Project | Health | Development and Integration ,Systems Management | The Maryborough Hospital redevelopment ICT project provides infrastructure integration of clinical equipment mobile/desktop devices to support clinical care in the new state-of-the-art healthcare facility; improving care outcomes for patients. | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-12-01 | 2021-06-01 |  | 2021-06-01 | 0 |  | 2021-06-01 |  | 2025-06-30 | 2026-03-31 | 5158000 |  | Green | Green | Green | Green | Green | ICT equipment and systems operational in new hospital. Minor close out works continuing. Project is on track.
Q2 25-26 | Triple Zero Victoria | TZV | 3651 | Next Generation Computer Aided Dispatch System | Emergencies and Safety | Systems Management | Implement a new enhanced, reliable and secure emergency services Computer Aided Dispatch system to support enhanced critical emergency services 000 call taking and dispatch capability. | Delivery | Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-07-01 | 2024-11-27 | 2024-12-01 | 20588172 |  | 2024-12-02 |  | 2027-06-30 | 2028-06-30 | 233301093 |  | Green | Green | Green | Green | Green | The project is tracking in accordance with overall scope, planned delivery cost and approved delivery schedule.
Q2 25-26 | Gippsland Health Alliance | GHA | 3654 | EMR Rural Expansion (Phase 4) | Health | Records Management | Expansion of EMR into 6 x Rural health services in the Gippsland Region | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial) |  | PMBoK | 2023-03-14 | 2023-11-30 | 2024-11-22 | 2024-11-22 | 200000 | 2675777 | 2025-03-12 |  | 2025-11-11 | 2026-04-30 | 3383375 |  |  |  | Green | Green | Green | The EMR Expansion project is tracking well—currently rated Green and actively progressing through the Delivery phase.
Q2 25-26 | Department of Families, Fairness and Housing | DFFH | 3658 | Integrated supervised contact and access solution | Community Services | Customer Relationship Management | Integrate existing case management and support systems (Contact & Access Transport System) for supervised contact and access to eliminate duplicate processes and better support planning and decision making for children in out of home care. | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2025-12-12 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-15 | 2022-09-09 |  | 2022-10-13 | 0 |  | 2023-02-01 |  | 2024-06-30 | 2025-12-14 | 1217500 | 3015452 | Green | Amber | Green | Green | Green | Project has successfully delivered and closeout activities are underway.
Q2 25-26 | Northern Health | NH | 3666 | Patient Engagement/Entertainment System (PES) | Health | Communication | To provide patient TVs and other supported clinical workflows for better patient care at Northern Health | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-02 | 2021-12-31 |  | 2021-12-31 | 50000 |  | 2023-02-01 | 2023-08-01 | 2024-07-30 | 2026-03-31 | 3450000 |  | Amber | Green | Amber | Green | Green | The system upgrade plan will be provided by the vendor shortly.
Q2 25-26 | Queen Elizabeth Centre | QEC | 3667 | Client Information Management System | Health | Data Management,Document Management ,Forms Management,Management of Process ,Reporting | QEC is focused on developing a Client Information Management System (CIMS) that can accommodate growth diversity and emerging evidence; enable clinical implementation of the outcomes framework; and meet funding and reporting requirements. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-11-23 | 2023-10-18 | 2023-11-15 | 2023-11-29 | 225000 | 283153 | 2023-12-04 |  | 2025-12-30 | 2026-06-30 | 1314347 | 1335472 | Green | Green | Green | Green | Green | Project is tracking as expected.
Q2 25-26 | Department of Justice and Community Safety | DJCS | 3668 | EMD (Emergency Management Day) PHASE 2 | Law and Justice | Development and Integration | This project supports management of EMD data for remanded prisoners to avoid unlawful detention or release and reduce legal risk. The objective is to provide a system for SCWA to manage sentences prisoner discharges and documentation for CV. | Closed - Completed | Compliance (Non Financial), Cost Avoidance (Financial), Cost Reduction (Financial) | 2025-12-02 | Agile | 2022-05-02 | 2023-03-31 |  | 2023-06-16 | 0 |  | 2023-03-31 | 2023-06-17 | 2024-06-30 | 2025-11-30 | 1466100 | 1466100 | Green | Green | Green | Green | Green | The project was completed in December 2025.
Q2 25-26 | Melbourne Health | Melb H | 3683 | CMI Data Access Project | Health | Data Management,Records Management ,Reporting | The CMI Data Access Project will deliver the disaggregation of data contained in the Mental Health Client Management Interface (CMI). There will be four data repositories created to enable mental health program reporting for NH, WH, RMH and Orygen. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2025-11-28 | PRINCE2 | 2023-07-01 | 2023-11-17 | 2023-09-04 | 2023-09-04 | 147800 | 80000 | 2023-09-04 |  | 2024-06-30 | 2025-11-28 | 1122200 | 1190000 | Green | Green | Green | Green | Green | Project delivered to schedule.
Q2 25-26 | Grampians Rural Health Alliance | GRHA | 3688 | Ballarat Base Hospital Redevelopment - ICT Program - Stage 3 | Health | Systems Management | Stage 3 will deliver ICT systems to support the project works, improving patient and staff systems & support. | Initiated |  |  | PMBoK | 2022-01-03 | 2025-12-01 | 2026-02-27 |  | 0 | [12 empty] | Project is continuing to scope IT deliverables and technical specifications. Currently finalising the tender phase for 2 of the ICT packages.
Q2 25-26 | Hume Rural Health Alliance | HRHA | 3694 | ICT transition to Hume Rural Health Alliance (KDHS) | Health | Organisational Management | The project will transition Kyabram District Health Service (KDHS) ICT from Loddon Mallee Rural Health Alliance to Hume Rural Health Alliance to provide IT oversight and support. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-03-31 |  | 2024-04-24 | 100000 | 37000 | 2024-04-24 |  | 2025-06-30 | 2026-06-30 | 3463000 |  | Amber | Amber | Amber | Amber | Amber | Kyabram Health IT environment was successfully migrated from LMSS to HRHA during the third week of November. The scope included the network, application and file servers, workstations, laptops, end user devices, business applications, security tool, user accounts and mailboxes. Clinical grade network links have been established at both Kyabram main site and Tongala. Telephony uplift project will commence in early 2026. The project is Amber as the Payroll implementation scope/timeline is under review placing schedule under pressure. The project team will propose an alternate approach for governance approval upon review completion.
Q2 25-26 | Grampians Rural Health Alliance | GRHA | 3695 | MDHS ICT transition to Grampians Rural Health Alliance | Health | Organisational Management | The project will transition Maryborough District Health Service from Loddon Mallee Rural Health Alliance to Grampians Rural Health Alliance to better align with natural patient flows in the region (improved patient experience ). | Delivery | Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-11-17 | 2025-04-01 | 2025-04-01 | 0 | 150000 | 2025-04-01 |  | 2026-12-31 |  | 3450000 |  |  |  | Green | Green | Amber | Minor procurement delays with key work packages for AD/Email/M365 have caused impacts to project timelines. Continued review of budget, timeframes, and scope under way with project stakeholders.
Q2 25-26 | Loddon Mallee Rural Health Alliance | LMRHA | 3696 | HR Information System | Health | Human Capital / Workforce Management | Implementation of a Human Resources Information System (HRIS) for members of Loddon Mallee Rural Health Alliance -this uplift will enable resource planning and management visibility across the region. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-12-31 |  | 2023-12-31 | 65000 | 175000 | 2024-01-01 | 2025-08-28 | 2025-12-20 | 2027-06-30 | 13500000 |  | Amber | Amber | Amber | Amber | Amber | The project status is AMBER due to a delay in SME recruitment and onboarding. This has impacted on readiness activities completion. Contingency in timeline will minimise impact on development implementation start date of February 2026.
Q2 25-26 | Transport Accident Commission | TAC | 3698 | Digital Identity Uplift | Transport and Vehicles | Systems Management | Uplift the Digital Identity environment to ensure people have the right access to resources, at the right time. This will enhance the user experience and strengthen security controls. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-05-18 | 2023-05-18 |  | 2023-05-18 | 0 |  | 2023-06-05 |  | 2025-06-30 | 2026-10-31 | 4316783 |  | Green | Green | Red | Red | Green | Project is tracking to plan for Q2 FY25/26.
Q2 25-26 | V/Line Corporation | V/Line | 3699 | HRIS (Human Resources Information System)​ system replacement | Transport and Vehicles | Human Capital / Workforce Management ,Human Resources | To implement a new human resource information system for V/Line, in order to improve accuracy and reliability of HR data for service delivery. | Initiated |  |  | PRINCE2 | 2023-07-01 | 2024-11-29 | 2026-04-24 |  | 900000 | 1476107 | [11 empty] | The project team has progressed with the evaluation of the product and implementation partner tenders and expects to complete evaluations as expected in early February with contract negotiations to commence shortly after. Recruitment activities are also progressing well, in preparation for the implementation of the system.
Q2 25-26 | Royal Women’s Hospital | RWH | 3703 | Rostering, Time and Attendance Project | Health | Human Capital / Workforce Management | The Project will upgrade the current Rostering system, delivering performance improvements and new enhanced functionalities. This project is part of an overarching People Systems Improvement Program with Royal Melbourne Hospital and Western Health | Closed - Completed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) | 2025-12-31 | PRINCE2 | 2023-07-03 | 2023-09-01 |  | 2023-09-01 | 31980 |  | 2023-09-03 |  | 2024-12-31 | 2025-10-30 | 1140573 |  | Green | Green | Amber | Amber | Green | All staff are now live on the new Rostering System. The project has been successfully delivered.
Q2 25-26 | Department of Health | DH | 3731 | Managed Services Provider Replacement (MSPR) | Health | Data Management,Development and Integration | Replacement of the Managed Service Provider (MSP) for the Oracle Cloud Infrastructure tenancies to better support the departments operations. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2023-06-01 | 2023-06-30 |  | 2023-06-30 | 0 |  | 2023-07-01 |  | 2025-12-31 | 2026-05-31 | 1412500 | 1088061 | Amber | Red | Amber | Amber | Amber | Project is reporting an Amber health status due to constraints in accessing the required services, which are affecting the schedule. The impact on the overall schedule will be assessed once the tender evaluation is completed.
Q2 25-26 | Department of Health | DH | 3733 | St Vincent's Electronic Medical Record Project | Health | Analyses and Statistics ,Collaboration ,Communication,Forms Management,Organisational Management ,Records Management | Implementation of an electronic medical record (EMR) to streamline clinical documentation medication management and other clinical activities to support the provision of safer higher quality and more efficient patient care. | Initiated |  |  | PRINCE2 | 2023-09-01 | 2024-07-01 | 2026-06-01 |  | 0 | 0 | [11 empty] | The primary focus of the St Vincent's Hospital Melbourne Electronic Medical Record (EMR) project continues to be on procurement and contracting processes in collaboration with another Victorian health service. Organisational readiness tasks continue including a network uplift and other infrastructure initiatives to prepare the clinical environment.
Q2 25-26 | Lower Murray Urban and Rural Water Corporation | LMUR Water | 3749 | Technology Uplift Program (Formerly - Business Transformation Program) | Environment and Water | Customer Relationship Management,Data Management,Financial Management,Human Capital / Workforce Management ,Human Resources,Reporting ,Supply Chain Management | Enabling LMW of the Future. The program will uplift capabilities across key business functions, including customer service, billing, assets and workforce and financial management to enable improved customer service and efficiency.​ | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2024-02-02 | 2024-05-30 | 2024-05-31 | 899582 |  | 2024-06-03 |  | 2026-06-30 |  | 12100105 | 15524022 | Green | Green | Green | Green | Green | Scheduled activities are proceeding as planned with minimal/no impacts for this quarter.
Q2 25-26 | Department of Families, Fairness and Housing | DFFH | 3756 | Communities and Families Transformation - Stage 1 | Community Services | Customer Relationship Management | Deliver a business case with options for strategic investment in technology platforms, underpinning delivery of care services to communities and families, to enable seamless interactions and experience for our clients and sector partners. | Delivery | Social Improvement (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2022-08-15 | 2024-01-11 | 2023-01-11 | 2023-06-19 | 0 |  | 2023-07-01 |  | 2025-06-30 | 2026-06-30 | 14429000 | 16282000 | Green | Green | Green | Green | Green | Project progressing to revised cost and schedule.
Q2 25-26 | Department of Transport and Planning | DTP | 3757 | Human Capital Management (HCM) Project - Phase 2 | Transport and Vehicles | Business Intelligence,Customer Initiated Assistance,Forms Management,Management of Process ,Tracking and Workflow | To lead the implementation of SAP SuccessFactors (including Payroll) for DTP . Program scope includes the changes required for the Machinery of Government (MoG) changes announced in December 2022. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-01 | 2023-06-30 |  | 2023-08-14 | 0 |  | 2023-08-14 |  | 2024-06-30 | 2025-12-31 | 7490000 | 13618209 | Amber | Amber | Amber | Green | Amber | The program is reporting amber status against the new baseline of scope, schedule and budget as there is continued pressure on the schedule across two project streams and an increasingly complex operating environment. The program team is working with the steering committee to resolve the issues and will inform the revise delivery end date in the next reporting period.
Q2 25-26 | Yarra Valley Water | YV Water | 3762 | Enterprise Analytics Platform - Phase 2 | Environment and Water | Data Management | Replacement of YVW's data warehouse, operational data-store and business intelligence reporting technologies with a modern, scalable data and analytics platform | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2023-09-01 | 2023-09-30 |  | 2023-09-30 | 0 |  | 2023-10-01 |  | 2025-04-28 | 2026-06-30 | 6640340 | 8243140 | Amber | Amber | Amber | Amber | Amber | The project is currently reporting an Amber status due to ongoing and significant schedule delays. The original vendor contract was terminated, and a new tender is currently out to market with responses expected in Q3 FY2026.
Q2 25-26 | Melbourne Polytechnic | MelbPoly | 3767 | Melbourne Polytechnic Student Management System Implementation | Employment, Skills and Workplace | Systems Management | Selection and Implementation of new Student Management System for Melbourne Polytechnic to improve student and user experience, increase digitalisation and automation, and improve functionality and compliance. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-29 | 2023-12-31 |  | 2024-01-08 | 182000 |  | 2024-01-15 |  | 2027-01-29 | 2027-07-30 | 7818000 | 13258270 | Green | Green | Green | Green | Green | Key scope, schedule and budget review conducted. Budget now reflects OTCD Grant and MP internal costs aligned to scope and schedule. Project progressing to revised plan and targets.
Q2 25-26 | Department of Transport and Planning | DTP | 3773 | Future Public Transport Ticketing System | Transport and Vehicles | Customer Initiated Assistance,Customer Preferences,Financial Management,Systems Management | The future Public Transport Ticketing (PTT) System will deliver modern customer payment features and progressively replace the current myki Ticketing System (myki System) | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-07-01 | 2021-10-18 |  | 2021-10-18 | 0 |  | 2021-10-18 |  | 2028-06-30 | 2028-12-31 | 543000000 | 680350000 | Green | Green | Green | Green | Green | The program is reporting an overall status as green. The program implementation activities are ongoing.
Q2 25-26 | Melbourne Water | MELB Water | 3807 | Network Resilience FY25-26 | Environment and Water | Assets/Materials Management | To continue investing in our IT network ensuring that we reduce the risk of unplanned network outages meet compliance requirements improve our security posture increase capacity reliability and bandwidth to accommodate future growth. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PMBoK | 2023-12-08 | 2024-02-27 |  | 2024-07-24 | 0 |  | 2024-07-24 | 2024-10-22 | 2026-06-22 | 2027-03-19 | 4966804 | 5128521 | Green | Green | Red | Amber | Red | As at 20251231: Further change request has been raised to include a hardware purchase.
Q2 25-26 | WorkSafe Victoria | WorkSafe | 3811 | Contact Centre Capability Uplift | Employment, Skills and Workplace | Communication | WorkSafe’s telephony system is built upon ageing infrastructure and tech. The introduction of a contact-centre-as-a-service will uplift person-centred services and ensure continuity for frontline support of injured workers & the Victorian community. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2022-01-01 | 2023-11-26 |  | 2023-12-11 | 441569 | 326274 | 2023-12-11 |  | 2025-12-31 | 2026-04-30 | 7321441 | 3867488 | Green | Green | Green | Green | Green | On track
Q2 25-26 | Grampians Rural Health Alliance | GRHA | 3812 | Grampian Health - Electronic Medical Record System | Health | Data Management | Implementation of an Electronic Medical Record system across five campuses of Grampians Health, namely Ballarat, Dimboola, Edenhope, Horsham, and Stawell. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-10-31 | 2028-06-30 | 2026-06-01 |  | 0 | [12 empty] | The primary focus of the Grampians Health Electronic Medical Record (EMR) project continues to be on procurement and contracting processes in collaboration with another Victorian Health Service. Organisational readiness tasks continue including a network uplift and the other infrastructure initiatives to prepare the clinical environment are in progress.
Q2 25-26 | Ambulance Victoria | AVS | 3816 | Rostering System Replacement (WMS) | Health | Systems Management | The project will replace the current end-of-life rostering software with a new workforce management solution, minimising software stability and security risks, and improving efficiency in rostering processes to deliver more impact to our community. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2025-12-05 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-03-30 |  | 2024-03-31 | 1271134 | 826551 | 2024-04-01 |  | 2025-06-30 | 2025-12-31 | 3846467 | 6370186 | Amber | Amber | Amber | Red | Green | The project has been successfully completed.
Q2 25-26 | Ports Victoria | PortsVic | 3824 | Port Management Information System (PMIS) Project | Transport and Vehicles | Routing and Scheduling | Implementation of a Port Management Information System (PMIS), directly supporting the management of maritime navigation and operational safety, providing safe, fair, and efficient access for the commercial ports of Melbourne, Geelong and Hastings. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-03 | 2024-12-20 | 2026-02-27 |  | 0 | 249990 | [11 empty] | The Blueprint and pre‑contract readiness engagement commenced in November 2025 and will conclude by the end of January 2026. The revised initiation end date reflects the time required to finalise the Blueprint activities and deliverables - covering cost, scope, and schedule - which will inform the final business case. The business case is scheduled for governance committee review in Q3.
Q2 25-26 | Chisholm Institute of TAFE | Chisholm TAFE | 3825 | Chisholm Student Management System Transformation Project | Employment, Skills and Workplace | Records Management | The project will migrate legacy student management system to new technology offered by the existing vendor to minimize technology risk and maintain student experience and business continuity. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-01-09 | 2023-05-31 |  | 2023-05-31 | 0 |  | 2023-11-16 |  | 2026-09-25 | 2027-12-31 | 8000000 |  | Amber | Amber | Green | Green | Green | Maintained ongoing coordination with the vendor to ensure all project deliverables remain on track with the agreed schedule.
Q2 25-26 | Department of Transport and Planning | DTP | 3828 | Trusted and Secure Program | Transport and Vehicles | Data Management,Security Management ,Systems Management | The objective of this program is to implement cyber and information security standards, enhancing information security measures and reducing risks of cyber incidents, by embedding robust and proactive cyber security practices. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2023-10-02 |  | 2023-10-02 | 0 |  | 2023-10-03 |  | 2024-06-30 | 2026-06-30 | 6800000 | 17334852 | Green | Green | Amber | Amber | Amber | The program status is reported as amber. The status is amber due to the challenges related to project work-streams. The program team is working on mitigating these risks. The program includes fourteen completed project streams with seven others in progress.
Q2 25-26 | Department of Transport and Planning | DTP | 3829 | Public Transport Data program (PTDP) (Formerly known as ITDP) | Transport and Vehicles | Business Intelligence,Communication,Customer Initiated Assistance,Customer Preferences,Data Management,Search | Purpose of this program is to improve the Department’s capability to deliver accurate and consistent real-time information for customers whenever, wherever and however they need it. | Closed - Completed | Customer Satisfaction (Non Financial) | 2025-12-04 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-03-29 | 2023-08-31 | 2023-08-31 | 0 | 0 | 2023-09-01 | 2024-01-01 | 2025-11-30 |  | 16140000 |  |  | Amber | Amber | Green | Green | The delivery phase of this project is now complete.
Q2 25-26 | Austin Health | AH | 3837 | CRM Statewide Project | Health | Customer Relationship Management | Make five CRM modules available to all metropolitan and some regional health agencies, improving referral management and waitlist management, providing efficiencies and improved waiting lists. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-01 | 2023-12-22 |  | 2023-12-22 | 0 |  | 2024-01-02 |  | 2024-12-31 | 2026-06-30 | 4565000 | 9509070 | Green | Green | Green | Green | Green | - Deployed Module 1 at Albury and Royal Children's. - Deploying Module 4 at Goulburn Valley Health. - Module 2 was on hold to provide resources for interhospital transfer build. - Module 5 deployment halted due to lower uptake.
Q2 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3839 | Biosciences Advanced Scientific Computing (BASC) Infrastructure Refresh Project | Government and Economy | Knowledge Discovery | The BASC Infrastructure Refresh project will deliver refreshed infrastructure to replace an end-of-life system that supports agricultural research. This project will be delivered in three phases over the next three years. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Eco Improvement (Non Financial), Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-09-25 | 2024-06-28 | 2024-12-31 | 2024-12-31 | 150000 | 399415 | 2025-01-01 |  | 2027-12-18 |  | 3675686 | 5836104 |  | Amber | Amber | Green | Green | Phase 1 activities have been successfully completed. Phase 2 requirements definition has been completed and orders have been placed with delivery underway and continuing throughout Q3 25/26 FY. Note that the project budget reflects the Phase 1 & 2 budget only and will be incrementally adjusted based on the subsequent phase planned commitment.
Q2 25-26 | Barwon Region Water Corporation | BR Water | 3841 | C1430 - Network Segmentation | Environment and Water | Security Management | The Network Segmentation project will segregate and segment the operational and corporate networks reducing the impact and recovery time of a network security breach ensuring the reduction in cyber incident risk profile and improved SOCI compliance. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-02-01 | 2023-04-14 |  | 2023-04-14 | 15000 |  | 2023-04-14 |  | 2024-11-07 | 2026-08-31 | 1477000 | 2983000 | Green | Green | Green | Amber | Amber | The IT/OT separation is behind schedule. This may impact the commencement of the IT segmentation phase.. The project is being rescheduled which, when approved, will return the project back to green status. Approval process nearing completion.
Q2 25-26 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3843 | Human Resources Information System Replacement | Education | Human Resources | Replace BKI’s ageing HR and Payroll systems with a modern cloud-based platform which will enable improved HR processes, improved user experience and significantly improved people data and reporting. | Postponed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2025-09-24 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-09-01 | 2023-12-08 |  | 2023-12-08 | 370000 | 125000 | 2024-02-01 |  | 2025-03-31 | 2025-12-19 | 2643965 | 3161265 | Amber | Red | Red | Red | Red | Phase 2 of the HRIS project remains formally on hold to allow resolution of outstanding Enterprise Agreement negotiations and the impact on staff back payments. To avoid unnecessary expenditure and rework, project activity has ceased until industrial outcomes are finalised and the organisation has capacity to complete the remaining implementation of the payroll module.
Q2 25-26 | Department of Health | DH | 3844 | Security Access Modernisation | Health | Systems Management | Cloud application migration from legacy TAM6 to ISVA10 environment, and engagement with business teams to transition their onboarding process to use Departmental User Onboarding Portal V2, reducing operational risk of the unsupported TAM6 platform. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-06-28 |  | 2024-06-28 | 574077 |  | 2024-06-28 |  | 2025-06-30 | 2026-06-30 | 1413388 | 1387986 | Green | Amber | Green | Green | Green | Project is progressing to cost and revised schedule.
Q2 25-26 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3845 | Apprentice and Trainee Management Module Implementation | Education | Systems Management | This project will deliver functionality into the core student management system to be enable apprentice and trainee student management. This will bring all BKI students management onto one platform, reducing integration and data risks | Postponed | Increased Revenue (Financial) | 2025-06-05 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-30 | 2023-12-08 |  | 2023-12-08 | 200000 |  | 2024-01-08 |  | 2025-06-30 | 2025-12-31 | 3157730 | 4311828 | Red | Red | Red | Red | Red | The project is currently paused. As system build activities are progressing in parallel for two other TAFEs, a decision has been made to pause our investment until that development is further advanced. This approach ensures the appropriate allocation of government resources, avoids duplication of effort and positions us to leverage shared learnings and system components once the build is complete.
Q2 25-26 | Department of Health | DH | 3846 | SDWAN activities and production rollout | Health | Systems Management | Delivering a new resilient, secure and internet centric network solution to all Department of Health and Families, Fairness and Housing sites, supporting the departments move towards cloud based IT services. | Closed - Completed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2025-12-19 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-03 | 2023-12-01 |  | 2023-12-04 | 0 |  | 2024-01-02 |  | 2025-06-30 | 2025-12-31 | 1422000 | 1281002 | Green | Green | Green | Amber | Green | Project has successfully delivered and closeout activities are underway. A small number of remaining data centre sites will be completed by a separate project.
Q2 25-26 | Western Health | WH | 3851 | Western Health - Mental Health Transition (ICT Infrastructure) | Health | Development and Integration | WH and RMH teams are migrating IT services to WH. Priority is minimal disruption to services, with workarounds in place to maintain service continuity and direct access to the Project team to address any issues potentially impacting patient care. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2025-12-12 | PRINCE2 | 2023-07-01 | 2023-10-30 |  | 2023-11-20 | 0 |  | 2024-01-01 |  | 2024-10-30 | 2025-12-12 | 1960000 |  | Green | Amber | Green | Green | Green | Project completed in December 2025
Q2 25-26 | Workplace Injury Commission | WIC | 3853 | Case Management System | Law and Justice | Tracking and Workflow | Implementation of a new case management system that improves efficiency and productivity, to support the resolution of workplace injury disputes for Victorian workers. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-02-14 | 2024-10-30 | 2025-05-28 | 2025-05-28 | 0 | 1900000 | 2025-05-29 |  | 2027-06-30 |  | 12000000 |  |  |  |  | Green | Green | The project is progressing well and remains on track across all key dimensions—schedule budget and benefits. Vendor is onsite for initiation in preparation for the discovery phase.
Q2 25-26 | Department of Justice and Community Safety | DJCS | 3854 | Impact Assessment Strategic Project | Emergencies and Safety | Data Management | This project will deliver improvements to Impact Assessment processes and systems in Victoria, aiming to provide efficient, timely and appropriate support for communities impacted by an emergency. | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2025-12-31 | Project Management Excellence | 2023-08-01 | 2024-01-31 |  | 2024-01-31 | 255242 |  | 2024-02-01 |  | 2025-06-30 | 2025-12-31 | 6800000 |  | Green | Amber | Green | Green | Green | The project was completed in December 2025.
Q2 25-26 | Department of Health | DH | 3856 | Mental Health and Wellbeing Client Management System Implementation Project (MHWCMS) | Health | Data Management,Development and Integration | Delivery of a Mental Health and Wellbeing Client Management System to the Mental Health Sector to replace CMI/ODS and acquit recommendation 62 in the Royal Commission into Victoria’s Mental Health System. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2023-12-01 | 2023-12-22 |  | 2023-12-22 | 0 |  | 2024-01-01 |  | 2026-06-30 | 2028-06-30 | 40229527 | 64701864 | Amber | Red | Red | Red | Red | Project is reporting a Red health status, primarily due to significant schedule slippage caused by solution implementation issues and constraints in accessing required services. The underlying issues are being actively addressed, and re-planning and re-baselining is in progress.
Q2 25-26 | North East Link State Tolling Corporation | NELSTC | 3858 | Toll Collection Capability (TCC) - Roadside Systems (RSS) | Transport and Vehicles | Analyses and Statistics ,Communication,Data Management,Development and Integration ,Records Management ,Reporting | The Roadside Systems will effectively & efficiently detect vehicles and capture tag or vehicle details ensuring toll revenue is collected accurately and road users have a seamless experience while accessing North East Link. | Initiated |  |  | PMBoK | 2023-06-27 | 2025-09-26 | 2026-06-29 |  | 1117000 | [12 empty] | The TCC RSS contract was awarded in FY25 Q4 and now in the delivery phase. RSS activities are progressing in line with planned schedules with the contractor progressing well into the Preliminary Design phase.​ The project will remain in initiation until TCC - Back Office Systems (BOS) procurement completes in FY26 Q4 to maintain procurement integrity. The TCC RSS and TCC BOS projects are complementary streams of the one project which share a budget. Disclosing the full cost of TCC RSS could potentially enable TCC BOS respondents to derive the BOS budget compromising procurement integrity and competitive positioning. The Revised Initiation End Date reflects this approach.
Q2 25-26 | North East Link State Tolling Corporation | NELSTC | 3859 | Toll Collection Capability (TCC) - Back Office Systems (BOS) | Transport and Vehicles | Communication,Customer Initiated Assistance,Customer Relationship Management,Management of Process ,Reporting | The Back Office Systems will efficiently manage trip formation, interoperability between Australian Toll Roads, billing and collection of toll revenue while providing road users an efficient way to pay for their travel on North East Link. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-27 | 2026-06-29 |  |  | 1117000 | [12 empty] | The project will remain in initiation until procurement completes in FY26 Q4 to maintain procurement integrity.​ The BOS procurement activities are progressing in line with baseline schedule and forecasted within the approved budget.
Q2 25-26 | Coliban Region Water Corporation | Coliban Water | 3860 | Core Capability Uplift | Environment and Water | Financial Management | New software implementation and business processes optimisation to uplift the Commercial and Financial Management capabilities, directly contributing to the strategic goals of ‘Financial Sustainability’ and ‘An Adaptive and Resilient Organisation’. | Delivery | Efficiency/Productivity (Non Financial) |  | PMBoK | 2023-08-08 | 2024-07-02 | 2025-07-02 | 2025-07-02 | 0 |  | 2025-07-07 |  | 2026-08-13 | 2026-11-30 | 11070000 |  |  |  |  | Amber | Green | Status returns to green on completion of re-plan activities.
Q2 25-26 | Greater Western Water Corporation | GW Water | 3863 | Asset, Works & Field Services Mgmt Consolidation (Concordia) | Environment and Water | Assets/Materials Management,Collaboration ,Data Management,Development and Integration ,Human Capital / Workforce Management ,Reporting ,Systems Management | AWFSMC serves as a foundational pillar to transform future ready Field Service mgmt & Asset & Works Mgmt capabilities . It will increase business & customer satisfaction & will be delivered in phases with budget increases reflecting each phase | Delivery | Compliance (Non Financial), Cost Avoidance (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-09-11 |  | 2023-09-11 | 760490 |  | 2023-09-11 |  | 2028-06-30 | 2026-06-30 | 3436310 | 8470976 | Green | Amber | Green | Green | Green | Procurement and Commercial activities have impacted the project schedule. GWW will do formal reassessment of the end-to-end delivery schedule in consultation with the vendor.
Q2 25-26 | Greater Western Water Corporation | GW Water | 3864 | Geospatial Capability Uplift (OSO 2030) | Environment and Water | Analyses and Statistics ,Assets/Materials Management,Data Management,Visualisation | The project will enhance geospatial capability through modern standards and technologies to maximise value of spatial information in order to gain new insights for improved asset management capabilities across the organisation. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial) |  | Waterfall | 2023-07-01 | 2024-04-07 |  | 2024-04-07 | 3900000 |  | 2024-04-07 |  | 2028-06-30 |  | 20300000 |  | Green | Green | Green | Green | Green | Phase 1 activities (including data migration and procurement) continue through Q2 as planned and remain on track for completion in Q3.
Q2 25-26 | Department of Justice and Community Safety | DJCS | 3869 | Replacement DJCS Safety Incident Management System | Community Services | Reporting | Procurement, and implementation of a safety incident management system will streamline how safety incidents are reported and investigated. This system will foster a proactive safety culture where incidents are managed efficiently and effectively. | Postponed |  | 2025-06-30 | Project Management Excellence | 2023-12-19 | 2024-01-31 | 2024-01-04 |  | 0 | [5 empty] | 0 | [6 empty] | Due to resourcing constraints, the project was postponed in June 2025. The project completed the initiation phase in January 2024 and was approved to commence procurement activities for the provision of a safety incident management system. Once resources become available, the project will transition to the delivery phase, commencing with procurement activities. The delay in procurement commencement does not result in any additional risk as the project seeks to deliver a replacement system that enhances functionality and provide efficiencies beyond what the current system offers. The current system is still fully functional and operational.
Q2 25-26 | Holmesglen Institute of TAFE | Holmesglen TAFE | 3870 | Identity Governance and Administration | Employment, Skills and Workplace | Security Management | The IGA project will deliver a new Identity Governance & Administration platform. The new IGA platform will improve staff/student identity governance and security by enabling contemporary features such as attestation and hardened authentication. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-09-14 | 2023-11-15 |  | 2023-12-06 | 0 |  | 2024-03-01 |  | 2025-03-28 | 2026-07-31 | 1205132 |  | Green | Green | Amber | Amber | Amber | Project team commenced a re‑evaluation of functional and technical requirements following the decision to shift key business logic into the Student Management System. T his new approach strengthens architectural alignment and ensures that identity processes are driven from the system best suited to manage them. Workshopping with vendor on updated solution designs. Project timelines will be re‑baselined once this design work and associated validation activities are completed. Revised timelines are expected to be confirmed next quarter.
Q2 25-26 | South East Water | SE Water | 3879 | Sample Management | Environment and Water | Assets/Materials Management,Management of Process | The project will deliver a sample management system to streamline current processes, modernising the system capability, and enabling improved reporting, faster processes and insights for customer water quality. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2024-04-08 | 2024-08-01 |  | 2024-08-01 | 159445 |  | 2024-09-02 |  | 2025-07-31 | 2026-06-30 | 1937205 |  | Green | Green | Green | Green | Green | Phase 2 of project underway with development and system testing completed. User acceptance testing and implementation on track for completion in FY26 Q3.
Q2 25-26 | Northern Health | NH | 3880 | Active Directory Segregation from Melbourne Health | Health | Systems Management | Northern and Melbourne Health are currently sharing the same Active Directory. Segregating from this shared active directory to a more modern version will allow NH to initiate its journey into cloud and enhance cyber security across all campuses | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2022-01-01 | 2022-09-27 |  | 2022-09-27 | 0 |  | 2023-03-09 |  | 2025-09-30 | 2026-04-30 | 3200000 |  | Green | Green | Amber | Green | Green | Significant progress has been made across key infrastructure initiatives. The majority of web services have now been successfully migrated to the new DMZ, with the remaining services scheduled to be completed by the end of Q1. Planning for the future Citrix Windows image is underway, with discussions focused on defining the operating system and application standards, which will also inform associated licensing requirements. The migration of Radiology and Cardiology servers has been rescheduled to March 2026 to reflect current resourcing constraints and to ensure operational risks are managed appropriately.
Q2 25-26 | WorkSafe Victoria | WorkSafe | 3881 | Medical Panels Capability Uplift | Employment, Skills and Workplace | Tracking and Workflow | Medical Panels technology will migrate to a modern system enabling digital record-keeping, workflow automation, and improved cyber security. This mitigates the risk of end-of-life tech, improves efficiency, and uplifts staff / stakeholder experience. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-03 | 2024-12-05 | 2025-02-24 | 2025-02-24 | 947722 | 758291 | 2025-02-25 | 2025-04-14 | 2025-10-31 | 2026-06-30 | 4999889 | 4914431 |  | Amber | Amber | Red | Amber | Status upgraded to Amber based on approval of schedule extension. Build has been completed but launch has been delayed due to several gaps in solution capability. Scope review is underway to identify potential impacts on delivery timeline and cost and provide a plan to return to Green status.
Q2 25-26 | Melbourne Water | MELB Water | 3882 | Business Process Optimisation 24-26 | Environment and Water | Systems Management | This project aims to optimise business processes and workflows using modern process management tool, improving process efficiency & reducing reliance on manual processes. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-06-13 | 2024-10-25 |  | 2024-11-14 | 0 |  | 2024-11-14 |  | 2026-07-21 |  | 2900000 | 3104887 | Green | Green | Green | Amber | Red | As at 20251231: Change Request has been raised to extend the project scope.
Q2 25-26 | Victorian Gambling and Casino Control Commission | VGCCC | 3883 | Compass - Gambling License System (GLS) replacement project - Release 1 | Law and Justice | Customer Relationship Management | A new regulatory system to replace the legacy license management system. The project will remediate and uplift VGCCC's ICT infrastructure, improving ICT capabilities and enabling effective, risk-based, and intelligence-led regulatory approach. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial) | 2025-10-13 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-04 | 2024-09-06 | 2024-08-30 | 2024-08-30 | 36000 |  | 2024-09-02 |  | 2025-08-01 | 2025-10-21 | 1500000 | 1757000 | Green | Green | Green | Green | Green | The project was successfully delivered on 13 October 2025.
Q2 25-26 | Grampians Rural Health Alliance | GRHA | 3886 | Grampians Health Success Factors Phase 2 | Health | Human Resources | Implementation of SAP SuccessFactors, including Employee Central Payroll, refactoring of Employee Central, Recruitment, Onboarding, and implementation of Performance & Goals. Phase 2 will deliver integration with rostering, finance and IT systems. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-13 | 2023-12-15 |  | 2023-12-15 | 0 |  | 2024-08-14 |  | 2025-09-26 | 2026-02-27 | 2905553 |  | Green | Green | Green | Green | Green | From the 3rd November the system has gone live as planned. This includes integrations to our rostering system and other modules. 6 full fortnightly pay processes have been completed successfully in the new system as well multiple offline cycles. There are 2 outstanding items that remain to be finalised with those being the integration with Epicor and Fit2Work. These are due to be finalised by the end of February 2026. Due to the complexities and criticality of the Optima integration this was prioritised ahead of the above integrations hence the reason these are being completed post go live.
Q2 25-26 | Greyhound Racing Victoria | GRV | 3887 | Greyhound Whole of Life Tracking (GWOLT) | Business and Industry | Analyses and Statistics ,Business Intelligence,Customer Relationship Management,Management of Process | Digital Whole of Life Greyhound Tracking (DGT) involves the digitised data capture storage and retrieval to automate processes for tracking and recording the location and health of Victorian greyhounds throughout stages of their lives. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-01-08 | 2025-01-31 | 2025-03-23 | 2025-03-23 | 0 |  | 2025-03-24 |  | 2026-03-31 |  | 2920000 |  |  | Green | Green | Green | Green | The project is tracking well against budget, schedule and scope. Delivery of the case management solution has commenced, which is the final deliverable from the endorsed program scope.
Q2 25-26 | Department of Government Services | DGS | 3889 | Common Corporate Platform (CCP) - VicGov People - DGS/DPC/DTF Cluster | Government and Economy | Human Capital / Workforce Management | Onboarding the Departments of Government Services, Premier and Cabinet, and Treasury and Finance on a common human capital management platform (VicGov People) to drive efficiency and productivity, enhancing employee experience and corporate services | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-04 | 2024-06-28 | 2024-06-01 | 2024-06-25 | 0 |  | 2024-07-01 | 2024-07-01 | 2026-06-30 | 2026-03-27 | 25000000 |  | Green | Green | Amber | Amber | Amber | The project reported amber due to risk of resourcing over the holiday period. Critical activities are needed in late December and early January to support execution. Overall progress has been sound with the successful completion of testing on critical functions such as payroll and data migration of staff records. Project is confident of delivery on time.
Q2 25-26 | Yarra Valley Water | YV Water | 3891 | Altus PPM Tool Implementation | Environment and Water | Investment Management | Implementation of a PPM tool to centralise visibility of up-to-date program information, support consistency in the way projects get delivered, and provide insights on demand. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-08-01 | 2024-08-15 |  | 2024-08-26 | 421280 |  | 2024-09-02 |  | 2026-06-10 |  | 2947600 |  | Green | Amber | Amber | Amber | Amber | Project is reporting Amber due to change in MVP scope and reassessment of the impact of this on the benefits, schedule and cost. Project team is working with internal stakeholders and vendor to inform the way forward and change request required.
Q2 25-26 | Fire Rescue Victoria | FRV | 3893 | Asset Sustainment | Emergencies and Safety | Assets/Materials Management | This project aims to procure ICT equipment to replace components at end-of-life. This includes equipment such as network equipment and fire station switches and will ensure a safe ICT environment and ensure ongoing reliability. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-07-01 | 2020-10-05 |  | 2020-10-05 | 0 |  | 2022-02-14 |  | 2024-12-31 | 2026-06-30 | 7069087 | 6967773 | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q2 25-26 | Department of Education | DE | 3896 | Kindergarten Attendance Program | Education | Analyses and Statistics ,Business Intelligence,Data Management | Delivery of a digital solution to collect kindergarten attendance data to improve child outcomes and to report on performance indicators as required by the Commonwealth Preschool Reform Agreement. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Increased Revenue (Financial) |  | Agile | 2023-02-01 | 2023-07-31 |  | 2023-08-01 | 0 |  | 2023-08-01 |  | 2026-06-30 |  | 20965000 |  | Green | Green | Green | Green | Green | The project is GREEN following stakeholder agreement to modify functionality and the rebaseline of the schedule for deployment of the funding and operational settings for Kindergarten Services.
Q2 25-26 | Department of Health | DH | 3899 | Health Technology Services Application Cloud Migration | Health | Data Management,Development and Integration | Migrate three Health Technology Services applications to the department’s ICT Cloud environments, namely Finance and Material Information System, Client Management System and HealthCollect, to improve data availability, security and reliability. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2024-05-01 | 2024-05-31 |  | 2024-05-31 | 0 |  | 2024-06-03 |  | 2025-06-30 | 2026-01-31 | 2715200 | 3091807 | Amber | Red | Amber | Amber | Red | Project is reporting a Red health status due to constraints in accessing the required services, which have affected the schedule. The schedule has been replanned and will be submitted to Steering Committee for approval in next reporting period. Project expected to return to Green once revised schedule approved.
Q2 25-26 | Westernport Region Water Corporation | WPR Water | 3906 | Asset Management Information System Replacement | Environment and Water | Assets/Materials Management | The project will replace legacy asset management and work order management systems improving functionality and flexibility to enable more accurate, accessible and comprehensive information for decision-making. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-09-03 | 2025-06-30 | 2025-04-14 | 2025-04-14 | 200000 | 254000 | 2025-04-14 |  | 2026-10-30 |  | 1440000 |  |  |  | Green | Green | Green | Project remains on-track and on-budget. Phase 1a is expected to be completed in the next quarter.
Q2 25-26 | Peninsula Health | PEN Health | 3907 | Peninsula Health Project Phoenix (MePACS Refresh) | Health | Customer Relationship Management | A technology refresh of the core MePACS systems with a modern Customer Relationship Management System (CRM) to secure the ongoing viability of the MePACS business. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-06-03 | 2024-10-31 |  | 2024-10-31 | 340000 |  | 2024-11-04 |  | 2025-10-31 | 2026-06-30 | 2620000 | 2621445 | Green | Green | Green | Green | Green | A revised plan for Phase 2 go-live has been approved to mitigate time impact due to issue resolution and data migration, subject to system testing and user acceptance. Phase 3 build is largely completed. A budget impact analysis is being prepared for Steering Committee’s consideration and approval.
Q2 25-26 | Monash Health | Monash H | 3911 | Delphi - Oracle Cloud Fusion | Health | Financial Management | The project will implement Oracle software as a service to uplift management of finance, procurement, enterprise performance, project management, supply chain, and warehouse, enabling more efficient and effective business processes for Monash Health. | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2025-12-31 | Waterfall | 2024-08-07 | 2024-09-13 |  | 2024-09-13 | 50000 |  | 2024-09-16 |  | 2025-12-26 | 2025-12-31 | 17631000 |  | Green | Green | Green | Amber | Green | Monash Health went live with the Enterprise Resource Planning and Supply Chain Management modules within its Oracle Fusion program. The project has successfully transitioned to operations and is nearing completion of the hypercare period with the team now focused on steady‑state support.
Q2 25-26 | Monash Health | Monash H | 3912 | Maternity Digital Transformation Project | Health | Management of Process | The project will implement EMR and breast milk management module onto a single EMR platform, supporting a single view of the patient's medical record, improving clinical outcomes for both mother and baby. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-10-31 | 2024-04-04 | 2024-04-04 | 0 | 0 | 2024-11-01 |  | 2026-05-27 |  | 11522379 |  |  | Amber | Green | Green | Red | The vendor has advised they are unable to meet current project timeline, requiring the project schedule to be re-baselined. An impact assessment of the schedule adjustment and mitigation options is currently under review.
Q2 25-26 | Barwon Region Water Corporation | BR Water | 3915 | C1062 - Works and Asset Management | Environment and Water | Assets/Materials Management | Improve strategic and operational asset management and service delivery through the implementation of Maximo Works Management providing benefits such as, a more financially sustainable business and keeping bills affordable for all. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-01 | 2025-03-31 | 2025-07-01 | 2025-07-01 | 824310 | 2162000 | 2025-07-01 |  | 2026-12-31 |  | 10208000 |  |  |  |  | Green | Amber | WAM progressed its Phase 1 initiative, with external works moving from build to testing. Planning in October–November highlighted increasing design, integration, and process complexity across later phases, leading to a changes request merging Phases 2 and 3 to streamline delivery and maintain the overall end date. Key work continued finance system and GIS integrations. The project remained on track against the revised plan in Q2, with a strong focus on risk management and readiness for Phase 1 go live and subsequent phases.
Q2 25-26 | Department of Families, Fairness and Housing | DFFH | 3917 | Public Housing Maintenance Modernisation Technology Enablement Program | Community Services | Development and Integration | Uplift digital capability of Homes Victoria systems including new housing maintenance portal, improvements to HiiP system, and integration capability with Contractor Work Systems, providing greater process efficiencies and ease of use by tenants. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-10-01 | 2024-10-11 |  | 2024-10-11 | 1214790 |  | 2024-10-11 |  | 2026-06-30 |  | 23066733 | 25623840 | Green | Red | Red | Red | Amber | The program status is amber due to delays in finalising business procurement activities. The impact to cost and schedule is currently being assessed, but at this stage is not expected to affect the overarching Public Housing Maintenance Modernisation schedule.
Q2 25-26 | Department of Families, Fairness and Housing | DFFH | 3921 | Automated System Integration of the Victorian Housing Register (online) Application | Community Services | Records Management | Moving the Victorian Housing Register Application to an automated integrated solution, thereby improving the timeliness and capacity to manage an increase in volumes at an office level, improving client experience with faster feedback. | Closed - Completed | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2025-11-28 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-28 | 2024-06-28 |  | 2024-06-28 | 192450 |  | 2024-07-15 |  | 2025-06-30 | 2025-11-28 | 1614264 | 2589264 | Red | Green | Red | Green | Green | Project has successfully delivered and closeout activities are underway.
Q2 25-26 | South East Water | SE Water | 3923 | Acumen Phase 2 | Environment and Water | Business Intelligence,Data Management | Phase 2 of Acumen will deliver foundation components, including architecture review and data preparation for ingestion and modelling. This will deliver key foundational elements necessary to support future phases. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-01-01 | 2024-02-29 |  | 2024-02-29 | 0 |  | 2024-02-29 |  | 2025-04-30 | 2026-02-28 | 3600000 | 6585000 | Amber | Green | Amber | Amber | Green | The project is reporting GREEN after re-baselining deliverables that were delayed. Schedule has been adjusted to deliver remaining data sources in FY26 Q3. Minimal impact to budget despite longer timeframe.
Q2 25-26 | South East Water | SE Water | 3924 | Information Management Strategy Delivery | Environment and Water | Business Intelligence,Data Management,Reporting | Program of work delivering multiple initiatives that is delivering on the Information Strategy including - Enterprise Content Management Data & Information Management Analytics & Reporting. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-06-01 | 2023-06-30 |  | 2023-09-26 | 0 |  | 2023-09-26 |  | 2025-07-31 | 2026-07-31 | 1859425 |  | Red | Red | Amber | Green | Green | The project is currently tracking GREEN with deliverables all on track as per baselined schedule.
Q2 25-26 | South East Water | SE Water | 3925 | Lentic Performance Enhancements | Environment and Water | Communication | Optimization of IoT platform to ensure scalability and optimal performance within the boundaries of the current architecture. This will ensure the IoT platform will support the mass roll out of digital meters across SEW network. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2024-03-01 | 2024-04-18 |  | 2024-06-05 | 0 |  | 2024-08-01 |  | 2025-12-31 | 2026-06-30 | 1161000 |  | Green | Amber | Amber | Green | Green | Project had returned to GREEN. Phase 2 implementation successfully implemented in FY26 Q2. Work has commenced on Phase 3 and deliverables are on track as per baselined schedule.
Q2 25-26 | Gippsland Health Alliance | GHA | 3928 | Payroll and Talent Modernisation (HRIS) | Health | Human Capital / Workforce Management | The project involves implementing a single instance of SAP SuccessFactors across eleven agencies in Gippsland. This initiative aims to modernise processes and systems, enhancing efficiency and collaboration among the agencies. | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2022-02-18 | 2022-05-20 |  | 2023-02-17 | 180000 |  | 2023-04-10 |  | 2025-06-27 | 2026-06-30 | 1600000 | 1700000 | Amber | Amber | Amber | Green | Green | All remaining sites are scheduled for go-live across two phases. One group in February and the second in March - April '26. Preparation activities such as data cleansing, trainig and change management are on track. Production verification testing to begin in the upcoming week.s
Q2 25-26 | Transport Accident Commission | TAC | 3931 | Strategic Analytics Program Phase 2 | Transport and Vehicles | Business Intelligence | Build capability for both analysts & the broader enterprise in working optimally to deliver use cases from a prioritised backlog that will result in well managed & trusted data, improved customer & workforce satisfaction, platform efficiencies. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-07-01 |  | 2024-07-01 | 0 |  | 2024-07-01 |  | 2026-06-30 |  | 11000000 |  | Green | Green | Green | Green | Green | The program is tracking to plan for Q2 FY25/26. Delivery Teams have been working with stakeholders to review and refine Q3 delivery plans.
Q2 25-26 | Melbourne Water | MELB Water | 3932 | Cyber Defence Initiatives | Environment and Water | Security Management | Redesign the existing SOC capability in line with the new Security Operations Operating Model. Deliver a better asset discovery and inventory capability, providing cyber control coverage assurance to the organisation. | Delivery | Risk Reduction (Non Financial) |  | PMBoK | 2024-07-26 | 2025-02-20 | 2025-07-07 | 2025-07-07 | 0 |  | 2025-07-07 |  | 2026-06-10 |  | 4868275 | 4547353 |  |  |  | Green | Green | As at 20251231: Integration and procurement phase is progressing.
Q2 25-26 | WorkSafe Victoria | WorkSafe | 3933 | Strategic Integration Platform | Employment, Skills and Workplace | Systems Management | Integration technology connects systems and data across platforms. This project will move existing integrations to the Strategic Integration Platform a modern cloud-based solution that reduces failures and speeds recovery benefitting all users. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 0 |  | 2024-07-01 |  | 2025-06-30 | 2026-06-30 | 4597071 | 10624421 | Green | Amber | Red | Green | Green | The final phase of the project is tracking to the schedule, however the project is proactively managing risks around the schedule and business continuity.
Q2 25-26 | WorkSafe Victoria | WorkSafe | 3934 | Licensing CRM (Customer Relationship Management) FY25 | Employment, Skills and Workplace | Customer Relationship Management | Transition of the remaining 5 license journeys from the legacy mainframe. This completes the transition of License Management capability to the CRM, unifying business processes, centralising data, and enhancing both customer and employee experiences. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 0 |  | 2024-07-01 |  | 2025-06-30 | 2026-03-31 | 4466242 | 7054661 | Green | Red | Green | Amber | Red | The project is reporting Red due to a delay in completing discovery activities and a scope review impacting timelines. The schedule is being revised and a change request will be prepared in Q3 to establish path to Green.
Q2 25-26 | Independent Broad-based Anti-corruption Commission | IBAC | 3941 | Case Management System Enhancement Project | Government and Economy | Business Intelligence,Collaboration | This project is to deliver enhancements to IBAC's case management system and improvements to data maturity in the form of analytics, reporting and dashboard outputs. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-03 | 2024-12-31 | 2025-01-31 | 2025-01-31 | 0 | 270000 | 2025-02-01 |  | 2026-06-30 |  | 2443584 | 2443584 |  | Amber | Amber | Amber | Green | On track to revised timeline. A minor delay in the Phase 2 software delivery and installation (1 week) may impact the Q3 timeline but this risk will be addressed during testing and validation. There is no anticipated impact to the approved budget overall project timeline and scope.
Q2 25-26 | Yarra Valley Water | YV Water | 3943 | Digital Meter Integrated Software Solution (HES/MDMS) | Environment and Water | Analyses and Statistics ,Assets/Materials Management,Knowledge Discovery ,Tracking and Workflow,Visualisation | Implementation of an integrated software solution for an Internet of Things Head End System (IoT HES) and Meter Data Management System (MDMS) to enable YVW’s digital water metering and IoT strategy which plans to deploy around one million digital met | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2022-08-01 | 2023-12-31 |  | 2024-01-09 | 1062000 |  | 2024-01-10 |  | 2025-06-30 | 2026-06-30 | 6678000 |  | Green | Green | Green | Green | Green | The project is tracking well against scope and budget, with a minor schedule delay to last milestone due to business reprioritisation. The software platform is live and over 25k meters deployed (Phase 1 goal) with enhanced features to identify customer leaks. Large meters from EDMI with new protocol has been tested in Production.
Q2 25-26 | Yarra Valley Water | YV Water | 3945 | WorksPortal System and Asset Creation Replacement | Environment and Water | Customer Relationship Management | The current WorksPortal System is reaching end of life with support expiring by July 2026. As the system relates to asset creation and revenue, a replacement is required. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-07-01 | 2025-03-31 | 2025-05-31 | 2025-06-19 | 650000 | 736000 | 2025-06-19 |  | 2026-04-30 |  | 3936260 |  |  |  | Green | Green | Amber | The project is reporting an Amber status due to a delay is onboarding key resources, which has affected the schedule and costs. These resources have now been onboarded and the impact for revisions being assessed. Requirements gathering and solution design for the new technology have been completed, with development and quality assurance activities now underway.
Q2 25-26 | Yarra Valley Water | YV Water | 3946 | Land Development System (easyACCESS) Replacement | Environment and Water | Customer Relationship Management | Full replacement of the current easyACCESS Land Development portal with a Salesforce solution, before the portal reaches end of life | Initiated |  |  | Agile | 2024-07-01 | 2025-06-30 | 2026-03-31 |  | 1772100 | 3795600 | [11 empty] | The project completed the final procurement review with 8 weeks of collaborative co-design (470 expert hours, plus 135 hours of quality checks). This built strong shared understanding of project needs, risks, and ways of working, while refining our delivery plan. These insights now feed into the business case for governance approval, triggering early actions like securing resources and addressing key dependencies. The project is progressing well
Q2 25-26 | Yarra Valley Water | YV Water | 3947 | MAXIMO 2025 UPGRADE | Environment and Water | Data Management | To upgrade Maximo software version 7.6 to version 9 to ensure continued support, enhance operational efficiency and leverage additional functionalities | Closed - Completed | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2025-12-31 | Agile | 2024-01-01 | 2025-01-15 | 2025-01-08 | 2025-01-08 | 697090 |  | 2025-01-08 |  | 2025-12-31 |  | 1723910 | 2193910 |  | Green | Amber | Green | Green | Project and hypercare now completed.
Q2 25-26 | Melbourne Water | MELB Water | 3948 | End User Computing Lifecycle Renewal FY24-26 | Environment and Water | Assets/Materials Management | Staff have been provided devices including laptops, tablets, heat sets and mobile phones to perform their tasks. These devices need to be regularly updated to ensure suitable performance and enabling the use of modern applications. | Initiated |  |  | PRINCE2 | 2024-09-30 | 2025-02-06 | 2026-06-24 |  | 0 | 3458441 | [11 empty] | As at 20251231: Business Case to be submitted Q3 FY25/26.
Q2 25-26 | Melbourne Water | MELB Water | 3949 | Identity and Access Management Initiatives | Environment and Water | Security Management | Process uplift, technology build and onboarding to the current identity access platform. | Delivery | Risk Reduction (Non Financial) |  | PMBoK | 2024-07-26 | 2025-05-21 | 2024-12-11 | 2024-12-11 | 0 |  | 2024-12-11 |  | 2026-06-30 |  | 4807000 | 4205076 | Green | Green | Red | Green | Green | As at 20251231: Project has been rescoped as per approved change request.
Q2 25-26 | Melbourne Water | MELB Water | 3950 | Intranet Renewal | Environment and Water | Communication | Renew or replace current Melbourne Water Intranet, including full investigation of options and user impacts. Re-imagine employee access to internal information. | Initiated |  |  | PMBoK | 2024-08-26 | 2024-12-18 | 2026-02-20 |  | 0 | 1725000 | [11 empty] | As at 20251231: Business case to be submitted in Q3 2026.
Q2 25-26 | Melbourne Water | MELB Water | 3952 | Privilege Access Management Initiatives | Environment and Water | Systems Management | This project aims to implement a comprehensive Privileged Access Management (PAM) system to enhance security by onboarding critical accounts across network and operational technology environments. The investment supports robust identity governance. | Delivery | Risk Reduction (Non Financial) |  | PMBoK | 2024-07-26 | 2025-03-21 | 2024-12-12 | 2024-12-12 | 0 |  | 2024-12-12 |  | 2026-06-30 |  | 2290000 | 1965947 | Green | Green | Red | Green | Green | As at 20251231: Change request approved to descope.
Q2 25-26 | Department of Transport and Planning | DTP | 3953 | OneDigital Workplace | Transport and Vehicles | Customer Preferences,Development and Integration ,Organisational Management ,Security Management ,Systems Management | Delivering a new Standard Operating Environment and operating model for the DTP so that all users can access a modern and consistent desktop environment. Includes rationalisation of ITSM tools (ServiceNow). | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2026-06-30 | 2025-02-28 | 2025-02-28 | 10000000 | 0 | 2025-03-03 |  | 2026-06-30 | 2026-12-30 | 10000000 | 10001234 |  | Green | Green | Green | Green | Overall program status is green and is on track.
Q2 25-26 | Melbourne Water | MELB Water | 3954 | Standalone Server Refresh | Environment and Water | Assets/Materials Management | Standalone servers at or approaching end of life &/or end of support require upgrading to meet ongoing operational requirements. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-08-09 | 2024-10-30 |  | 2024-11-13 | 0 |  | 2024-11-13 |  | 2026-03-12 | 2026-06-17 | 1992000 |  | Green | Green | Green | Green | Green | As at 20251231: Change Request to be submitted for additional requirements.
Q2 25-26 | Melbourne & Olympic Parks | M&OP | 3955 | End of Life Switch Replacement 2024/25 | Culture, Sport and Recreation | Systems Management | The project will replace end-of-life hardware to maintain support for the network switch environment, enabling the organisation to minimise legacy system risks and improve security. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2024-05-01 | 2024-07-01 |  | 2024-07-01 | 0 |  | 2024-07-15 |  | 2025-06-30 | 2026-11-30 | 2750000 |  | Green | Amber | Amber | Amber | Amber | Phase 1 deliverables on track for completion targeting Q3 25-26. Project reporting AMBER until Phase 2 planning is finalised, and implementation completion date confirmed considerate of BAU event schedule.
Q2 25-26 | Department of Education | DE | 3956 | Brief Connect | Education | Content Management,Data Management,Document Management ,Management of Process ,Reporting ,Tracking and Workflow | The project will deliver a workflow solution for managing all departmental briefings and correspondence. This solution will enhance the depts digital capabilities by utilising existing Cloud Service. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-12 | 2023-07-04 |  | 2023-09-05 | 0 |  | 2024-07-29 |  | 2025-03-07 | 2026-03-31 | 2657628 | 3757628 | Green | Amber | Green | Green | Amber | The project is AMBER due to schedule delays caused by issues identified in User Acceptance Testing and alignment with other cross departmental systems. Minor development is underway to resolve remaining issues.
Q2 25-26 | Department of Education | DE | 3961 | Securing Connected Learners (SCL) Program – Phase 2 | Education | Development and Integration ,Security Management ,Systems Management | SCL is a ‘high profile’ program of work creating enhanced security capabilities for schools initially addressing child safety & security risks in schools by transitioning schools to platforms with enhanced cyber security features. | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-01 | 2024-06-03 |  | 2024-06-03 | 0 |  | 2024-06-03 |  | 2025-06-30 | 2026-06-30 | 3100000 | 6098000 | Amber | Amber | Amber | Amber | Amber | Project has been extended by 12 months and budget increased to address a number of additional cyber security remediation activities to extend child safety and security across a wider number of schools.
Q2 25-26 | Department of Education | DE | 3963 | 50 Early Learning Childcare Centres - Technology Components | Education | Customer Relationship Management | The project will deliver the required technology components in 50 ELC centres to support the Victorian Government initiative in broader early learning, enabling great start for young Victorians. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-15 | 2024-03-15 |  | 2024-03-18 | 0 |  | 2024-03-18 |  | 2032-06-30 |  | 2108035 | 4205068 | Green | Green | Green | Green | Green | The project is GREEN and is on track to finalise delivery of the ICT component for the 18 Early Learning Childcare Centre sites budgeted for this financial year with 14 planned to open doors on the 28 January 2026.
Q2 25-26 | State Revenue Office | SRO | 3965 | Vacant Residential Land Tax 2 | Government and Economy | Development and Integration | This project will expand the Vacant Residential Land Tax (VRLT) system to collect and administrate VRLT across all Victorian properties from January 2025 and underdeveloped residential land in Greater Melbourne areas from January 2026. | Delivery | Social Improvement (Non Financial) |  | Agile | 2024-05-23 | 2024-06-30 |  | 2024-06-30 | 35000 |  | 2024-07-01 |  | 2026-06-30 |  | 1927652 | 4738171 | Amber | Amber | Green | Green | Green | The project is on track to deliver the 2026 changes. The budget increase is to reflect the full scope delivery including the 2026 changes.
Q2 25-26 | Alfred Health | ALFRED | 3968 | Disaster Recovery | Health | Security Management | The Disaster Recovery project will enhance ICT infrastructure for disaster recovery, prioritizing patient safety and data integrity by establishing a robust, adaptable ICT environment that maintains continuous operations during disruptions. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-10-21 |  | 2024-10-21 | 148217 | 69382 | 2024-10-28 |  | 2026-07-01 |  | 1171783 | 1250618 | Green | Green | Green | Green | Green | The project is on track.
Q2 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3977 | Energy Customer Relationship Management (CRM) Project | Government and Economy | Customer Relationship Management | The Energy CRM Project will deliver a customer management system to enable DEECA's Energy Group to deliver best practice stakeholder engagement and more efficient government processes. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-04 | 2024-12-11 |  | 2024-12-11 | 150000 |  | 2024-12-12 |  | 2025-06-30 | 2026-04-30 | 1277120 | 1250822 | Green | Amber | Green | Green | Green | The project is tracking well against scope budget and schedule. Stage 1 has been successfully completed. Stage 2 delivery has commenced a re-baseline was approved to complete the delivery by the end of Q4.
Q2 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3980 | FireWeb Decommissioning Project | Emergencies and Safety | Management of Process | The FireWeb Decommissioning Project will replace the legacy system FireWeb to improve the accessibility of the information. This infrastructure will be DEECA's primary source for Fire Management. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-01 | 2024-06-30 |  | 2024-06-30 | 0 |  | 2024-07-01 |  | 2028-06-30 |  | 5047000 |  | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q2 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3981 | Emergency Management (EM) Deployment Project | Emergencies and Safety | Management of Process | The EM Deployment project will deliver a modern system to plan and coordinate the commitments and resources for bushfire and other emergency incidents to increase DEECA's capabilities to manage these incidents effectively and in a timely manner. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-01 | 2024-06-30 |  | 2024-06-30 | 0 |  | 2024-07-01 |  | 2026-12-31 | 2026-12-31 | 1223000 |  | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule with a planned incremental increase in spend.
Q2 25-26 | Department of Government Services | DGS | 3982 | Service Victoria - Firearms & Private Security Digital Program - Phase 1 | Government and Economy | Customer Initiated Assistance,Management of Process | The project will deliver a minimum viable product to digitise the Firearms licence renewal process, in addition to enabling Firearms licence holders to obtain and securely store their licences in a digital form through Service Victoria app | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-09-01 | 2024-03-01 |  | 2024-03-01 | 0 |  | 2024-03-01 |  | 2025-06-30 | 2026-01-30 | 2239255 | 1800000 | Green | Green | Green | Green | Green | The project remains on track with respect to the approved scope budget and schedule with pilot delivery having commenced in August 2025.
Q2 25-26 | Peninsula Health | PEN Health | 3985 | Peninsula Health Replacement of legacy Citrix virtual desktop environment & virtual server infrastructure | Health | Systems Management | Replacement of legacy Virtual Desktop and Converged Infrastructure at Frankston Hospital providing clinical application access to all sites, increasing usability and access for all staff to applications and data, including Video conference/telehealth | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-03-04 | 2024-10-18 |  | 2024-10-18 | 10000 |  | 2024-10-18 | 2024-10-21 | 2026-02-27 |  | 7329269 | 7982065 | Green | Green | Green | Green | Green | The build of the virtual desktop management platform is completed with business as usual support process established and confirmed with the vendor. The project continues with server migration (68% of server migrated), decommission of the legacy desktop environment, and the delivery of firewall scope.
Q2 25-26 | Department of Health | DH | 3987 | Donor Conception Register IT System | Health | Customer Relationship Management | Deliver a new IT system to manage Victoria's donor conception registers and allow applicants (donors, donor-conceived persons', parents, and their families) to request information under the legislation. | Postponed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial) | 2024-09-01 | Agile | 2024-01-15 | 2024-03-26 |  | 2024-03-26 | 7800 |  | 2024-04-01 |  | 2025-06-30 |  | 1522446 |  | Green | Green | Red | Red | Red | Major components of the system were delivered and the project remains on hold. Delivery will progress once the revised scope and remaining funding are confirmed.
Q2 25-26 | South East Water | SE Water | 3989 | CRUX - Stabilisation | Environment and Water | Financial Management | Uplift of ERP solution implemented in 2023. Including Finance Procurement & Project Management functions. | Delivery | Cost Reduction (Financial) |  | Waterfall | 2024-07-01 | 2024-12-20 |  | 2024-12-20 | 0 |  | 2025-01-27 |  | 2026-01-30 | 2026-04-30 | 3510000 | 3990000 |  | Green | Green | Amber | Amber | Project currently AMBER due to delays in closing out remaining modules due to change in priorities. Resources have now been secured and plan to complete remaining deliverables in FY26 Q3.
Q2 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3991 | Victorian Water Register (VWR) Evolve Project | Environment and Water | Development and Integration | The VWR Evolve Project will uplift the Victorian Water Register to a supported platform to improve the integrity security and reliability of Victoria's water market and enable future improvements in service delivery and information sharing. | Initiated |  |  | PRINCE2 | 2024-07-01 | 2025-05-31 | 2026-03-31 |  | 0 | 4233990 | [11 empty] | Procurement was initiated in the September 2025 quarter and progressed in the December 2025 quarter to secure a suitable Implementation Partner to support project execution. This follows successful completion of a proof of concept and approval of the project business case in 2024-25.
Q2 25-26 | Melbourne Water | MELB Water | 3992 | Routine Telecommunications Upgrades FY24-26 | Environment and Water | Assets/Materials Management | Upgrade and replacement of degrading IT network cabling and devices - including microwave dishes 4G boosters WAPs and GWIP services. | Initiated |  |  | PMBoK | 2024-10-04 | 2025-02-13 | 2026-07-01 |  | 0 | [12 empty] | As at 20251231: Business case submitted for approval.
Q2 25-26 | Eastern Health | EH | 3994 | Eastern Health EMR and Digitisation in the home | Health | Development and Integration | This project implements the EMR workflows across Care@Home services at Eastern Health alongside new integrated electronic logistics and fleet management applications to improve the coordination and delivery of care outside the hospital walls. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-28 | 2023-06-28 |  | 2023-06-28 | 420139 |  | 2024-12-06 |  | 2025-08-31 | 2026-03-31 | 4832935 |  | Green | Green | Amber | Amber | Green | The project timeline is being finalised with vendor before seeking endorsement from Steering Committee in early 2026. Tentative go live date in April 2026.
Q2 25-26 | Eastern Health | EH | 3996 | Eastern Health EMR Mobility and Enterprise Extension (Acute) | Health | Development and Integration | The EMR Mobility and Extension (Acute) Program aims to expand EMR footprint at Angliss and Maroondah Hospitals, simplify clinician workflows and patient information access, and implement EMR Mobility solutions while decommissioning legacy systems. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-01 | 2025-02-28 |  | 2025-02-28 | 0 |  | 2025-03-01 |  | 2025-12-15 | 2026-04-10 | 9979000 |  |  | Green | Green | Amber | Green | Throughout 2025 the EMR Mobility and Enterprise Extension changes have successfully gone live at Box Hill Hospital Blackburn Public Surgical Centre and Maroondah Hospital. In parallel the project steering committee have agreed the Angliss Hospital go live to move to 10th March 2026. The December EMR Steering Committee agreed for the status to reflective Green which includes acknowledging continued work between EH project team and vendors to provide mitigations and resolution of outstanding warranty items.
Q2 25-26 | Eastern Health | EH | 4000 | Advancing Cancer Services through Digital Chemotherapy Project | Health | Development and Integration | This project implements the EMR Oncology modules to all Eastern Health sites where Cancer Services are delivered providing electronic cancer medication prescription and management for more safe and timely care. | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-11-01 | 2025-02-28 |  | 2025-02-28 | 0 | 511021 | 2025-03-31 |  | 2026-05-31 |  | 3438979 |  |  | Green | Green | Green | Amber | The December Steering committee agreed that the timeline will be extended to allowing for scheduling solution to be built and validated. However final timeline to be presented in February SC meeting before approval of a rebaselined schedule. The project's focus has been on Scheduling Design Phase with focus on determining a scheduling and correspondence solution while in parallel continuing to build and validate treatment protocols.
Q2 25-26 | WorkSafe Victoria | WorkSafe | 4002 | Mature Platform to Target State | Employment, Skills and Workplace | Analyses and Statistics ,Business Intelligence,Data Management | The Mature Platform work has been defined to complete the implementation of the data pipelines and data objects in the EDH aligned to the approved target state architecture and transform and uplift operational processes aligned to new architecture. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-23 | 2024-10-31 |  | 2024-10-31 | 85310 |  | 2025-01-02 |  | 2025-12-31 |  | 1536799 |  |  | Green | Green | Green | Red | The project has exceeded its current baseline closure date. A formal change request extending the schedule and funding for delivery of remaining scope items has been raised to return the project to a Green status and is pending final approval.
Q2 25-26 | WorkSafe Victoria | WorkSafe | 4003 | Return to Work Product Pipeline Implementation | Employment, Skills and Workplace | Analyses and Statistics ,Business Intelligence,Data Management | Deployment of a production-grade Return to Work (RTW) Dashboard Product to business users including operational support processes user training and change management. As well as automated ingestion of Australian Bureau of Statistics data. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-23 | 2024-10-31 |  | 2024-10-31 | 60290 |  | 2025-01-02 |  | 2025-12-31 | 2026-03-31 | 1318806 |  |  | Amber | Green | Amber | Red | The project is behind schedule as build effort exceeds the baseline time-boxed plan. A change request for a 3-month extension and additional funds is pending approval. A checkpoint has been set in Q3 to assess progress and confirm next steps for returning project to Green.
Q2 25-26 | WorkSafe Victoria | WorkSafe | 4004 | Oracle Exadata Platform Refresh | Employment, Skills and Workplace | Systems Management | The project will upgrade the existing Oracle Exadata platform to improve/uplift Oracle Capacity and performance to meet current and future application landscape expansion. | Closed - Completed | Cost Reduction (Financial) | 2025-11-28 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-05 | 2024-11-29 |  | 2024-11-29 | 240072 |  | 2024-12-01 |  | 2025-10-27 | 2025-11-28 | 2269561 |  | Green | Green | Green | Green | Green | Project completed
Q2 25-26 | Department of Health | DH | 4005 | Enterprise Operational Workforce Management System | Community Services | Human Capital / Workforce Management | Replace end-of-life Rostering, Time and Attendance systems for disability residential services, child protection, emergency response and maternal child health divisions across DFFH and DH to enhance workforce management and improve service delivery. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2023-12-14 | 2024-09-30 |  | 2024-09-30 | 239974 |  | 2024-10-01 |  | 2026-06-30 |  | 3518876 |  | Green | Green | Green | Green | Green | Project is progressing to cost and schedule.
Q2 25-26 | CenITex | CenITex | 4008 | AWS and Azure Cloud Landing Zone deployment | Government and Economy | Assets/Materials Management | This project iteratively implements Landing Zone feature enhancements. The focus is security enhancement standards implementation. Landing Zone “Official” security status implementation and delivery of a new cost model for efficient Cloud consumption | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | PRINCE2 | 2023-05-01 | 2023-06-30 |  | 2023-06-30 | 0 |  | 2023-07-01 |  | 2025-06-30 | 2026-03-31 | 1420000 | 1433831 | Green | Green | Green | Green | Green | Project is tracking to plan.
Q2 25-26 | CenITex | CenITex | 4009 | DC Exit Network Establishment – Phase 2 | Government and Economy | Assets/Materials Management | To establish a network extension from Burwood to Equinix ME2 using VicTrack colocation service at Equinix and then execute the base network infrastructure required at the data centre to start migrating Cenitex workloads out of Burwood to Equinix. | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2024-11-01 | 2024-11-30 |  | 2024-11-30 | 0 |  | 2024-12-01 |  | 2025-10-30 | 2026-02-28 | 1993326 | 2986585 | Green | Amber | Green | Green | Green | Project is tracking to plan
Q2 25-26 | Goulburn Valley Region Water Corporation | GVR Water | 4011 | SCADA System Replacement | Environment and Water | Assets/Materials Management,Communication,Data Management,Systems Management | Replacement of the Supervisory Control and Data Acquisition (SCADA) System to ensure GVW's core operational monitoring and automation system remains fit for purpose and reduce business continuity risk. | Initiated |  |  | PMBoK | 2023-05-01 | 2025-04-30 | 2026-04-30 |  | 200000 | 415000 | [11 empty] | GVW has completed part of the procurement, namely the software licensing arrangement with a service provider for SCADA licenses. GVW is now intending to engage an integrator to begin the implementation of the project for which we have received Board approval to begin the process.
Q2 25-26 | Hume Rural Health Alliance | HRHA | 4012 | Hume Regional EMR Preparation Project | Health | Customer Relationship Management,Records Management | The project will develop and deliver a series of business readiness activities prior to the full implementation of a whole of Hume Rural Health Alliance Electronic Medical Record (EMR), ensuring all IT environments are ready for the roll-out | Delivery | Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-13 | 2025-12-31 | 2025-03-31 | 2025-04-30 | 0 | 200000 | 2025-05-01 |  | 2026-06-30 |  | 4200000 |  |  |  | Green | Green | Green | The focus is on undertaking procurement activities including the release of the Expression of Interest to the Market and assessment of responses.
Q2 25-26 | Victorian Funds Management Corporation | VFMC | 4013 | Migration to cloud | Business and Industry | Systems Management | This project will transition our investment management system from an on-premises setup to a managed service offering, enhancing support, security and access to new functionality for our core technology platform. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-05-01 | 2024-05-28 |  | 2024-05-28 | 0 |  | 2024-12-01 |  | 2025-12-31 | 2026-03-31 | 2787000 |  | Green | Amber | Amber | Amber | Amber | User Acceptance Testing (UAT) is ongoing with critical bugs remaining unresolved. Go-live planning has commenced including review of the joint go-live runbook and preparation. The project remains at risk for go-live deadline.
Q2 25-26 | Transport Accident Commission | TAC | 4030 | Oracle Exadata Platform Refresh | Transport and Vehicles | Systems Management | The project will upgrade the existing Oracle Exadata platform to improve/uplift Oracle Capacity and performance to meet current and future application landscape expansion. | Closed - Completed | Cost Reduction (Financial) | 2025-10-27 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-04 | 2024-11-29 |  | 2024-11-29 | 160048 |  | 2024-12-01 |  | 2025-10-27 |  | 1513041 |  | Green | Green | Green | Green | Green | The project has been completed according to the plan.
Q2 25-26 | State Revenue Office | SRO | 4045 | Revenue Management System - Foundation | Government and Economy | Development and Integration | The Revenue Management System (RMS) is the core backend software & technology managing tax-related activities for all customers. This initiative aims to establish the technical foundations to transition all revenue lines to utilise modern technology. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-02-03 | 2025-06-30 |  | 2025-07-01 | 1370114 |  | 2025-07-02 |  | 2026-06-30 |  | 11665000 |  |  |  |  | Amber | Amber | Resourcing issues have caused minor delays. Return to green plan in place.
Q2 25-26 | Peninsula Health | PEN Health | 4046 | Patient Flow Management Solution | Health | Organisational Management | Electronic Patient Flow Management streamlines patient movement, enhances collaboration, optimises access and demand management, reduces length of stay, improves communication, and increases workplace satisfaction and providing bed visibility. | Delivery | Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2023-09-08 | 2024-06-10 |  | 2024-08-07 | 50000 |  | 2024-12-20 |  | 2026-01-29 | 2026-04-30 | 2440404 |  |  | Green | Green | Green | Green | On track for go live. Superuser Training Application Training and initial round of User Acceptance Testing underway.
Q2 25-26 | VicGrid | VicGrid | 4048 | VicGrid Finance & Procurement - System Establishment | Energy and Resources | Financial Management | The project will deliver the system to manage finances, budgets, and procurement processes for VicGrid, in line with VicGrid's requirements and in compliance with Whole of Victorian Government information security standards. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) | 2025-11-14 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-11-18 | 2024-12-17 |  | 2024-12-17 | 0 |  | 2025-02-03 |  | 2025-06-30 | 2025-10-31 | 1490000 |  |  | Green | Green | Green | Green | The project has completed on time (01-Nov-2025) with the go-live of the Finance & Procurement management system, and the hyper-care successfully ending on 14-Nov-2025.
Q2 25-26 | Victorian Legal Services Board & Commissioner | VLSBC | 4049 | Regulatory Management System | Law and Justice | Customer Relationship Management | A Regulatory Management System will be delivered. Replacement of legacy systems will improve delivery of service and modernisation of legal regulatory systems will support legal regulation in Victoria. | Postponed | Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2025-02-25 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-11-10 | 2023-08-22 |  | 2023-08-22 | 330680 |  | 2023-11-27 |  | 2026-05-01 |  | 18400000 |  |  | Red | Amber | Amber | Amber | Project delivery is currently postponed. The vendor completed a technical release and is no longer contracted to deliver the remaining scope. The remaining business requirements have been reviewed and updated. A Request for Proposal for a new system integrator for the remaining scope was released in October 2025. Tender responses are currently being evaluated. Once a vendor has been selected, delivery activities will recommence with a revised budget and schedule,
Q2 25-26 | Liquor Control Victoria | LCV | 4050 | Liquor Control Victoria ICT relocation and support for hardware and software | Law and Justice | Systems Management | The project will relocate on-premises servers to Richmond, decommission legacy hardware, and improve software and hardware support to enable business continuity | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-04-01 | 2024-12-01 | 2025-03-31 | 2025-03-31 | 0 |  | 2025-06-27 |  | 2026-01-31 | 2026-06-30 | 4373050 |  |  |  | Green | Green | Green | The project is tracking well against budget and scope. The server relocation was completed in July 2025. Work is underway to enable the transition of systems and support from the Victorian Gambling and Casino Control Commission (VGCCC) to LCV. The end date was revised to align with the staged transition of approximately 40 ICT contracts from VGCCC to LCV. These contracts have varying end dates through to June 2026 and are being progressed based on criticality and business continuity requirements, with VGCCC cost reimbursements reducing as transitions are completed.
Q2 25-26 | Liquor Control Victoria | LCV | 4051 | New liquor platform for Liquor Control Victoria (delivered by Service Victoria) | Law and Justice | Customer Initiated Assistance | The project will deliver online licence application forms and a digital proof of age card. Efficiency and data quality will be enhanced, resulting in an improved user experience. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2022-07-01 |  | 2022-07-01 | 0 |  | 2022-10-01 | 2023-06-01 | 2026-06-30 |  | 4580000 | 6835000 |  | Green | Green | Green | Green | The project is tracking well against budget, schedule and scope. Planning for the next tranche of digital forms is underway.
Q2 25-26 | South West Alliance of Rural Health | SWARH | 4052 | Windows Server Upgrades | Health | Assets/Materials Management | Upgrade of operating systems across SWARH Server environment​. This will provide enhanced performance and scalability of IT infrastructure and simplify management and streamline operations through modern tools and features. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2025-12-30 | Waterfall | 2025-01-31 | 2025-02-01 |  | 2025-02-01 | 5000 |  | 2025-02-28 |  | 2026-12-20 |  | 2806000 |  |  | Green | Green | Green | Green | The upgrade of operating systems across the SWARH server environment has been completed.
Q2 25-26 | South West Alliance of Rural Health | SWARH | 4053 | PACS Replacement | Health | Systems Management | Raplace the existing medial imaging Picture Archiving Communication System (PACS) used by Barwon Health Medical Imaging services. The current system is old and now unsupported with no capacity to upgrade to a new version. | Delivery | Efficiency/Productivity (Non Financial) |  | Waterfall | 2024-09-01 | 2025-01-16 |  | 2025-01-16 | 5000 |  | 2025-02-01 |  | 2025-10-30 | 2026-02-27 | 2295508 |  |  | Green | Green | Red | Red | The PACS replacement project is progressing, addressing end-of-life system risks, with a short schedule adjustment related to vendor technical matters.
Q2 25-26 | Department of Jobs, Skills, Industry and Regions | DJSIR | 4055 | TAFE Customer Relationship Management (CRM) tool phase 2 | Education | Customer Relationship Management | The Office of TAFE Coordination and Delivery and the TAFE Network work to improve student experiences and industry outcomes. This phase launches a modern CRM to streamline enrolments at two TAFEs and boost industry engagement across six. | Postponed | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2025-11-28 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-17 | 2024-11-30 |  | 2025-02-19 | 1 |  | 2025-03-24 |  | 2025-11-30 |  | 4718530 |  |  | Green | Green | Amber | Amber | The project was placed on hold in November 2025 to reassess the remaining scope and dependencies. The project is expected to resume in Q3 2025-26 pending governance approval of the revised plan.
Q2 25-26 | Department of Transport and Planning | DTP | 4056 | Two-way radio | Transport and Vehicles | Communication | The project will leverage the state emergency radio network to implement two-way radio communication system, enabling enhanced safety of roadside operations through real-time location monitoring, duress alarm capability, and broader coverage. | Delivery | Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-01-01 | 2024-12-31 |  | 2025-01-06 | 0 |  | 2025-01-13 |  | 2025-12-01 | 2026-04-30 | 1507000 |  |  | Amber | Green | Green | Green | The project is tracking well against the project scope, budget, and schedule.
Q2 25-26 | Department of Transport and Planning | DTP | 4057 | OneView Separation | Transport and Vehicles | Systems Management | The project will migrate the Medical Review application to a dedicated instance of Dynamics 365 platform, addressing audit privacy concerns and ensuring stronger compliance with security standards and enhancing the protection of sensitive information | Closed - Completed | Risk Reduction (Non Financial) | 2025-11-20 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-09-24 |  | 2024-09-25 | 0 |  | 2024-10-01 |  | 2025-07-22 | 2025-11-07 | 1092420 | 1264000 |  | Green | Amber | Green | Green | The project delivery is now complete.
Q2 25-26 | Department of Transport and Planning | DTP | 4058 | Transport Victoria website Release 2 and Release 3 | Transport and Vehicles | Development and Integration | The project will consolidate existing digital channels, delivering an enhanced customer experience that integrates all modes of transport, and enables longer term operational efficiencies by simplifying the underlying technical infrastructure. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-08-01 | 2025-01-06 |  | 2025-01-06 | 0 |  | 2025-01-13 |  | 2026-06-30 |  | 8119044 |  |  | Amber | Amber | Amber | Green | The project status is green and tracking well against scope, budget and schedule.
Q2 25-26 | Department of Transport and Planning | DTP | 4059 | Pay Portal for Public Transport Ticketing (PTT) | Transport and Vehicles | Development and Integration | The project will roll out a digital pay portal, enabling commuters to interact with the new public transport ticketing (PTT) system, providing faster and easier ticketing transactions for Victorian commuters. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-12-02 | 2025-02-28 |  | 2025-03-03 | 0 |  | 2025-03-03 |  | 2027-05-13 | 2027-06-30 | 16700000 |  |  | Amber | Amber | Amber | Green | The project is on track with its budget, scope, and schedule.
Q2 25-26 | South West Alliance of Rural Health | SWARH | 4060 | Citrix environment upgrade | Health | Systems Management | Upgrade to the current Long Term Service Release (LTSR) of Citrix to improve platform performance and supportability. | Delivery | Efficiency/Productivity (Non Financial) |  | Waterfall | 2024-10-01 | 2024-10-30 |  | 2024-11-30 | 5000 |  | 2025-01-01 |  | 2025-05-31 | 2026-03-01 | 4467000 |  |  | Green | Green | Amber | Amber | Planning and pilot phases for the Citrix Long Term Service Release upgrade have been completed, with full deployment scheduled for March 2026.
Q2 25-26 | WorkSafe Victoria | WorkSafe | 4062 | Claims Systems Modernisation Initiative - Phase 1 | Employment, Skills and Workplace | Customer Relationship Management | The project will deliver a new claim management solution based on the already established CRM platform uplifting both usability & functionality to improve claims management. Phase 1 will roll out the functionality to WorkSafe's internal claims team. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-02-24 | 2025-02-24 |  | 2025-02-24 | 0 |  | 2025-02-25 |  | 2025-12-31 | 2026-06-30 | 36083436 | 40666844 |  | Green | Amber | Red | Amber | A project change request was approved in December 2025 extending schedule and funding and adjusting scope. Overall status will move back to Green once project completes re-baselining to the approved change request and aligns milestones to schedule.
Q2 25-26 | South East Water | SE Water | 4064 | Asset Management Platform Uplift | Environment and Water | Assets/Materials Management | Upgrade of SEW's Asset Management system from on-premise to cloud including major version uplift. | Closed - Completed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2025-12-19 | Waterfall | 2024-07-01 | 2025-03-15 |  | 2025-03-15 | 0 |  | 2025-03-17 |  | 2025-12-19 |  | 1305000 |  |  | Green | Amber | Green | Green | Project is reporting GREEN after the successful go-live of the new cloud platform in September. Successfully completed hypercare and project in the process of being closed.
Q2 25-26 | South East Water | SE Water | 4065 | Enterprise Telephony Uplift | Environment and Water | Communication | Replacement and uplift of SEW's enterprise telephony solution across the organisation. | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial) |  | Waterfall | 2025-01-06 | 2025-02-28 |  | 2025-03-03 | 0 |  | 2025-03-03 |  | 2025-11-30 | 2026-03-31 | 1220000 |  |  | Green | Green | Green | Green | All major deliverables and onboarding of contact centre functions to new telephony solution completed. Remaining work to close out self-serve functionality complete Penetration Testing and decommission legacy telephony system.
Q2 25-26 | CenITex | CenITex | 4066 | Software Defined Datacentre (SDDC) Migration | Government and Economy | Assets/Materials Management | To design configure and consume an alternate VMWare based Private Cloud platform, and migrate Cenitex and customer applications from the current platform to the Multicloud solutions including a new IaaS Platform with built-in backup capability. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | PRINCE2 | 2025-02-21 | 2025-04-01 | 2025-02-27 | 2025-02-27 | 0 |  | 2025-11-30 | 2025-03-10 | 2025-11-30 | 2026-02-28 | 1431025 | 1427929 |  | Green | Green | Green | Green | Project is tracking to plan
Q2 25-26 | Peter MacCallum Cancer Centre | Peter MAC | 4069 | High Performance Compute and Storage infrastructure refresh and upgrade (HPC) | Health | Assets/Materials Management,Systems Management | The project will deliver a refreshed and upgraded High Performance Compute (HPC) and Storage infrastructure for Peter Mac Research, replacing outdated hardware with advanced, high-performance equipment. | Initiated |  |  | PRINCE2 | 2024-10-01 | 2025-11-28 | 2026-06-30 |  | 0 | [12 empty] | Business case has been drafted and is planned to be presented to the Board to seek funding approval.
Q2 25-26 | Peter MacCallum Cancer Centre | Peter MAC | 4070 | Network Infrastructure Refresh | Health | Assets/Materials Management,Systems Management | The project will deliver a comprehensive refresh of Peter Mac's network infrastructure, including all physical components and the provision of layer 2 and layer 3 services across the WAN, LAN, and WLAN. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-10-01 | 2025-10-31 | 2025-07-23 | 2025-07-23 | 0 |  | 2025-10-01 |  | 2026-12-31 |  | 6773270 | [5 empty] | Green | Design and implementation planning is progressing on track.
Q2 25-26 | State Revenue Office | SRO | 4071 | Inbound Correspondence | Government and Economy | Development and Integration | This Project focuses on inbound communication – phone calls, forms, and emails initially. It aims to enhance data quality, streamline processes, and improve communication channels to deliver a seamless customer experience and boost staff productivity | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Customer Satisfaction (Non Financial) |  | Agile | 2025-02-01 | 2025-06-30 |  | 2025-07-01 | 181072 |  | 2025-07-02 |  | 2026-06-30 |  | 5390331 |  |  |  |  | Amber | Amber | Project status is amber due to resourcing issues causing delays to delivery. Return to green plan in place.
Q2 25-26 | State Revenue Office | SRO | 4072 | Enabling Technology | Government and Economy | Development and Integration | This project is establishing enabling technologies and processes to enhance security and uplifting capabilities for future project delivery. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2025-02-01 | 2025-06-30 |  | 2025-07-01 | 294163 |  | 2025-07-02 |  | 2026-03-27 |  | 1232673 |  |  |  |  | Amber | Amber | Reporting amber due to minor delays. Return to green plan in place.
Q2 25-26 | Western Health | WH | 4073 | Network Switches Asset Replacement 23/24 | Health | Development and Integration | End of life replacement of network switches at Sunshine Hospital to ensure network reliability, supportability and security, enabling WH to deliver services for the future, high quality connected care and better health outcomes for our community. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2024-01-02 | 2024-02-23 |  | 2024-02-26 | 0 |  | 2024-11-18 |  | 2025-08-26 | 2026-05-29 | 4156643 |  |  | Green | Green | Green | Green | Phase 3 (final) stage deferred by steering committee until after patient migration to new Footscray Hospital to ensure ICT infrastructure stability.
Q2 25-26 | Grampians Rural Health Alliance | GRHA | 4074 | Grampians Health Success Factors Phase 3 | Health | Human Resources | The regional adoption of the full Grampians Health instance of SAP Success Factors by GRHA Health Services (Core HR, Recruitment, Onboarding, Payroll, Performance & Goals and Integration Centre). | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-05-05 | 2025-10-31 | 2026-02-27 |  | 78000 | [12 empty] | Tender contract negotiations still in progress with an expected completion in Feb 2026.
Q2 25-26 | Melbourne Water | MELB Water | 4076 | Mobile Device Management | Environment and Water | Assets/Materials Management | Enhance support for flexible remote working arrangements for staff improving management of corporate devices by implementing a system that effectively addresses the challenges of remote device management and supports Bring your own device policies. | Postponed |  | 2025-09-08 | PMBoK | 2024-08-21 | 2025-05-21 | 2026-09-12 |  | 0 | [5 empty] | 0 | [6 empty] | As at 20251231: The project has been deferred and is now scheduled for delivery in FY2027.
Q2 25-26 | Department of Education | DE | 4078 | Academy Customer Relationship Management_Course Management | Education | Customer Relationship Management,Data Management,Reporting | The project will improve business processes focusing on the Victorian Academy of Teaching and Leadership’s relationship management and enables the effective marketing management delivery and reporting of professional learning to Victorian educators. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-01 | 2024-08-16 |  | 2024-08-30 | 0 |  | 2025-01-28 |  | 2026-08-13 |  | 9649702 |  |  | Green | Green | Amber | Amber | The project is AMBER due to schedule delays from two integration issues and capacity to support data migration activities. Solutions are being assessed. The final parts of the build are in progress. The project is expected to return to GREEN upon resolution of integration and capacity issues.
Q2 25-26 | Yarra Valley Water | YV Water | 4080 | IT Systems Monitoring & Logging | Environment and Water | Security Management ,Systems Management,Visualisation | Implement a platform which will encompass comprehensive monitoring, logging, synthetic monitoring, and a unified monitoring dashboard to enhance security, improve reliability, and visibility into our IT infrastructure and application performance. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-02 | 2025-01-31 |  | 2025-02-04 | 48000 |  | 2025-02-04 |  | 2027-02-28 |  | 1334300 |  |  | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q2 25-26 | Department of Education | DE | 4081 | Service Tracking and Reporting Legacy (STaR) | Education | Communication,Data Management,Forms Management,Reporting ,Tracking and Workflow | The solution will uplift user experience for staff through better controls, efficient case management, robust data visualisations and reporting. Providing actionable insights to influence operational or policy changes for better student outcomes. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial) | 2025-10-19 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-01 | 2024-10-31 |  | 2024-11-20 | 0 |  | 2024-12-01 |  | 2025-06-30 | 2025-10-19 | 3000000 |  |  | Amber | Amber | Amber | Green | The project is GREEN and tracking to plan. Minor issues identified during User Acceptance Testing have been resolved in hypercare and the solution was successfully implemented. The project is now in the closed stage and closure activities are being completed.
Q2 25-26 | Department of Education | DE | 4082 | SupportED (formerly Student Support and Intervention) | Education | Analyses and Statistics ,Customer Relationship Management,Data Management,Records Management ,Routing and Scheduling,Tracking and Workflow | This solution streamlines service referrals and case management. Increasing compliance with privacy information security record keeping and other legal obligations ensuring compliance to the departments legislative and regulatory responsibilities. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial) | 2025-11-28 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-01 | 2024-12-10 |  | 2025-01-10 | 0 |  | 2025-02-19 |  | 2025-06-30 | 2025-11-28 | 3651000 | 4388720 |  | Amber | Amber | Amber | Green | The project is GREEN and has delivered a solution for the Mental Health Practitioners in November 2025 which has subsequently achieved a successful pilot. The project is now in the closed stage and closure activities are being completed.
Q2 25-26 | Victorian Fisheries Authority | VFA | 4088 | Licensing Quota Management System | Business and Industry | Customer Initiated Assistance,Data Management,Management of Process ,Reporting ,Systems Management | The project will digitise the commercial quota management, licencing and permit application process, by delivering a self-service mobile application for commercial fishers and permit holders, improving access to data and support from VFA. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-06-01 | 2022-11-14 |  | 2024-07-14 | 0 |  | 2025-01-14 |  | 2026-06-30 |  | 1450000 |  |  | Green | Green | Green | Green | The project is progressing well and remains on track against key milestones.
Q2 25-26 | Victorian Rail Track | VicTrack | 4090 | Cyber Security Roadmap | Transport and Vehicles | Security Management | To uplift the cyber-security maturity of VicTrack, fulfil our regulatory obligations under VPDSS and the Essential 8, and secure critical assets against cyber threats. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-01-31 | 2025-03-19 |  | 2025-03-19 | 0 |  | 2025-03-19 |  | 2028-06-30 |  | 12530000 |  |  |  | Amber | Green | Green | The overall program status remains green. The program will continue to monitor progress against the current baseline schedule, however it's likely some Year 1 projects will carry over to Year 2. There is no cost impact were this to occur.
Q2 25-26 | Victorian Rail Track | VicTrack | 4091 | Project Backup Server & Storage Replacement | Transport and Vehicles | Data Management | Refresh of the current storage and backup solution to improve storage capacity, introduce additional security features, uplift to provide better resilience against modern cyber-attacks. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-01-06 | 2025-06-27 |  | 2025-06-27 | 0 |  | 2025-06-27 |  | 2026-06-30 |  | 1594439 |  |  |  | Amber | Green | Green | Project is still on track to achieve the identified benefits, with in budget and on schedule.
Q2 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4094 | Payroll Technical Upgrade Project | Environment and Water | Human Resources | The project involves the technical upgrade of DEECA's SAP Payroll solution, as the current license and version support are due to expire by the end of 2025. Upgrading to SAP H4S4 is a mandatory requirement to ensure payroll business continuity. | Closed - Completed | Compliance (Non Financial), Risk Reduction (Non Financial) | 2025-12-19 | Waterfall | 2024-11-04 | 2024-12-24 |  | 2025-03-21 | 0 |  | 2025-03-21 |  | 2025-12-19 |  | 3750000 |  |  |  | Green | Green | Green | The project successfully delivered the approved scope budget and schedule. Testing and deployment to the target date in October was achieved as planned and hypercare in November completed successfully. The project is now closed.
Q2 25-26 | Victorian Public Sector Commission | VPSC | 4102 | Cloud Migration and Transformation | Government and Economy | Analyses and Statistics | Modernising VPSC’s analytics by migrating to a secure cloud platform using Microsoft Fabric, Power Platform, and Entra ID to streamline reporting, improve data quality, and enable scalable, AI-driven workforce insights. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-08-29 | 2024-12-19 |  | 2024-12-19 | 0 |  | 2025-03-21 |  | 2026-06-30 |  | 1773267 | 2097607 |  |  | Green | Green | Green | The VPSC Cloud Transformation project is progressing well. This period, the team has nearly finalised the build of the new data hub for government users and continues to progress work on the technical configuration for data ingestion.
Q2 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4103 | Common Technology Platform (CTP) Program - Phase 3 | Government and Economy | Security Management | The CTP Program was established to deliver the technology strategy via a 3-year phased approach. Phase 3 will uplift the 2 remaining platforms (spatial and digital) and enhance platforms established during previous phases. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-02-03 | 2024-12-12 |  | 2025-03-21 | 0 |  | 2025-03-21 |  | 2026-06-30 |  | 1798000 |  |  |  | Green | Green | Green | The project is on track as per the endorsed baseline delivery plan and budget.
Q2 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4104 | Cyber Security Uplift Program | Government and Economy | Security Management | Cyber Security program will deliver a set of controls, processes and education that aligns with the Victorian Cyber Security Strategy and leverages the WoVG capabilities to reduce and address cyber security risks. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-02-01 | 2024-12-12 |  | 2025-03-21 | 0 |  | 2025-03-21 |  | 2027-06-30 |  | 6034000 |  |  |  | Green | Green | Green | The project is on track as per the revised delivery plan and budget.
Q2 25-26 | Hume Rural Health Alliance | HRHA | 4106 | Cyber Security Maturity Uplift implementation | Health | Security Management | The purpose of this project is to ensure a regional uplift in Cybersecurity through reducing risks uplifting governance and risk management practices and alignment to the Department of Health's Cyber Security Assurance Framework. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-10-02 | 2024-02-12 |  | 2024-02-12 | 0 |  | 2024-07-01 |  | 2027-06-30 |  | 1950000 |  |  |  | Green | Green | Green | Project activities remain on track.
Q2 25-26 | WorkSafe Victoria | WorkSafe | 4107 | Claims Management System Uplift for Workplace Injury and Rehabilitation Compensation (WIRC) Amendment Act | Employment, Skills and Workplace | Systems Management | This project will operationalise the proposed WIRC Act Amendment Bill (now WIRC Amendment Act 2025) and uplift existing claims management systems to ensure high-quality service and improve support to users of Victoria’s workers compensation scheme. | Delivery | Compliance (Non Financial), Increased Quality (Non Financial), Social Improvement (Non Financial) |  | Waterfall | 2024-11-25 | 2025-03-05 |  | 2025-03-05 | 0 |  | 2025-03-05 |  | 2026-12-15 |  | 1728437 |  |  |  | Amber | Green | Green | On track
Q2 25-26 | South East Water | SE Water | 4108 | Service Management System Implementation | Environment and Water | Systems Management | Replacement and transformation of SEW's internal Service Management solution used across multiple business functions. This project will deliver uplift in internal capabilities and deliver efficiencies through streamlining service management processes | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial) |  | Waterfall | 2024-10-01 | 2025-03-28 |  | 2025-04-01 | 0 |  | 2025-04-01 |  | 2026-01-30 | 2026-04-30 | 1380500 |  |  |  | Green | Amber | Green | Project reporting GREEN after successful go-live and hypercare period concluded for Phase 1. Phase 1.5 and 2 are underway and on track for completion as per baselined schedule.
Q2 25-26 | South East Water | SE Water | 4109 | Payment Gateway Replacement | Environment and Water | Financial Management | Replacing current payment gateway solution which is end of life. Project will move all existing payment channels for customers across to a new provider. | Closed - Completed | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) | 2025-12-19 | Agile | 2024-06-01 | 2025-02-28 |  | 2025-03-10 | 0 |  | 2025-04-01 |  | 2025-11-30 |  | 2120000 |  |  |  | Amber | Green | Green | Project completed close out of remaining deliverables in FY26 Q2. Project has been successfully delivered and closed off.
Q2 25-26 | WorkSafe Victoria | WorkSafe | 4111 | Cheques Migration Strategy | Employment, Skills and Workplace | Financial Management | This project will operationalise the Victorian Government directive to cease cheque payments and will implement complex system changes to ensure faster payments for injured workers and providers and reduce administration costs. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial) |  | Waterfall | 2024-10-08 | 2025-05-27 |  | 2025-05-28 | 0 |  | 2025-05-28 |  | 2027-12-31 |  | 2143701 |  |  |  | Green | Green | Green | The project is on track and proactively managing implementation changes.
Q2 25-26 | Department of Transport and Planning | DTP | 4112 | Records Management Uplift - Stage 2b | Transport and Vehicles | Records Management | The project will review and refine the records management environment and consolidate organisational data into Records365, standardising and uplifting the records management solution & practices across the DTP. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-07 | 2025-07-10 | 2025-12-01 | 2025-12-01 | 0 |  | 2025-12-01 |  | 2026-06-30 |  | 3400000 | [5 empty] | Amber | The project has reported an amber status due to risks related to project costings & data migration pilot. The project, however, is on track with pilot planning activities in progress for data migration to the new records management solution & launch of all staff awareness communications.
Q2 25-26 | Melbourne Water | MELB Water | 4117 | Data Lake | Environment and Water | Data Management | Build a data warehouse solution that is scalable, secure and evolves to meet growing business insights and reporting needs of Melbourne Water. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2024-02-01 | 2024-04-02 |  | 2024-04-02 | 0 |  | 2024-04-02 |  | 2026-05-15 |  | 3301197 | 3212274 |  |  | Amber | Green | Green | As at 20251231: Continuing with data and report migration.
Q2 25-26 | CenITex | CenITex | 4118 | Cenitex Office Relocation | Government and Economy | Assets/Materials Management | Make 35C fit for Cenitex purpose to undertake its core role in providing support and technology solutions for customers across WoVG. With a lease end of Jun’25 at 80C, the timeline to undertake this work is tight with a early June relocation target. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | PRINCE2 | 2025-03-20 | 2025-03-20 |  | 2025-03-20 | 0 |  | 2025-03-20 |  | 2025-10-31 | 2026-03-31 | 2570677 | 2567674 |  |  | Green | Green | Green | Project is tracking to plan
Q2 25-26 | Victorian Rail Track | VicTrack | 4120 | HCI Replacement Project | Transport and Vehicles | Systems Management | Hyper-converged infrastructure (HCI) utilises physical servers to create a software-defined IT environment that virtualises all components of traditional hardware-based systems. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-01 | 2025-05-16 |  | 2025-05-16 | 0 |  | 2025-05-16 |  | 2026-12-31 |  | 9000000 |  |  |  | Green | Green | Green | Project is still on track to meet budget, scope and timeline.
Q2 25-26 | Department of Families, Fairness and Housing | DFFH | 4121 | Replacement Document and Records Management System | Community Services | Records Management | Replace the existing out-of-support records management system (Housing TRIM) with a new, supported record keeping system that uses cloud storage and provides staff with improved business functionality. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-11-29 | 2025-04-09 |  | 2025-04-09 | 351860 |  | 2025-04-09 |  | 2026-03-31 |  | 5898928 | 5898928 |  |  | Amber | Amber | Green | Project has successfully delivered core functionality and is expected to complete in the next reporting period.
Q2 25-26 | Melbourne Water | MELB Water | 4127 | Asset Maintenance application upgrade | Environment and Water | Tracking and Workflow | Upgrade of our asset management system to a modern platform that enhances scalability, security, and usability. Ensuring ongoing support beyond 2025, reduces operational risk, and provides advanced features and improved reporting. | Initiated |  |  | Waterfall | 2023-10-09 | 2026-04-09 | 2026-08-31 |  | 0 | [12 empty] | As at 202601206: Continuing with drafting the business case. Workshops ongoing to finalise presentation detailing recommended options for approach and scope.
Q2 25-26 | Melbourne Water | MELB Water | 4128 | SCADA For Our Future | Environment and Water | Assets/Materials Management | A next-generation system to enhance real-time monitoring, decision-making, and automation across our water, sewerage, & drainage networks. Providing advance alarm and incident management to meet growing service complexity and performance expectations | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2019-10-25 | 2025-11-25 |  | 2025-11-25 | 0 |  | 2025-11-25 |  | 2028-08-28 |  | 39352377 | [5 empty] | Red | As at 20251231: Business Case submission approved. Re-baseline of critical path requiring approval.
Q2 25-26 | Melbourne Water | MELB Water | 4129 | Dam Surveillance Information System | Environment and Water | Management of Process | Replacement of an outdated system with a modern, fully supported solution that brings enhanced automation, smarter features, and improved reporting—empowering the Water Control teams to work more efficiently and make better-informed decisions | Delivery | Risk Reduction (Non Financial) |  | Agile | 2023-05-10 | 2024-12-10 |  | 2024-12-10 | 0 |  | 2024-12-10 |  | 2026-10-05 | 2027-04-01 | 3340950 |  |  |  | Amber | Green | Green | As at 202601206: Procurement process complete vendors chosen and purchase orders raised. Network vendor has been onboarded and server designs have commenced. Application vendor purchase order has been raised is scheduled to be onboarded third week of January.
Q2 25-26 | Treasury Corporation of Victoria | TCV | 4130 | Infrastructure IT Refresh | Government and Economy | Systems Management | Deployment of a resilient IT infrastructure with cloud-based disaster recovery and secure remote access. It will enhance system uptime, disaster recovery speed and secure remote work capabilities whilst ensuring continuity of TCV’s critical systems. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial) |  | Waterfall | 2025-04-01 | 2025-04-22 |  | 2025-04-22 | 0 |  | 2025-06-20 |  | 2025-11-30 | 2026-05-31 | 1476000 | 1536000 |  |  | Green | Green | Green | The project has successfully completed disaster recovery testing that strengthened operational resilience improving performance and responsiveness for critical workloads as well as significant improvement in recovery times. Deployment of the flexible-working component is delayed due to supplier and procurement requirements but costs remain within scope.
Q2 25-26 | Western Health | WH | 4132 | Workstation on Wheels (WoW) replacement | Health | Systems Management | This project will replace end-of-life hardware for Workstations on Wheels (WoW) with updated hardware and software, enabling patient record access and update for doctors and nurses to provide quality patient care. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2025-02-24 | 2025-06-05 |  | 2025-06-06 | 0 |  | 2025-06-23 |  | 2025-11-28 | 2026-04-30 | 2400000 |  |  |  | Green | Green | Green | Schedule change approved by Steering Committee. Delay due to technical configuration issues, now resolved.
Q2 25-26 | Western Health | WH | 4134 | Network Switches Asset Replacement 24/25 | Health | Systems Management | End of life replacement of network switches across WH sites to ensure network reliability, supportability and security, enabling WH to deliver services for the future, high quality connected care and better health outcomes for our community. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2024-01-02 | 2025-04-23 |  | 2025-04-24 | 0 |  | 2025-08-04 |  | 2026-05-25 | 2026-07-24 | 2353000 |  |  |  |  | Green | Green | Detailed project schedule finish date baselined to 24-07-26 by steering committee . Equipment delivered and implementation proceeding on track.
Q2 25-26 | Holmesglen Institute of TAFE | Holmesglen TAFE | 4135 | ICT Infrastructure (Servers, LAN, Wifi, Telephony) & Data Centre Refresh | Employment, Skills and Workplace | Systems Management | The project will replace and upgrade the end-of-life ICT infrastructure and data centre with enhanced cyber security protection, minimising security risks and enabling faster, advanced technology access for students and staff at Holmesglen. | Delivery | Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2025-03-26 | 2025-07-28 | 2025-09-30 | 2025-10-07 | 0 |  | 2025-10-17 |  | 2027-12-17 |  | 32000000 | [5 empty] | Green | The project is progressing well with key contractual and initiation activities completed. Requirements‑gathering workshops have commenced across core ICT infrastructure streams and construction has begun at the Data Centre. Early engagement with stakeholders including demonstrations of the Contact Centre solution has been positive. The project remains on track as it transitions into the detailed design phase next reporting period.
Q2 25-26 | Western Health | WH | 4136 | Automatic Dispensing Cabinets (ADC) | Health | Systems Management | Implementation of automated medication cabinets replacing manual shelving for electronically tracked & secure storage of Imprest medications, enabling timely & safe medication access for staff at new Footscray Hospital delivering quality patient care | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2019-05-14 | 2019-09-04 |  | 2020-01-06 | 0 |  | 2024-03-04 |  | 2026-06-28 |  | 2502072 |  |  |  | Green | Green | Green | Project is on track
Q2 25-26 | Southern Metropolitan Cemeteries Trust | SMCT | 4137 | PeoplePro (Human Resources Information System) | Health | Human Capital / Workforce Management ,Human Resources | SMCT's current human resources system is no longer vendor-supported. A replacement system will provide greater efficiencies, employee experience, decision-making and information through more seamless data management and improved processes. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Waterfall Agile hybrid | 2022-07-28 | 2024-10-22 |  | 2024-10-22 | 311733 |  | 2024-11-18 |  | 2027-06-30 |  | 1932705 |  |  |  | Amber | Green | Green | No change - planned pause until commencement of Phase 3 in FY27
Q2 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4140 | Permissions Application Project | Environment and Water | Collaboration ,Customer Initiated Assistance,Customer Relationship Management,Tracking and Workflow | The project will deliver a new system to replace the current Wildlife Licence System, which is now at end-of-life. The new system will feature a self-service portal designed to improve user experience, streamline processes, and enhance compliance. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-01 | 2026-04-01 |  |  | 390151 | [12 empty] | The project is on track with the agreed schedule. The project has commenced procurement activities. On 15th December, the RFT closed and we are currently in tender evaluation phase. Anticipate selecting the preferred tenderer by the end of February 2026 and commencing development activities in April 2026
Q2 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4142 | Emergency Resource Management System (ERMS) Project | Emergencies and Safety | Customer Initiated Assistance,Human Capital / Workforce Management | The project will deliver a fit-for-purpose ERMS to reduce the impact of bio-security, agriculture, and other emergencies on the Victorian community and environment through timely and effective preparedness, response, relief, and recovery services. | Initiated |  |  | Hybrid - Waterfall and Agile | 2025-07-01 | 2026-01-30 |  |  | 240000 | [12 empty] | Continue through the procurement process with expectation that the project will engage the vendor in January 2026 to execute the contract.
Q2 25-26 | Hume Rural Health Alliance | HRHA | 4144 | Optima Roster System | Health | Human Capital / Workforce Management | Replacement of end-of-life Rostering system (RosterOn) with upgraded version - Optima | Closed - Completed | Compliance (Non Financial), Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) | 2025-12-31 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-04-01 | 2022-05-11 |  | 2022-05-11 | 0 |  | 2022-10-18 |  | 2024-10-31 | 2025-11-28 | 1118495 | 1711000 |  |  |  | Green | Green | "The project is completed, having delivered the roster system that has gone live in Goulburn Valley Health and Hospice, and transitioned to operation in a stable environment. All affiliated health services have been successfully onboarded."
Q2 25-26 | Court Services Victoria | CSV | 4147 | VCAT Long Term Accommodation (LTA ) - Technology Component | Law and Justice | Assets/Materials Management,Development and Integration | The objective of the project requires the preparation of the new VCAT Long Term Accommodation site to be a member of the Cenitex GSP INTERNAL Network for use by CSV/VCAT Staff and Customers. | Delivery | Customer Satisfaction (Non Financial) |  | Waterfall and Agile | 2025-05-06 | 2025-05-06 |  | 2025-05-06 | 0 |  | 2025-07-01 |  | 2026-04-30 |  | 1178028 |  |  |  |  | Green | Green | Cenitex Network 95% completed and on track.
Q2 25-26 | Barwon Region Water Corporation | BR Water | 4148 | C1419 - Smart Networks Water - Proof of Value (POV) | Environment and Water | Assets/Materials Management | The Smart Networks Water Project will procure, implement and monitor Digital Meters in a series of locations within the Barwon region to capture the benefits, costs, resourcing and effort to inform a Mass Rollout Business Case for PS28. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-10 | 2023-11-21 |  | 2023-11-21 | 376900 |  | 2024-03-04 |  | 2028-06-30 |  | 9490000 |  |  |  |  | Amber | Amber | The Smart Networks Water project delivery commenced in March 2024. The project has progressed significantly with key deliverables including the finalisation of the Digital Meter procurement process the Data and Device Management platform being productionised and the progressive updating of supporting processes.
Q2 25-26 | Barwon Region Water Corporation | BR Water | 4149 | C1441 - Smart Networks Sewer - Proof of Value (POV) | Environment and Water | Assets/Materials Management | The Smart Networks Sewer Project will trial, implement and monitor a series of Sewer Sensors and an analytics capability to capture the benefits, costs, resourcing and effort to inform a Mass Rollout Business Case for PS28. | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-10 | 2023-11-23 |  | 2023-11-23 | 251300 |  | 2024-03-04 |  | 2028-06-30 |  | 7170000 |  |  |  |  | Green | Green | The Smart Networks Sewer Proof of Value project commenced in March 2024 The project continues to progress with the ongoing trialling of both sewer sensors in higher risk locations and an analytics capability to support Barwon Water in forming a predictive view of sewer network behaviour. The knowledge being captured from these trial phases informs both the deployment and ongoing monitoring of the sewer sensors and demonstrating alignment of the trial scope with expected benefits.
Q2 25-26 | Transport Accident Commission | TAC | 4151 | Continuous Delivery 2026 | Transport and Vehicles | Systems Management | The project will deliver enhancement to TAC’s Claims Management system to uplift performance, reduce risk, and improve user experience, ensuring sustained business value and responsiveness to priorities | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2025-07-01 | 2025-07-01 |  | 2025-07-01 | 0 |  | 2025-07-01 |  | 2026-06-30 |  | 5404953 |  |  |  |  | Green | Green | The project is tracking well against the approved plan.
Q2 25-26 | Transport Accident Commission | TAC | 4152 | Microsoft Program of Work for Enterprise Readiness (M-POWER) | Transport and Vehicles | Systems Management | This project will establish a dedicated Microsoft tenancy & cloud infrastructure for TAC, streamlining enterprise systems using a modern platform & minimising the risks associated with legacy technologies to enable more efficient services to clients. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-07-01 |  | 2025-07-01 | 0 |  | 2025-07-01 |  | 2027-12-31 |  | 20000000 |  |  |  |  | Green | Green | The program delivered a strong quarter, transitioning smoothly from design to execution with increased momentum following partner onboarding. Core technical and governance foundations are in place, risks are well understood and managed, and the program is well positioned for scaled delivery and organisational readiness next quarter
Q2 25-26 | Melbourne Water | MELB Water | 4153 | Web Enhancements | Environment and Water | Content Management | Additional features to be added to MW website to deliver core functions. | Initiated |  |  | Agile | 2025-02-25 | 2026-11-10 |  |  | 0 | [12 empty] | As ay 20251231: Business case has been submitted.
Q2 25-26 | Yarra Valley Water | YV Water | 4154 | Finance Transformation | Environment and Water | Financial Management | Implementation of a new Finance system with integrations, including uplift to operating model. Key outcomes being risk reduction achieved by replacing EoL system plus aligning to business priorities of operational efficiencies and UX improvements. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-09-01 | 2026-08-28 |  |  | 1760200 | [12 empty] | The project has undertaken a formal Expression of Interest (EOI) process, ensuring compliance with government requirements. A strong response was received from vendors, providing valuable insights into implementation capability, systems integration and overall alignment with project objectives. EOI Evaluation was conducted and supported through independent probity advisor to confirm adherence to procurement process. The project had completed DTF’s risk assessment tool and Project Profile Model (PPM) for HVHR assessment.
Q2 25-26 | Melbourne Water | MELB Water | 4155 | OS Upgrade | Environment and Water | Systems Management | Upgrading all laptops and PC's to a new operating system. | Delivery | Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2024-10-24 | 2025-07-25 |  | 2025-07-25 | 0 |  | 2025-07-25 |  | 2026-02-27 |  | 1308000 | 1156849 |  |  |  | Green | Green | As at 20251231: Project is in the delivery phase.
Q2 25-26 | Yarra Valley Water | YV Water | 4156 | Customised Collections | Environment and Water | Financial Management | This project will deliver a Customised Collections solution in Oracle CC&B, uplifting YVW’s ability to segment customers and tailor debt management. It will reduce bad debt and improve outcomes for customers and the organisation. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Agile | 2020-08-01 | 2025-09-17 |  | 2025-09-18 | 888100 |  | 2025-09-18 |  | 2026-05-18 |  | 1119197 |  |  |  |  | Green | Amber | Delivery is in progress. Detailed discovery workshops with business stakeholders completed impacting the project scope. Timelines and budget being reviewed due to the scope change
Q2 25-26 | Yarra Valley Water | YV Water | 4157 | Digital Metering – Customer Solutions for New Segments | Environment and Water | Communication,Content Management,Customer Relationship Management,Development and Integration | The project will enable the implementation of the more complex customer journeys inclusive of the process uplifts required to facilitate the installation of digital meter to more complex and larger scale customer types. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-06-01 | 2025-08-31 |  | 2025-09-01 | 270000 |  | 2025-09-01 |  | 2026-06-30 |  | 2169620 |  |  |  |  | Green | Green | Priority one deliverable to remove parallel reads delivered. Design work for Bulk reactive meter replacement completed/ Build work commenced. Plan for high level priorities established Mid-tier priority deliverable implementation plan mapped out.
Q2 25-26 | WorkSafe Victoria | WorkSafe | 4158 | Safety CRM (Customer Relationship Management) | Employment, Skills and Workplace | Customer Relationship Management | This project will modernise safety inspection and notification systems to improve frontline efficiency and stakeholder experience. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-14 | 2025-05-28 |  | 2025-05-28 | 0 |  | 2025-07-01 |  | 2026-06-30 |  | 4863898 | 4994037 |  |  |  | Green | Green | The project is tracking Green, with scope of Quarter 2 being delivered as planned. The budget is also tracking green for upcoming quarters.
Q2 25-26 | Department of Government Services | DGS | 4159 | Children's Digital Program | Government and Economy | Development and Integration | Developing an end-to-end digital experience from birth to school that provides parents with a digital family organiser to manage key information about their child. | Delivery | Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-06-03 | 2025-06-24 |  | 2025-06-24 | 0 |  | 2025-06-25 |  | 2026-09-30 |  | 17003000 |  |  |  |  | Amber | Amber | The program status is Amber due to technical design complexities. Expected to return to Green with Phase 1 to be delivered by due date.
Q2 25-26 | Department of Health | DH | 4160 | Data Loss Prevention Phase 1 | Health | Security Management | Conduct detailed current state analysis of DH and DFFH Data Loss Protection (DLP) capability for emails classified as 'Protected' and 'Cabinet-in-Confidence' and implement improved DLP controls to emails, reducing risk of accidental data loss. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-10-27 | 2025-10-22 | 2025-10-22 | 74200 | 96525 | 2025-10-23 |  | 2026-06-30 |  | 1407475 | [5 empty] | Amber | Project is progressing but is reporting an amber health status due to delay in accessing required services.
Q2 25-26 | V/Line Corporation | V/Line | 4161 | TrackR Stabilisation | Transport and Vehicles | Systems Management | The objective of the project is to stabilise V/Line’s critical train and fleet operations system (TrackR). Stabilisation of TrackR will result in increase in reliability and performance of the system’s key workflows, and improve service delivery. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-09-30 |  | 2025-10-01 | 57000 |  | 2025-10-01 |  | 2027-12-31 |  | 3230000 | [5 empty] | Green | Progress has been good with no major roadblocks or issues to date.
Q2 25-26 | Goulburn-Murray Rural Water Corporation | GMR Water | 4162 | PC/Laptop Replacement | Environment and Water | Assets/Materials Management | This project will deliver 550 new PCs and laptops, enhancing Goulburn Murray Water’s IT capability by improving performance and reliability, enabling a more productive, digitally enabled workforce for better service delivery. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2025-03-25 | 2025-09-02 |  | 2025-09-02 | 0 |  | 2025-09-02 |  | 2028-06-30 |  | 1300000 |  |  |  |  | Green | Green | The project has commenced with planning and procurement activities now underway. Initial assessments of staff requirements have been completed and deployment scheduling and coordination with relevant departments are in progress.
Q2 25-26 | Melbourne Health | Melb H | 4165 | E-referral for outpatient specialist clinics | Health | Development and Integration | Implementing an Electronic Medical Record integrated e-Referral system across the 4 Parkville Precinct hospitals, which enhances management of external GP/Specialists referrals to outpatient specialist clinics and improves patient data quality | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2025-03-03 | 2025-03-05 |  | 2025-03-05 | 0 |  | 2025-09-01 |  | 2026-08-31 |  | 1180854 |  |  |  |  | Green | Green | Project initiation and establishing project governance. Project discovery phase complete.
Q2 25-26 | CenITex | CenITex | 4166 | DOH Modern Desktop Implementation | Government and Economy | Assets/Materials Management | The project will support DoH and DFFH to modernise workforce desktop environment, streamlining service provision and enabling workforce efficiency and productivity through modern technology. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2025-07-24 | 2025-07-24 |  | 2025-07-24 | 0 |  | 2025-07-31 |  | 2026-06-30 |  | 1949180 |  |  |  |  | Green | Green | Project is tracking to plan
Q2 25-26 | Barwon Region Water Corporation | BR Water | 4167 | C1073 - Information & Records Management (IRM) | Environment and Water | Content Management | This initiative aims to enhance Barwon Water Group's Information Records Management (IRM) capability through a phased maturity uplift. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-01 | 2025-09-08 |  | 2025-09-08 | 537000 |  | 2025-09-08 |  | 2026-10-31 | 2026-12-31 | 580000 |  |  |  |  | Green | Green | A cyber security challenge has delayed the implementation of Objective Gov365. The project is working with the system integrator for resolution as soon as possible.
Q2 25-26 | Bendigo Kangan Institute of TAFE | BKI TAFE | 4168 | Artificial Intelligence for Recognition of Prior Learning | Employment, Skills and Workplace | Development and Integration | On behalf of the Victorian TAFE Network, BKI will pilot an artificial intelligence (AI) solution to uplift the assessment capability in the Recognition of Prior Learning (RPL), enabling a more efficient processing time for assessors and applicants. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-08-28 | 2025-12-31 | 2026-03-31 |  | 180000 | 273000 | [11 empty] | The AI-enabled Recognition of Prior Learning (RPL) pilot continues to progress. Current activity is focused on early service design and analysis work to inform the future RPL operating model and identify priority opportunities for the use of AI within the process, using a small number of qualifications to test applicability. Over the next period, the project will review these outputs and move toward defining an implementation and procurement approach.
Q2 25-26 | South East Water | SE Water | 4170 | Acumen Phase 3 | Environment and Water | Business Intelligence | Acumen Phase 3 will deliver remaining data sources into new Acumen platform. A subset of Data Modelling will be undertaken to support the report development required to decommission the legacy data warehouse and reporting environment. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2025-05-01 | 2025-07-28 |  | 2025-07-30 | 0 |  | 2025-07-30 |  | 2026-12-18 |  | 8220471 |  |  |  |  | Green | Green | Project reporting GREEN with development completed for several data sources. Discovery and design continue for other data sources in scope for phase 3. Project on track as per baselined schedule.
Q2 25-26 | Victorian Gambling and Casino Control Commission | VGCCC | 4172 | Compass - Gambling License System (GLS) replacement project - Release 2 | Law and Justice | Customer Relationship Management | Release 2 will deliver the remaining components of the new regulatory system to replace the legacy license management system. The project will remediate and uplift VGCCC's ICT infrastructure improving ICT capabilities. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-14 | 2025-09-12 |  | 2025-09-12 | 120000 |  | 2025-09-15 |  | 2026-03-23 |  | 2541000 |  |  |  |  | Green | Green | The project is tracking well against budget, schedule and scope. Planning for the transition to the new system has commenced. The project is on track for completion in March 2026.
Q2 25-26 | Department of Health | DH | 4173 | Maternal and Child Health IT System | Health | Customer Relationship Management | Deliver a new statewide IT system to support the delivery of Maternal Child Health services, providing additional functions as well as accommodating future growth in service delivery and customer base. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Agile | 2025-03-03 | 2025-05-02 |  | 2025-05-02 | 163733 |  | 2025-05-02 |  | 2027-06-30 |  | 12286267 | 12286267 |  |  |  | Green | Amber | Project is progressing but is reporting an amber health status due to delays in finalising integration design. Workshops to complete this work are progressing and project is expected to return to green in next reporting period.
Q2 25-26 | Ambulance Victoria | AVS | 4174 | Mobile Data Network Rural (MDNR) | Health | Communication | The project will upgrade and expand communication services for emergency responders in rural Victoria, improving real-time data access to enable dispatch efficiency, enhancing paramedic safety and better patient care. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-10-08 | 2022-10-21 |  | 2022-10-21 | 24043 |  | 2024-11-14 |  | 2027-05-30 |  | 24971040 |  |  |  |  | Green | Red | The project is tracking Red due to a delay in testing commencement. A schedule change request is being proposed for governance approval and will be revised in Q3 upon approval.
Q2 25-26 | South East Water | SE Water | 4175 | Portfolio & Project Management Uplift | Environment and Water | Financial Management | South East Water is uplifting its ERP environment to enable enterprise-wide project and portfolio management. This project will enhance planning execution reporting and data integration across capital and operational projects. | Initiated |  |  | Waterfall | 2025-07-01 | 2026-02-28 | 2026-06-30 |  | 1388000 | [12 empty] | Project reporting RED as vendor not able to provide a solution that meets all mandatory requirements. Alternative solution pathways being explored with the vendor and internally. Due to the magnitude of expenditure and ongoing costs, this will require SEW board level approval to proceed.
Q2 25-26 | Emergency Services Superannuation Scheme | ESS SUPER | 4177 | NetSuite General Ledger Implementation | Business and Industry | Financial Management | ESSSuper is implementing Oracle NetSuite to replace its SunGL general ledger. The new cloud‑based system will enhance efficiency, improve resilience, and provide a secure, scalable platform that better supports the Fund's future requirements. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2025-07-01 | 2025-10-31 | 2025-10-24 | 2025-10-24 | 50000 | 42538 | 2025-11-03 |  | 2026-10-15 |  | 1282333 | [5 empty] | Green | Project tracking to plan.
Q2 25-26 | State Revenue Office | SRO | 4178 | Emergency Services Volunteers Fund | Government and Economy | Development and Integration | This project implements changes to collect the Emergency Services Volunteers Fund (ESVF) from 1 July 2025, ESVF supports a broader range of emergency services such as floods, storms and other emergencies, replacing the Fire Services Property Levy. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Agile | 2025-04-02 | 2025-06-30 |  | 2025-06-30 | 208928 |  | 2025-07-01 |  | 2026-06-30 |  | 2208201 |  |  |  |  | Green | Green | Project is tracking according to planned activities.
Q2 25-26 | State Revenue Office | SRO | 4179 | Enterprise Service Management | Government and Economy | Development and Integration | The State Revenue Office is procuring a modern Enterprise Service Management tool to provide better business outcomes with automation and self-service capabilities. This initiative procures and integrates the tool and implements the required workflow | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2025-03-05 | 2025-06-30 |  | 2025-06-30 | 29739 |  | 2025-07-01 |  | 2027-06-30 |  | 3643630 |  |  |  |  | Green | Amber | Project start-up activities advanced.
Q2 25-26 | State Electricity Commission (SEC) Victoria Pty Ltd | SECV | 4180 | One-stop shop project | Energy and Resources | Customer Initiated Assistance | Deliver a one-stop shop digital platform to enable Victorian households to be supported by information and access to SEC endorsed installers manage home electrification. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-01 | 2025-07-31 |  | 2025-07-31 | 248955 |  | 2025-08-01 |  | 2026-06-30 |  | 7417752 |  |  |  |  | Green | Amber | A project re-set in response to the solution architecture design is underway.
Q2 25-26 | State Revenue Office | SRO | 4181 | Data Lakehouse Utilisation | Government and Economy | Development and Integration | Establishing a cloud-based Data Lakehouse is a key element of the SRO's data and analytics strategy to uplift the organisation's data and analytics capacity, capability, operational efficiency and reporting. This project includes 2 use cases. | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | Agile | 2025-02-03 | 2025-06-30 |  | 2025-06-30 | 429284 |  | 2025-07-01 |  | 2026-06-30 |  | 2327800 |  |  |  |  | Green | Green | Project tracking according to plan.
Q2 25-26 | Department of Health | DH | 4183 | Victorian Patient Transport Assistance Scheme (VPTAS) System Replacement | Health | Customer Initiated Assistance | Implement a new VPTAS claims system that leverages the DFFH-DH Enterprise Payments Platform, enabling digitising of the current paper based claimant forms, providing greater efficiencies in the response to and management of claims. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-07-31 |  | 2025-07-31 | 89154 |  | 2025-08-01 |  | 2026-04-30 |  | 1710846 |  |  |  |  | Amber | Amber | Project is progressing but is reporting an amber health status due to testing issues. Project is expected to return to green in next reporting period.
Q2 25-26 | Environment Protection Authority | EPA | 4184 | MAJ143 - Land Renewal | Environment and Water | Tracking and Workflow | The project aims to enable efficient, effective and environmentally safe land development aligned with the Victorian Housing Statement (VHS). | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2025-05-01 | 2025-05-20 |  | 2025-06-18 | 0 |  | 2025-07-01 |  | 2026-07-31 | 2026-03-31 | 1540840 |  |  |  |  | Green | Amber | Project is on watch due to budget underspend however the majority of deliverables are on track and the project is transitioning to business as usual.
Q2 25-26 | Department of Families, Fairness and Housing | DFFH | 4185 | L17 Family Violence Portal phased upgrade | Community Services | Development and Integration | Upgrade the L17 Family Violence Portal, including software and infrastructure, to the latest supported version, further increasing security and ensuring continuity of service. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2025-12-01 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-02 | 2025-05-16 |  | 2025-05-21 | 0 |  | 2025-06-02 |  | 2026-02-13 |  | 1273000 |  |  |  |  | Amber | Green | Project has successfully delivered and closeout activities are underway.
Q2 25-26 | East Gippsland Regional Water Corporation | EGR Water | 4187 | Enterprise Asset Management | Environment and Water | Assets/Materials Management | It is a modern solution for managing the entire asset lifecycle supporting functions such as commissioning maintenance optimization planning reporting and analytics. The system aims to deliver operational cost savings and efficiency improvements. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-10-29 | 2025-01-31 |  | 2025-01-31 | 0 |  | 2025-05-01 |  | 2026-06-30 |  | 1993000 | 2032000 |  |  |  | Green | Green | The project is tracking well against scope, budget and schedule. Phases one has been implemented and Phase 2 is due for rollout within the next reporting period. Phase 3 is due by 30th June 2026
Q2 25-26 | Department of Education | DE | 4190 | Cove (formerly School Compliance) | Education | Tracking and Workflow | The project will re-platform the current assessment and standards management system, improving time to response with evidence attribution and enabling a scalable workforce. | Delivery | Compliance (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-06-30 | 2025-08-15 |  | 2025-08-15 | 0 |  | 2025-08-18 |  | 2026-01-30 |  | 1400000 |  |  |  |  | Green | Green | The project is GREEN and is tracking to plan. The new solution is scheduled to Go-Live in early 2026.
Q2 25-26 | Department of Education | DE | 4191 | Student Travel System | Education | Management of Process | The project will digitise Student Travelling applications and centralise information, reducing administrative effort and improving accuracy and timeliness of school bus program. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-02-03 | 2025-03-21 |  | 2025-09-08 | 0 |  | 2025-09-08 |  | 2026-03-20 |  | 4242287 |  |  |  |  | Amber | Amber | The project is AMBER due to schedule delays from a change request to deliver additional capabilities to support the mapping component of the new solution.
Q2 25-26 | Department of Education | DE | 4192 | School Sport Victoria Website Redevelopment | Education | Management of Process | The project will deliver a modern, secure website to centralise all school sports program information, delivering a comprehensive school sport program information portal to primary and secondary students across Victoria | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-21 | 2025-09-15 |  | 2025-09-15 | 0 |  | 2025-09-30 |  | 2026-04-24 |  | 1200000 |  |  |  |  | Green | Green | The project is GREEN and is tracking to plan. There has been no change to finances in this reporting period.
Q2 25-26 | Department of Education | DE | 4193 | Legacy System Migration Program | Education | Development and Integration ,Security Management ,Systems Management | This program will transition services and systems from outdated infrastructure to modern, scalable and secure infrastructure, minimising security risk and support cost. | Closed - Terminated | Efficiency/Productivity (Non Financial) | 2025-12-31 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-07-01 |  | 2025-07-01 | 0 |  | 2025-07-01 |  | 2026-06-30 |  | 7451000 |  |  |  |  | Green | Green | The Legacy System Migration Program was designed to progressively replace outdated and end-of-life IT systems used by the department and school and school-support staff. To improve transparency this work will now be reported as 2 separate projects: STaR which will transform legacy service tracking capabilities that enable school support activities and SupportEd which will transform legacy case management capabilities that enable student support services.
Q2 25-26 | WorkSafe Victoria | WorkSafe | 4196 | Information Security and Management Uplift | Employment, Skills and Workplace | Records Management ,Security Management | WorkSafe Victoria is improving its information management security and cyber security maturity to strengthen governance, clarify ownership, uplift capability and reduce risk through targeted improvements and formal assessment. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-10-30 |  | 2025-10-30 | 189460 | 125073 | 2025-11-03 |  | 2026-11-30 |  | 1548186 | 1612573 |  |  |  |  | Green | Project is on track with discovery activities and reviews in progress. Planning activities for immediate risk mitigation under way.
Q2 25-26 | Court Services Victoria | CSV | 4199 | Case and List Management System (CLMS) Stabilisation Project - Tranche 1 | Law and Justice | Development and Integration | The project will stabilise and upgrade the existing technology for eCase and CourtConnect, to enhance critical functionalities across County Court of Victoria (CCV) digital infrastructure. | Initiated | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2024-09-01 | 2026-03-31 |  |  | 0 | [12 empty] | Consultations undertaken for the eCASE and CourtConnect delivery options. Briefs are with the Project Sponsor for endorsement to proceed to the procurement phase.
Q2 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4200 | Procurement @ DEECA – Digital Enablement | Business and Industry | Management of Process | This project will deliver a new technology solution to optimise procurement processes. The primary goal is to implement procurement forms to meet evolving requirements and ensure that updated framework elements are enabled through technology. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid – Waterfall and Agile | 2025-04-07 | 2025-04-07 |  | 2025-08-06 | 0 |  | 2025-08-06 |  | 2026-08-31 |  | 3176852 | [5 empty] | Green | Delivery is on track as per the approved plan and schedule.
Q2 25-26 | Court Services Victoria | CSV | 4201 | County Court of Victoria Audio-Visual (in-court technology) systems upgrade (2025-29) | Law and Justice | Collaboration ,Communication | Upgrading Audio Visual systems across the County Court of Victoria to deliver modern, integrated solutions for video conferencing, evidence display, and remote participation in 100 spaces, including 53 courtrooms and 39 jury rooms. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial) |  | Waterfall and Agile | 2023-11-03 | 2024-10-01 |  | 2024-10-01 | 14530 |  | 2024-10-01 |  | 2029-10-16 |  | 17039154 | [5 empty] | Green | Project Delivery initiated, with initial/trial courtroom build to commence in Q3.
Q2 25-26 | Court Services Victoria | CSV | 4202 | Case and List Management System (CLMS) Stabilisation Project - Tranche 2 | Law and Justice | Development and Integration | The project will stabilise and upgrade the existing technology for CLMS and its associated systems, while consolidating and enhancing critical functionalities across County Court of Victoria (CCV) digital infrastructure. | Initiated |  |  | PMBoK | 2024-09-01 | 2026-03-31 |  |  | 0 | [12 empty] | Consultations commenced for CLMS stablilsation and modernisation delivery options.
Q2 25-26 | Yarra Valley Water | YV Water | 4203 | STP Firewalls Replacement and SD-WAN Implementation | Environment and Water | Security Management ,Systems Management | This project replaces EOL firewalls at remote sites and modernises our IT/OT network with SD WAN, delivering a more secure, reliable, high performance network that improves business continuity and simplifies management. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-10-06 | 2026-02-12 |  |  | 60000 | [12 empty] | The project business case was approved in November, with Delivery commencing in Q3 2025-26
Q2 25-26 | Yarra Valley Water | YV Water | 4206 | MAINTENANCE SERVICES MOBILISATION | Environment and Water | Development and Integration | This project delivers the digital and system integration foundations required to enable the safe, effective, and coordinated transition to the new Maintenance Services Contracts with new Delivery Partners. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-01-01 | 2025-12-31 |  |  | 2125163 | [12 empty] | The project has completed its initiation and planning activities and will enter the Delivery phase from 1/01/26
Q2 25-26 | Melbourne Water | MELB Water | 4208 | AV Upgrade | Environment and Water | Communication | This project aims to deliver AV upgrades at operational sites across Melbourne Water. | Initiated |  |  | PMBoK | 2025-11-07 | 2026-02-02 |  |  | 0 | [12 empty] | As at 20251231: Business case to be submitted.
Q2 25-26 | Melbourne Water | MELB Water | 4210 | IT Storage Refresh | Environment and Water | Data Management | Current data centre storage and connectivity are end of life in 2026. Project will deliver upgraded storage infrastructure that meets current needs and can scale to support future growth. | Initiated |  |  | PMBoK | 2025-10-08 | 2026-02-16 |  |  | 0 | [12 empty] | As at 20251231: RFP documentation in progress to inform business case submission.
Q2 25-26 | Melbourne Water | MELB Water | 4211 | Telemetry Network | Environment and Water | Systems Management | Current network services will be decommissioned in 2027, this project is to upgrade to scale and support future growth. | Initiated |  |  | PMBoK | 2025-12-08 | 2026-04-08 |  |  | 0 | [12 empty] | As at 20251231: Business Case to be submitted.
Q2 25-26 | Department of Health | DH | 4212 | Data Centre Exit | Health | Systems Management | Exit the Burwood and Ballarat Data Centres by migrating workloads to alternate data centres, including network establishment, VMware to IaaS migration and SAN/Oracle relocation, to meet June 2026 exit objectives, avoiding increased hosting costs. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-11-10 | 2026-02-27 |  |  | 193168 | [12 empty] | Planning and mobilisation activities underway.
Q2 25-26 | Melbourne Water | MELB Water | 4213 | Enterprise WAN Refresh | Environment and Water | Systems Management | SD‑WAN integrates all network connections to optimise bandwidth and improve performance. This pilot will validate the technology before a full roll-out that will replace outdated hardware and enhance network management. | Initiated |  |  | PMBoK | 2025-10-23 | 2026-05-29 |  |  | 0 | [12 empty] | As at 20251231: Business case to be submitted.
Q2 25-26 | Melbourne Water | MELB Water | 4214 | Mapping Analytics Upgrade | Environment and Water | Systems Management | Major upgrade of Melbourne Waters Geographic Information System to the latest supported version. | Initiated |  |  | PMBoK | 2025-10-25 | 2026-09-30 |  |  | 0 | [12 empty] | As at 202601206: Impact assessment artefact released for formal review and walk-through conducted. Feedback from review scheduled to be completed late January.
Q2 25-26 | Department of Education | DE | 4220 | Student Insight Platform Establishment and Digital Enrolment Product - Phase 3 | Education | Customer Relationship Management | Student Insight is a centralised enrolment and student administration platform, replacing paper-based processes for schools and families. The project will enhance and implement the Digital Enrolment Product across mainstream schools in the SEV & NEV | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - Waterfall and Agile | 2025-07-01 | 2025-10-30 |  | 2025-10-30 | 0 |  | 2025-11-01 |  | 2026-06-30 |  | 11450000 | [5 empty] | Green | The project is GREEN and tracking to plan without issues.
Q2 25-26 | Department of Education | DE | 4221 | Justice Education System Portal | Education | Analyses and Statistics ,Systems Management,Tracking and Workflow | This Portal brings together various systems and platforms to create a scalable system for justice education. This is to create a well-connected Portal to track and monitor young people at risk or involved in youth justice & those presenting to police | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - Waterfall and Agile | 2025-05-01 | 2025-05-30 |  | 2025-06-25 | 267000 |  | 2025-11-01 | 2025-11-17 | 2027-06-30 |  | 2500000 | [5 empty] | Green | The project is GREEN and tracking to plan. Currently working through requirements and design for the minimum viable product portal solution.
Q2 25-26 | Department of Education | DE | 4222 | VRQA Victorian Home Schooling Register Replacement | Education | Customer Relationship Management | The VRQA is redeveloping the Home Schooling Register to meet current technology and security standards to better support our business needs and improve efficiency across the organisation. | Initiated |  |  | Hybrid - Waterfall and Agile | 2025-05-16 | 2025-11-25 |  |  | 0 | [12 empty] | The project is registered and not yet commenced. Project is currently in initiation following business case approval. The project is planned to commence in Q3 2025-26.
Q2 25-26 | Development Victoria | Development Vic | 4223 | HRIS & Payroll solution | Property and Planning | Human Capital / Workforce Management | Human Resources and Payroll System implementation to improve operational efficiencies, improve data and reporting quality, reduce risk and improve the employee experience. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-08-18 |  | 2025-08-18 | 0 |  | 2025-08-18 |  | 2027-03-31 |  | 2551166 | [5 empty] | Green | Procurement activities for the project are currently in progress.
Q2 25-26 | Department of Health | DH | 4224 | Briefings Solution Implementation | Health | Communication,Management of Process ,Tracking and Workflow | The DH & DFFH Briefings Solution will manage ministerial & secretarial briefings/correspondence, parliamentary questions, executive memos & other materials requiring executive approval, improving collaboration & efficiency in correspondence approval. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-01 | 2025-10-10 |  | 2025-10-10 | 684600 |  | 2025-10-13 |  | 2026-06-30 |  | 2509210 | [5 empty] | Green | Project is progressing to cost and schedule.
Q2 25-26 | Department of Government Services | DGS | 4225 | Working With Children Check Employer Platform and Training | Government and Economy | Development and Integration | Provide an improved online and offline experience that supports the revised regulatory framework and further strengthens the Working with Children Check. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-10-08 | 2026-03-04 |  |  | 200000 | [12 empty] | Project Initiation underway, Business Case targeted for approval March 2026.
Q2 25-26 | Barwon Region Water Corporation | BR Water | 4226 | C1069 - TechOne CiA Transition | Environment and Water | Financial Management | This project aims to maximise the value of the TechnologyOne platform by migrating the remaining Supply Chain Management (SCM) module from Ci to CiA platform. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2024-06-02 | 2025-09-30 |  | 2025-10-30 | 400877 |  | 2025-11-09 |  | 2026-04-30 |  | 781253 | [5 empty] | Green | Project has successfully mobilised and design has completed. Solution configuration has commenced.