## ProjectData
CollectionPeriod | ProjectID | AgencyName | AgencyShortName | ProjectTitle | GovernmentDomain | Description | StartDate | PMMethod | PMOther | Stage | PreImpEndDate | PreImpCost | PlanndedImpEndDate | PlannedImpCost | RevisedImpEndDate | RevisedImpCost | ImpStatus | Previous Status 3mth | Previous Status 6mth | Previous Status 9mth | Previous Status 12mth | Comments | DataCurrencyDate
Q3-2016-17 | 6F51921B-0BE8-43F9-A56E-7AFB03E8F2D8 | Alfred Health | ALFRED | Upgrade Alfred Health PABX Telephony, switchboard, computer core network, cabling and wireless services | Health | Implement Alfred Health ICT Strategy including managing critical ICT infrastructure risks to carry out technology refresh and replace out-of-support systems (PABX Telephony, switchboard, computer core network, cabling and wireless) to support safe and high quality care to patients. | 2014-09-23 | PRINCE2 |  | In progress - implementation | 2014-10-10 | 0 | 2016-11-30 | 3700233 | 2017-05-31 |  | GREEN | AMBER | GREEN | GREEN | GREEN | Project is ON TRACK. | 2017-03-31
Q3-2016-17 | BDF32C2A-6A20-4FB5-AD21-871F569D346B | Alfred Health | ALFRED | Alfred Emergency and Trauma Centre Redevelopment - ICT Component and Emergency Department Information System (EDIS) | Health | Expand and refurbish the Alfred Emergency & Trauma Centre facility staged to ensure operational continuity during the indicative 18 months of building works - ICT Component and EDIS. Full implementation of EDIS functionality is planned as components of the ED&TC redevelopment are released. ETA: Feb-2018. | 2015-10-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project is ON TRACK. | 2017-03-31
Q3-2016-17 | EB80B721-ED14-40F9-84D5-C160E1399621 | Alfred Health | ALFRED | Implement eTQC Phase One program to upgrade clinical information systems to significantly improve electronic timely quality care for our patients | Health | Development and Implementation of Phase One of the electronic-Timely Quality Care (eTQC) project that will significantly improve clinical real-time data capture, management and patient care service delivery, to progress towards a fully electronic medical record across Alfred Health. | 2016-04-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project is ON TRACK. | 2017-03-31
Q3-2016-17 | 43042989-DA36-498B-B806-059CC6769E4B | Alfred Health | ALFRED | Upgrade of Alfred Health analogue telephone with digital phones and wireless network to remove black spots | Health | Replacement of remaining Alfred Health analogue telephone handsets with digital phones, decommissioning of Nortel PABX system and remediate wireless network black spots | 2016-09-15 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project is ON TRACK. | 2017-03-31
Q3-2016-17 | CD035DCD-9DDD-44F9-8587-392E51AA223E | Ambulance Victoria | AV | Improving 000 Triage | Health | To work with ESTA to develop a full Business Case for consideration by the government, in accordance with the Department of Treasury and Finance (DTF) guidelines that makes an evidenced based recommendation on a solution that best meets AV’s need to Improve Triage. | 2016-01-01 | Other – please specify | AV Project Management Framework (PRINCE2 based) | Terminated | [11 empty] | In developing the final business case, Ambulance Victoria (AV) and ESTA determined that a number of areas would benefit from further investigation before the business case should be progressed further. The project was undergoing restructure to enable further supporting evidence to be obtained through the running of a number of pilots. Following advice from a key potential provider that they would be unable to engage with AV for at least twelve months, AV and ESTA have placed investigation into a new integrated triage solution on hold, and will focus on other priority reform programs. | 2017-03-31
Q3-2016-17 | 5EE27FC9-5491-4667-9009-804C43CF940A | Ambulance Victoria | AV | VACIS 3 | Health | Upgrade electronic Patient Care Record software (VACIS 2 to VACIS 3), and deployment of mobile devices for mobile office. | 2016-02-08 | Other – please specify | AV Project Management Framework (PRINCE2 based) | In progress - pre-implementation | [11 empty] | Proof of concept successfully completed on the 13th of April. Planning for the building of devices to commence, and training for the Paramedics is scheduled via CPD days from 22 May to Mid Aug. | 2017-03-31
Q3-2016-17 | 82DC1100-ECE9-4799-93B5-41F8ABEE8C0B | Austin Health | AH | Laboratory Information System | Health | Implementation of a common Laboratory Information System as an externally hosted fully managed service in collaboration with two other state public health services. It will replace an existing internally hosted Pathology Laboratory System . | 2014-07-21 | Other – please specify | Overarching PRINCE2 approach with AGILE management of agency configuration and build. | In progress - implementation | 2015-06-04 | 50000 | 2017-01-31 | 1366875 | 2017-10-06 | 1486087 | AMBER | AMBER | GREEN | GREEN | GREEN | Following a phased deployment approach. Commencement date for phase 2 to occur 30 days after phase 1 go-live. | 2017-03-31
Q3-2016-17 | FE15A512-0A86-454E-B368-753337768B4B | Austin Health | AH | Clinical Research Data Warehouse | Health | The objective is to implement a Data Warehouse to support clinical research. This entails developing the technical platform to extract and store data from a number of systems; and provide the foundation for clinical analytics. | 2015-07-01 | PRINCE2 | Vendor specific framework - based on Prince 2 | In progress - implementation | 2017-02-01 | 95000 | 2017-06-30 | 1150000 |  |  | GREEN | N/A |  |  |  | Project Design & Build phase is due to be completed in January 2017. Testing timelines have been reset to match the Oncology project testing timelines. Technical Go Live scheduled for 13th April 2017. | 2017-03-31
Q3-2016-17 | 5AC945FC-3674-4D21-844B-10637572BA48 | Austin Health | AH | Oncology Information System (OIS) | Health | The objective of the OIS is to improve the coordination of patient care and cancer treatments through ordering, scheduling and documenting cancer protocols within the EMR (Electronic Medical Record). The goal is to capture patient information electronically to populate the Data Warehouse to facilitate cancer research. | 2015-09-22 | Other – please specify | Vendor specific framework, based on Prince 2 | In progress - implementation | 2015-12-14 | 966042 | 2016-10-14 | 3400000 | 2017-06-30 | 3552000 | AMBER | GREEN | GREEN | AMBER | AMBER | Ability to meet 30 June 2017 go-live is dependent upon the timing of defect fix delivery by the vendor. | 2017-03-31
Q3-2016-17 | CCCA63CF-018C-40E7-A31D-47DA7D152911 | Austin Health | AH | Theatre Management System | Health | The objective of Theatre Management System, is to improve the ordering and scheduling of procedures for both elective and emergency patients; to improve documentation of the preadmission process and ensure patients are ready for care; and to improve the flow of patients through the perioperative area. | 2015-09-22 | Other – please specify | Vendor specific framework - based on Prince 2 | Completed | 2015-12-14 | 617185 | 2016-10-14 | 3600000 | 2016-12-31 |  | N/A | GREEN | GREEN | AMBER | GREEN | Project went live according to schedule in November 2016. There were no major issues at go live. Project warranty period has now expired. Benefits realisation - as per schedule. | 2017-03-31
Q3-2016-17 | 8352D5BD-1DAA-40A5-A939-FFC692545477 | Barwon Region Water Corporation | Barwon Water | Customer Relationship Management System | Environment and water | Current customer systems are disparate and no longer meet business needs and expectations. This project's objective is to implement a CRM Solution to replace a suite of existing solutions, enabling improved levels of service, greater efficiency in service provision and deliver digital customer transformation. | 2016-11-01 | PMBoK |  | In progress - pre-implementation | [11 empty] | Project is on track and GREEN | 2017-03-31
Q3-2016-17 | B4AA2A5D-8DB1-47B7-BB04-7E54A94C1930 | Bendigo Kangan Institute | BKI | Student Management System Implementation | Education | Implementation of new Student Management System across the integrated Bendigo Kangan Institute | 2013-02-01 | PRINCE2 |  | In progress - implementation | 2014-04-01 | 82723 | 2016-12-31 | 9800000 | 2017-11-30 | 12300000 | GREEN | AMBER | AMBER | AMBER | AMBER | Since the implementation in December 2015 of the Student Management System Phases One and Two, the project has expended significant effort in post go-live support of the business in particular with AVETMISS reporting and defect resolution. In parallel, Phase 4A (ASMS) and 4B (Moodle two way interface) and some tranches of Phase 5 have been completed. The project continues to undergo a review of business functions and product functionality to re-validate scope for the remainder of the implementation. Work has commenced on investigation of two major modules: document management and workflow. | 2017-03-31
Q3-2016-17 | 12173148-2781-4F08-9A8F-8B5751C5C4AB | Bendigo Kangan Institute | BKI | Human Resources and Payroll Information System Implementation | Education | Implementation of new Human Resource and Payroll Information System across the integrated Bendigo Kangan Institute | 2015-01-27 | PRINCE2 |  | In progress - implementation | 2017-01-31 | 284550 | 2017-07-03 | 1241354 | 2017-09-30 | 1915341 | GREEN | AMBER | AMBER |  |  | The HR IS/Payroll Integration Project is in Implementation Phase. An integrated project plan with Fusion5 has been scoped and approved. Performance Management - module was delivered in February, recruitment and on-boarding go-live in May 17, Learning & Development go-live June 17 and Payroll, OHS & TA modules go-live Aug17. As the modules are delivered BAU user training documentation is collated. Additional funding of $390k was approved for the project to cover resourcing & instructional designer costs required to deliver the modules | 2017-03-31
Q3-2016-17 | 18C8670A-54B5-49A6-8807-DA93761CFDC2 | CenITex | CTX | Operating System Upgrade Across Windows Fleet | Government and economy | To upgrade fully managed servers in the shared environment to a supported server operating system | 2015-06-01 | PRINCE2 |  | In progress - implementation | 2015-06-01 | 15000 | 2017-06-30 | 2295214 |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | Upgrades continue as planned and activity has commenced to test secure network enclave zones for unsupported Windows 2003 servers that cannot be upgraded due to customer business constraints. Migrations have begun, further migrations dependant on customer approvals. | 2017-03-31
Q3-2016-17 | 9F6B93E7-4787-44D2-AA55-43B016AB8D05 | CenITex | CTX | Shared Storage & Backup Refresh | Government and economy | To consolidate the existing Storage and Backup environment to meet growth requirements, mitigate email related operational risks and accommodate customers migrating to the shared storage platform. | 2015-07-01 | PRINCE2 |  | Completed | 2015-07-01 | 15000 | 2016-06-30 | 6995450 | 2016-12-30 | 7295450 | N/A | GREEN | GREEN | AMBER | GREEN | Project completed. | 2017-03-31
Q3-2016-17 | 2CD0BFF9-07A8-454C-BABE-D43FA107C182 | CenITex | CTX | Network Access Switch Refresh | Law and justice | To refresh the oldest network equipment at a large CBD customer site. | 2015-07-20 | PRINCE2 |  | Completed | 2015-07-20 | 15000 | 2016-05-22 | 1436180 | 2016-09-30 | 1036180 | N/A | GREEN | GREEN | GREEN | GREEN | Project completed. | 2017-03-31
Q3-2016-17 | E95CD7A0-7AE2-4E02-80D0-EECE6ED01B5D | CenITex | CTX | Operating System Upgrade Across Windows Fleet | Health | To upgrade servers in the customer environment to a supported server operating system | 2016-02-08 | PRINCE2 |  | In progress - implementation | 2016-02-08 | 15000 | 2018-06-30 | 3570000 |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | Migration and decommissioning activities continue with 52% of the two year scope successfully remediated in the first nine months. | 2017-03-31
Q3-2016-17 | 9F535AA9-B719-4257-AAA1-5AFDDBC8AB98 | CenITex | CTX | Office365 Establishment & Migration | Government and economy | To implement Office 365 and make it available as a service for Victorian Government | 2016-05-01 | PRINCE2 |  | In progress - implementation | 2016-06-30 | 200000 | 2017-06-30 | 4194583 |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | Yammer and OneDrive migrations completed, SharePoint migration process has commenced. | 2017-03-31
Q3-2016-17 | 1C538086-D306-4A51-BED5-7047BADB4AE5 | CenITex | CTX | Hosting Storage Refresh/Consolidation | Government and economy | Refresh and consolidate shared storage infrastructure that supports Victorian government shared server hosting environment | 2016-05-01 | PRINCE2 |  | In progress - implementation | 2016-06-08 | 15000 | 2017-06-30 | 1997000 |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | Project on track and is completing data migrations as planned. | 2017-03-31
Q3-2016-17 | 272863AD-C71E-47A8-8104-BAFAD910BBC4 | CenITex | CTX | Firewall Refresh for Victorian Government Shared Platform | Government and economy | Refresh firewalls at both primary and secondary Data Centres for Victorian government shared platform | 2016-06-03 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Procurement and planning activities are underway. | 2017-03-31
Q3-2016-17 | D27645D5-6B7A-46FB-BE31-1BEF20CE3E49 | CenITex | CTX | Corporate ERP SaaS Solution | Government and economy | Implement SaaS based ERP - CRM, PPM and Finance subsystems | 2016-07-01 | PRINCE2 |  | In progress - implementation | 2017-03-15 | 91113 | 2018-01-31 | 2049361 |  |  | GREEN | N/A | N/A | N/A | N/A | Procurement activities complete, vendor has been engaged and project initiation activities are underway. | 2017-03-31
Q3-2016-17 | 067986DF-4C3B-4133-955F-EC9183FE0FD9 | Country Fire Authority | CFA | CFA Resource Tracking System (RTS) | Emergencies and safety | Provide a Resource Tracking System for all CFA resources using CFA mobile radios to collect and transmit location data. This will allow Incident Controllers to have a near real time view of where all resources are located at major incidents enhancing firefighter safety. | 2010-10-01 | PRINCE2 |  | In progress - implementation | 2013-06-30 | 126034 | 2017-06-30 | 2500000 | 2017-10-31 |  | AMBER | AMBER | AMBER | AMBER | AMBER | The CFA is consulting with its staff and volunteer associations on a policy for the use of data from the resource tracking system. Consultation process has not impacted forecast completion dates. | 2017-03-31
Q3-2016-17 | 45FB2EDF-AAF8-4838-AFD6-666A020C065A | Country Fire Authority | CFA | CFA Short Status Messaging (SSM) | Emergencies and safety | Provide a Short Status Messaging system to allow CFA mobile radios to send status messages to fire dispatchers at ESTA. This will deliver more efficient use of radio channels by minimising voice congestion on radio dispatch channels. | 2010-10-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | This short messaging system project is an element of the larger Radio Dispatch Service (RDS) project and due to delays in the rollout of the RDS project, this element is running four years behind schedule. Consultation with a third party supplier is in progress. | 2017-03-31
Q3-2016-17 | B7F9C2EA-37D7-4DB8-B611-B29D43452097 | Chisholm Institute | Chisholm TAFE | Customer Relationship Management Implementation | Education | To provide an improved service to existing and potential students to maximise the take-up of educational services | 2016-06-01 | Other – please specify | Chisholm PMF (Prince 2 Based) | In progress - pre-implementation | [11 empty] | Tender evaluation completed, negotiating contract with preferred vendor. | 2017-03-31
Q3-2016-17 | DA1E050A-DE50-4412-A9B4-12F6A492DAC8 | Chisholm Institute | Chisholm TAFE | Network Refresh | Education | To refresh and improve the network infrastructure to improve functionality, availability and security | 2016-11-01 | Other – please specify | Chisholm PMF (Prince 2 Based) Business Case Approved and Tender Documentation Completed and Reviewed. | In progress - pre-implementation | [11 empty] | Business Case approved December 2016. Tender Documentation completed and reviewed 31st of March 2017 Tender to be issued 5th of April 2017. Tender Brief to be held 12th of April 2017. Tender closes 12th of May 2017. | 2017-03-31
Q3-2016-17 | 6590BED9-31CE-4DDF-BA60-DC11B034A1DE | Chisholm Institute | Chisholm TAFE | Systems Integration | Education | To improve productivity, data integrity, functionality and reduction in operating costs | 2016-11-01 | Other – please specify | Chisholm PMF (Prince 2 Based) Business Case Approved. Analysis and Discovery Phase - in progress. | In progress - pre-implementation | [11 empty] | Business Case approved December 2016. Discovery phase in progress planned completion by July 2017. | 2017-03-31
Q3-2016-17 | 6D6B7957-C247-453A-9019-51DDF5610B13 | Chisholm Institute | Chisholm TAFE | Migration to Cloud | Education | To migrate the on-site server environment to cloud services to improve availability, improve security, reduce risk and reduce operating costs. | 2016-11-01 | Other – please specify | Business Case Approved | In progress - pre-implementation | [11 empty] | Business Case approved December 2016. | 2017-03-31
Q3-2016-17 | 5D524B9A-1598-4E8C-92ED-80CCDBDD0371 | City West Water Corporation | CWW | Arrow Program | Business and industry | The Arrow program is a business transformation program to phase in the upgrade of most the business systems to an enterprise platform. | 2011-09-05 | Other – please specify | Oracle AIM | In progress - implementation | 2011-09-30 | 4109900 | 2022-06-30 | 104119621 | 2019-06-30 | 114200000 | AMBER | AMBER | AMBER | AMBER | AMBER | Arrow program has three releases: Release 1 (Foundation module) - completed in May 2014 Release 2 (Asset management and Field Mobility module) is in progress: - Release 2.1 - Enterprise Asset Management - completed in June 2016 for Facilities. Network assets will be added in June 2017. - Release 2.2 - Field Mobility - project timeline has been revised due to a change in system integrator and product selection. New product has been selected and the project has now recommenced. Release 3 (Customer billing module) is yet to commence, pending on additional funding approval. The implementation cost has been revised to exclude the additional funding for Release 3 as it is yet to be approved. The planned implementation end date has also been corrected due to a data error in the previous report. | 2017-03-31
Q3-2016-17 | 6C1D62AD-9BAD-4613-88D5-87E0CD1355F4 | City West Water Corporation | CWW | Customer Experience Platform - Contact Centre Uplift | Environment and water | Augment new deployed Enterprise Telephony technology to contact centre | 2014-07-02 | PRINCE2 |  | Completed | 2014-07-02 | 179000 | 2016-03-30 | 1435000 | 2017-02-28 | 1569931.28 | GREEN | AMBER | AMBER | GREEN | AMBER | Project has been completed. Full go-live takes effect at the beginning of February 2017 (to maximise value of 30 day warranty on installed software, it was decided to delay full go-live until Christmas and summer holidays concluded). | 2017-03-31
Q3-2016-17 | E80F599B-A91F-46C8-87A9-BD4D7B916132 | City West Water Corporation | CWW | IAPU Arrow Technology Upgrade | Business and industry | Oracle system upgrade initiative is to address the operational risk with CWW's Oracle EBS entering extended support in December 2016. | 2015-08-01 | Other – please specify | Gates Process, Benefit Realisation Model | Completed | 2015-09-01 | 10000 | 2016-02-15 | 2494000 | 2016-06-30 | 2494000 | GREEN | GREEN | N/A | N/A | N/A | Upgraded system went live on 12 May 2016. Upgrade took longer than expected due mainly to issues encountered during implementation as such project was officially closed in Q1, 2016-17. | 2017-03-31
Q3-2016-17 | F04697A0-69A5-4BE3-998D-4FAA3AD7FF52 | Court Services Victoria | CSV | eLodgement Project - Tranche 2 | Community services | Implementation of eLodgement capability in an additional 3 lists within the following Jurisdictions; County Court, Magistrates' Court and VCAT | 2015-08-01 | PRINCE2 |  | Completed | 2015-11-16 | 0 | 2016-06-30 | 1652000 | 2016-08-30 | 1652000 | GREEN | GREEN | GREEN | GREEN | GREEN | Finalising last part of this 2nd tranche of the project which enables electronic lodgement of documents in an additional list. | 2017-03-31
Q3-2016-17 | C610A140-8B8B-46D4-82AD-AC71AA647C3B | Department of Economic Development, Jobs, Transport & Resources | DEDJTR | Laboratory Information Management Strategy Implementation | Government and economy | This project will implement an enterprise web-based Laboratory Information Management System (LIMS) platform that will consolidate and centralise the existing veterinary diagnostics, plant diagnostics and chemistry Laboratory Information Management Systems to an agreed departmental standard (LabWare WebLIMS). This project is co-sponsored by Greg Harper and German Spangenberg | 2013-04-01 | PRINCE2 |  | In progress - implementation | 2014-12-22 | 0 | 2016-12-30 | 2062000 | 2017-07-10 | 2202000 | GREEN | GREEN | GREEN | GREEN | GREEN | The project is currently on track to complete delivery of LIMS by July 2017 | 2017-03-31
Q3-2016-17 | 856FC387-1720-40E8-BEF1-E8BF59874DCA | Department of Economic Development, Jobs, Transport & Resources | DEDJTR | DEDJTR ICT Transition Program | Government and economy | The new DEDJTR Department created the ICT Transition program in early January 2015 to handle all ICT MOG related projects and activity. The main focus for the ICT Transition Program is to design and implement an agreed transition approach and plan to establish consolidated technology services for DEDJTR. | 2015-03-01 | PRINCE2 |  | Completed | 2015-09-30 | 0 | 2016-09-30 | 9496352 | 2016-12-23 | 9496352 | N/A | GREEN | GREEN | GREEN | GREEN | Project deliverables have been successfully completed. | 2017-03-31
Q3-2016-17 | 7B327050-2480-4A33-BC24-EF6E38E1085D | Department of Economic Development, Jobs, Transport & Resources | DEDJTR | Resource Rights Allocation and Management (RRAM) Enhancement Project | Government and economy | RRAM is used by the earth resources regulator (ERR) and the industry to administer and regulate mining and petroleum tenement activities in Victoria. The project aims to deliver enhancements to RRAM's functionality and application by the regulator and industry. | 2017-01-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project Manager has been appointed with recruitment of team members continuing. A roadmap has been established, outlining three key phases for the project to address. This has been presented to the ERR Executive and the industry via the ERR Symposium, recently held at Treasury Gardens. A Project Control Board (PCB) has been established and will meet monthly to observe the project from a governance perspective. | 2017-03-31
Q3-2016-17 | 5FF8E95C-6029-43F1-A725-B025B25CF43D | Department of Environment, Land, Water and Planning | DELWP | Enterprise Content Management System | Environment and water | Deliver an enterprise content management system | 2012-01-01 | PRINCE2 |  | Completed | 2012-06-01 | 0 | 2016-04-30 | 6011100 | 2017-02-28 | 6326100 | N/A | GREEN | GREEN | GREEN | GREEN | The project has been completed | 2017-03-31
Q3-2016-17 | 8C478395-B494-4ACB-92B8-281698823E39 | Department of Environment, Land, Water and Planning | DELWP | Departmental Resourcing and Capability Project (DRaC) | Emergencies and safety | To develop consistent business processes, rules and supporting systems for the identification, management and deployment of resources for emergency management, surge operations and related business continuity issues in DELWP and Regulation and Compliance groups in other departments. | 2014-08-01 | PRINCE2 |  | In progress - implementation | 2015-05-29 | 418012 | 2016-12-31 | 3475758 | 2017-06-30 | 3475758 | GREEN | AMBER | AMBER | GREEN | GREEN | The project will complete on 30 June 2017. Project is currently on budget and is on track to meet its objectives. The controls are in place to manage any risks and issues as they arise. | 2017-03-31
Q3-2016-17 | C9C85060-4F47-423C-B1FA-0F0438299C85 | Department of Environment, Land, Water and Planning | DELWP | Native Vegetation Information Management System (NVIM) | Environment and water | NVIM supports a platform to obtain information on Victoria's native vegetation and biodiversity assets and access to a range of tools. These tools are designed to assist the implementation of government reforms to Victoria's native vegetation permitted clearing regulations, estimating habitat compensation and land security obligations under the Melbourne Strategic Assessment | 2014-09-01 | Agile |  | Completed | 2015-12-21 | 150551 | 2016-06-30 | 1439441 | 2017-05-01 | 1439441 | N/A | GREEN | GREEN | GREEN | N/A | The project implementation has been completed on budget. Project closure activities are underway. | 2017-03-31
Q3-2016-17 | B703BCE9-F1B3-495E-B4EC-4F8D76B8DF51 | Department of Environment, Land, Water and Planning | DELWP | DELWP Website Transformation | Community services | Deliver a DELWP web presence that supports the delivery of our community charter and facilitates effective interaction with our community and customers online. This will be achieved through new technologies allowing improved content, structure and functionality, supporting community activities and businesses processes and support positive user-experience through any future organisation changes. | 2015-07-23 | Other – please specify | Combination of PRINCE2 Project Management and Agile development and delivery | In progress - implementation | 2016-03-15 | 334468 | 2017-04-01 | 1866175 | 2017-05-19 | 0 | GREEN | GREEN | GREEN | GREEN | N/A | The project is now on schedule, change request submitted to accommodate the development of three additional websites. Project is currently on budget. The project is currently on track to meet its objectives. Project controls are in place. | 2017-03-31
Q3-2016-17 | 0695877D-2DF9-40F2-9753-477ADE5A3934 | Department of Environment, Land, Water and Planning | DELWP | Regional WIFI | Employment and workplace | Implementation of WIFI Infrastructure in DELWP regional locations to increase collaboration and efficiency by providing secure network access for 6 priority regional sites (de-scoped from original 20). DELWP has provided relevant information to CENITEX and DEDJTR who are managing WIFI implementations at DELWP/Shared/Own sites that are no longer within scope. | 2016-07-14 | PRINCE2 |  | Completed | 2016-07-30 | 146745 | 2017-08-31 | 1191684 | 2016-12-20 | 485172 | GREEN | GREEN | N/A | N/A | N/A | The de-scoped project has been completed on schedule and within budget. The project has met its objectives. The controls were in place to manage the risks and issues as they arose. | 2017-03-31
Q3-2016-17 | 4E0FC0FC-9AA9-4D4A-9517-5695DDF46AC5 | Department of Environment, Land, Water and Planning | DELWP | Business Support System Project | Employment and workplace | Replatform of existing HCM/Payroll solution to a cloud based system for DELWP to align with WoVG strategy. | 2016-11-03 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Pre-implementation phase is in progress with RFT evaluation for HCM/Payroll due to complete end July 2017. Implementation project estimated to commence in August 2017. | 2017-03-31
Q3-2016-17 | 275A6261-85C3-4F9C-8E82-7BE579DFD170 | Department of Environment, Land, Water and Planning | DELWP | Digital Workplace | Employment and workplace | Establishment of a user-centered digital workplace productivity platform and collaboration hub, for the enablement of delivering of service excellence. | 2016-07-01 | Other – please specify | Combination of PRINCE2 Project Management and Agile development and delivery | In progress - implementation | 2017-01-16 | 166401 | 2017-09-30 | 1148372 |  |  | GREEN | GREEN | N/A | N/A | N/A | The project is currently on schedule. Project is currently on budget. The project is currently on track to meet its objectives. The controls are in place to manage the risks and issues as they arise. | 2017-03-31
Q3-2016-17 | 0D0E45CD-5526-4A2F-AACB-63CF885267DC | Department of Environment, Land, Water and Planning | DELWP | Smart Planning - Planning Portal | Property and Planning | The Planning Portal Project will provide an easily identifiable web-based entry point for the community and government to access a comprehensive and integrated set of planning policies, legislation, planning scheme information, guidelines and services. Introduced as part of the 2016-17 Victorian Budget | 2016-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | The project is currently on schedule. Project is currently on budget. The project is currently on track to meet its objectives. The controls are in place to manage the risks and issues as they arise. | 2017-03-31
Q3-2016-17 | 7D123DE0-72D1-4CD1-A5DC-4BD3AC2385AE | Department of Environment, Land, Water and Planning | DELWP | Planning Scheme Information Management System | Property and Planning | The system will support the full amendment life-cycle from creation to Gazettal. The project is phased over two stages. The first will see production use by internal areas (DELWP and Panels Victoria) and the second stage will be used by pilot councils. Introduced as part of the 2016-17 Victorian Budget | 2016-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | The project is currently on schedule. Project is currently on budget. The project is currently on track to meet its objectives. The controls are in place to manage the risks and issues as they arise. | 2017-03-31
Q3-2016-17 | 93899F63-09E5-4F87-A155-23F4F63AAEB9 | Department of Environment, Land, Water and Planning | DELWP | Smart Planning Online Permits | Property and Planning | Pilot the online lodgement of Planning Permit applications. This includes refreshing the Greenlight applicant and register interface and integrating the Departments WestPac payment gateway for online payments. Introduced as part of the 2016-17 Victorian Budget | 2016-07-01 | Other – please specify | Combination of PRINCE2 Project Management and Agile development and delivery | In progress - pre-implementation | [11 empty] | The project is currently on schedule. Project is currently on budget. The project is currently on track to meet its objectives. The controls are in place to manage the risks and issues as they arise. | 2017-03-31
Q3-2016-17 | 5BD14F78-D355-41BF-9C3E-1669E5A02028 | Department of Environment, Land, Water and Planning | DELWP | Smart Planning - Interactive Planning Scheme Maps | Property and Planning | The Victorian Planning Scheme is defined geographically by 15,000 static maps. This project will replace static maps when a web-based experience that facilitates interacting with the Planning Scheme spatially across the state. This will be supported by a geospatial relational database. Introduced as part of the 2016-17 Victorian Budget | 2016-07-01 | Other – please specify | Combination of PRINCE2 Project Management and Agile development and delivery | In progress - pre-implementation | [11 empty] | The project is currently on schedule. Project is currently on budget. The project is currently on track to meet its objectives. The controls are in place to manage the risks and issues as they arise. | 2017-03-31
Q3-2016-17 | 73F151E7-D2F3-4CF8-A7A8-FC629476ECC4 | Department of Education and Training | DET | Student Transport Management System | Education | The project will upgrade the Student Conveyance Allowance System, used to manage claims and conveyance allowance payments in the order of $30m per year. The project will incorporate student transport functionality, used to support administration of special school bus contracts worth $72m per annum. | 2010-07-01 | PRINCE2 |  | Completed | 2015-06-29 | 1221835 | 2016-05-09 | 1316079 | 2017-03-31 | 1816052 | GREEN | GREEN | GREEN | GREEN | GREEN | The extended pre-implementation phase is due to the project being on-hold for a prolonged period pending DET decisions. In April 2015 the project engaged a vendor to upgrade the Department’s Student Conveyance Allowance System (SCAS) from CRM 4 to CRM 2015, enhance the upgraded SCAS and then incorporate the student transport functions into SCAS. This will result in a single system for DET to manage all student transport and conveyance functionality. The upgraded SCAS with enhancements was successfully released to all Victorian schools in May 2016. During the development of the Functional Design, additional requirements were identified and a Project Change Request was approved to include these new functions in the project scope and the project re-baselined accordingly. The SCAS incorporating the student transport functions has now been migrated into Production and the project has now commenced closure activity. | 2017-03-31
Q3-2016-17 | BA167DCC-D9C4-433A-90B0-7B19679C66E2 | Department of Education and Training | DET | FUSE SharePoint 2013 Upgrade | Education | FUSE (Find Use Share Education) is an online curriculum and resource portal for teachers and students. This project will upgrade the platform from SharePoint 2007 to SharePoint 2013 with some additional enhancements to improve usability and align resources to the new Victorian Curriculum | 2012-05-21 | PRINCE2 |  | Completed | 2015-03-06 | 283815 | 2015-11-11 | 1238225 | 2016-10-20 |  | GREEN | GREEN | GREEN | GREEN | AMBER | Project activities have progressed to plan. Testing and cutover preparation activities have been completed. FUSE Go Live occurred 26 September. Post cutover activities have been completed and the project closed. | 2017-03-31
Q3-2016-17 | 891F2445-1AE7-411E-B7DD-CBB33725A606 | Department of Education and Training | DET | Asset Management System Replacement | Education | The AMSR project will identify and implement an Asset (Facilities) Management Software solution for managing information on DET property assets. The system will provide for the end-to-end asset management lifecycle and will replace a number of disparate legacy systems | 2013-02-28 | PRINCE2 |  | In progress - implementation | 2014-04-30 | 679000 | 2016-07-25 | 5269000 | 2017-07-21 | 5198600 | GREEN | GREEN | AMBER | AMBER | AMBER | The Asset Management System Replacement (ASMR) project is in the process of closure. The Department’s Asset Management System (AMS) has been operational and live within DET corporate since late 2014 and will continue in use until at least 2019-20. The AMS vendor has recently advised of the intent to retire the Atrium product and will not support further development beyond 2019 and will cease support from around April 2021. In these circumstances, the Department is starting the process of strategic options planning for a successor asset management system. Project reporting on the AMSR project will cease from 30 June 2017 as the project is complete. | 2017-03-31
Q3-2016-17 | AC84992F-C35D-4A5C-891D-3CD6C0956E15 | Department of Education and Training | DET | Exchange Upgrade | Education | The Exchange Upgrade project will upgrade the DET Microsoft Exchange platform from Exchange 2010 to Exchange 2016, including migration of all DET users. The system will provide an enhanced email solution for Government school teachers and corporate staff at DET. | 2013-11-11 | PRINCE2 |  | In progress - implementation | 2015-05-14 | 214280 | 2017-09-22 | 1045087 |  | 1530840 | AMBER | GREEN | GREEN | GREEN | GREEN | Vendors have been selected and engaged. A solution design is undergoing a technical review prior to submission for Management approval. Approval has been sought to extend scope and budget, and re-baseline schedule to accommodate a full mailbox migration for approximately 120,000 users (original scope only 50 users), as the most efficient way to deliver migration rather than the original approach of handing it over to Operations Support Team to progressively migrate all users. The infrastructure build activities have commenced as planned with the project on track to deliver planned benefits, including the provision of an enhanced email solution for Government school teachers and corporate staff at DET. | 2017-03-31
Q3-2016-17 | 6B6471E0-8596-484C-A61C-CFDAAA8ADF6C | Department of Education and Training | DET | International Student Information Management System | Education | This project will identify, procure and customise an existing (Off the Shelf) International Student Information Management System to address existing shortfalls and meet current and future business needs for the International Education Division. | 2014-01-02 | PRINCE2 |  | In progress - implementation | 2016-05-31 | 201000 | 2017-12-08 | 905000 | 2018-03-01 | 1478903 | GREEN | AMBER | GREEN | GREEN | N/A | Due to clearer understanding of detailed requirements and necessary functionality enhancements, a briefing was raised and approved to increase the budget and deliver the enhanced functionality. The supplier is underway with development of the customised solution to compliment the base off-the-shelf product. The Department is developing data migration validation rules and detailed test cases for UAT and to assist the supplier's development and testing. | 2017-03-31
Q3-2016-17 | A173558D-57C2-442B-83CE-9C5D19ECE124 | Department of Education and Training | DET | eduHub | Education | The eduHub project will develop an integration platform that enables secure and reliable exchange of school administration data with 3rd party vendors. The first phase which supports central delivery of the data to schools has been completed. | 2014-03-24 | PRINCE2 |  | Completed | 2015-11-13 | 100472 | 2016-12-31 | 1449528 |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | Go live complete. | 2017-03-31
Q3-2016-17 | 831C988E-83C3-44A5-8C6D-E7DFCE78BA41 | Department of Education and Training | DET | Antivirus for eduMail and eduGate | Education | The Antivirus for eduMail and eduGate project will implement a solution for DET's email platform and websites in order to protect against SPAM and malware threats. | 2014-07-23 | PRINCE2 |  | Completed | 2015-10-31 | 271000 | 2015-12-31 | 1229000 | 2016-07-29 | 1520000 | GREEN | GREEN | GREEN | GREEN | GREEN | The antivirus and spam protection solution have been successfully deployed. Email protection has been successfully deployed. The project scope has delivered protection of the Department's email and websites against virus and SPAM threats. Project is commencing close out activities. | 2017-03-31
Q3-2016-17 | 9300696A-14B5-4D65-8325-83871F2A1687 | Department of Education and Training | DET | eduPass Phase 3 Staff Provisioning | Education | The eduPass Phase 3 Staff Provisioning project will provide a system to manage the identity (username and password) and access controls for over 100,000 users in the Department of Education and Training. | 2014-11-07 | PRINCE2 |  | Completed | 2015-02-28 | 580968 | 2016-03-31 | 2019032 | 2017-03-20 | 3419032 | GREEN | AMBER | GREEN | AMBER | AMBER | Further data cleansing activities required post end of February. Project live as at 20 March 2017. | 2017-03-31
Q3-2016-17 | 8B759B25-3C35-4848-9F65-B6D9CCE2F81D | Department of Education and Training | DET | CASES Technology Refresh | Education | The CASES Technology Refresh project will perform the 4 year refresh of Government schools' technology environment to support administration and financial management functions. The scope encompasses a server, workstations, switch, UPS, printer and backup service. | 2014-12-19 | PRINCE2 |  | In progress - implementation | 2016-07-20 | 692729 | 2017-02-28 | 14707271 | 2017-07-31 |  | GREEN | GREEN | GREEN | N/A | N/A | Installation of network switches, school servers, desktops, and printers is complete. Procurement is underway for the centralised backup ICT solution. Project has completed the installation of refreshed equipment at schools during the first school term of 2017 and the backup solution will commence deployment in term 2. | 2017-03-31
Q3-2016-17 | AC434B54-18F9-494A-83BE-33714A2FFEE8 | Department of Education and Training | DET | Insight Part A Migration | Education | Migration of all existing DET paper and online assessments that exist in disparate systems onto the Insight Platform to provide teachers with the opportunity to understand student progress and develop targeted learning plans to increase student achievement. | 2015-02-01 | PRINCE2 |  | Completed | 2015-06-30 | 150000 | 2016-09-30 | 2500000 |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | The migration "Part A" instruments (everything other than on-demand instruments) has been completed and will be deployed to production. | 2017-03-31
Q3-2016-17 | F39DA9A5-0659-4E84-BD7F-314615493E2E | Department of Education and Training | DET | HCM and Local Payroll - Schools Local Payroll (SLP) | Education | The project will migrate the School Council payroll from the schools’ local administration system (CASES21) to DET’s central payroll system (eduPay) through extension of DET's PeopleSoft based eduPay shared services arrangement; delivering a single payroll system for all Department and School Council staff. | 2015-02-19 | PRINCE2 |  | In progress - implementation | 2015-12-31 | 837899 | 2017-06-30 | 2092053 |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | The application is now in production use with schools gradually being migrated across from CASES21 to eduPay. The migration will be completed by 30 June 2017. The project is on track to deliver planned benefits, including enabling DET to strengthen its financial controls and compliance measures for the payment of School Council staff; the ability to connect with, and directly communicate information to all staff; a single system view of the workforce so as to provide improved visibility and functionality for workforce management and planning; and improved productivity of school and corporate administration. | 2017-03-31
Q3-2016-17 | 375103CE-0C1B-4288-B786-63EE697E55F3 | Department of Education and Training | DET | HCM and Local Payroll - Performance (PDP) and Learning Management (LMS) | Education | A fully integrated payroll, performance, career and learning management capability for DET and its shared service customers through extension and utilisation of DET's PeopleSoft based eduPay shared services arrangement. To deliver an integrated solution for VPS and teaching staff and a systemic, evidence-based response to aid strategic decision making. | 2015-02-19 | PRINCE2 |  | In progress - implementation | 2016-03-30 | 398000 | 2017-06-30 | 3712048 | 2017-12-31 |  | GREEN | GREEN | GREEN | GREEN | GREEN | The LMS has been configured and is currently undergoing various forms of testing in preparation for release during 2017. The performance management system to support Performance and Development Planning (PDP) for all VPS and Executive Officers for the 2016/17 period was implemented in August 2016. The performance management system to support the Performance and Development Planning (PDP) for Teaching Service staff for the 2017 school year was released in February 2017. The project is on track to deliver planned benefits by enabling support for improved compliance in terms of financial, performance and learning management; provision of an entire workforce view and facilitating capability, career and succession planning; and more timely and accurate reporting. | 2017-03-31
Q3-2016-17 | F432CE02-811D-4103-AFC6-488E9555038A | Department of Education and Training | DET | Victorian Training Information System (VTIS) | Education | This project is to replace the Skills Victoria Training System (SVTS). This project was previously known as HESG IT Business System Replacement. | 2015-02-23 | PRINCE2 |  | In progress - implementation | 2017-03-30 | 1910590 | 2018-01-31 | 15821697 |  |  | GREEN | N/A | N/A | N/A | N/A | The project has formally moved into the Implementation phase. The project schedule has been reviewed and agreed by both the Department and vendor. The project board has baselined the implementation budget and project schedule. Change management activities have begun and stakeholder workshops have been held. | 2017-03-31
Q3-2016-17 | B7586CF1-6B49-4C1F-991B-2A6BB18AEDD2 | Department of Education and Training | DET | ICT fit-out for Public Private Partnership schools | Education | This project will procure and provision ICT equipment for fit-out of 15 new schools being constructed via the Victorian School Building Authority's New Schools Public Private Partnership (PPP) Project. | 2016-07-01 | PRINCE2 |  | In progress - implementation | 2017-02-28 | 1369524 | 2018-02-28 | 1781166 |  |  | GREEN | N/A | N/A | N/A | N/A | Installation and commissioning of ICT for the first tranche of schools is complete. The project will pause until September when activities for the second and final tranche commence. | 2017-03-31
Q3-2016-17 | D4C5688A-D845-4CAD-BD8A-2B7D7512C568 | Department of Education and Training | DET | eduSTAR SAS for Parents | Education | This project extends the eCASES application to make student attendance and family data available online to pre-registered parents, supporting better engagement in the school community and information on their child’s progress. A Proof-of-Concept in 6 schools (pre-implementation) will prove a solution and confirm the business case for implementation. | 2014-05-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | The project is delivering a limited selection of existing student information to a small group of parents from two schools as an online proof-of-concept. Improved user interfaces are being developed and tested. Once the new interfaces are in place the proof of concept will be extended to four more schools and an increased number of parents. A business case will then be developed prior to any move to full implementation. | 2017-03-31
Q3-2016-17 | 81387017-AFA1-41E2-B2D1-D982CA8D3EB6 | Department of Education and Training | DET | Youth Engagement System | Education | An integrated IT solution which will capture data on disengaged students and students in out-of-home care. It will provide a more comprehensive picture of these key cohorts to ensure they receive the support they need to achieve educational success. | 2017-01-04 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Underlying business processes are being documented. This will be followed by the development of a Solution Concept and a subsequent approach to the market. | 2017-03-31
Q3-2016-17 | 277079FA-D426-4367-8577-31A6E82F4294 | Department of Health and Human Services | DHHS | Health & Hospital Funding Regional ICT cancer Multidisciplinary Meeting Management Project | Health | To deliver a software solution to support multidisciplinary team meetings within and across regional integrated cancer services. | 2012-12-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project planning in progress. | 2017-03-31
Q3-2016-17 | 3E31DAAA-7C0F-4E9B-A887-1D2CB2CB48AC | Department of Health and Human Services | DHHS | Organisation Design and Visualisation | Community Services | Changes to the Human Resources system to move from a people based to a 'position' based structure, improve functionality and provide a better organisational design and change capabilities. | 2013-05-13 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | In progress - implementation | 2014-05-29 | 0 | 2014-09-23 | 934468 | 2017-06-02 | 2086236 | GREEN | AMBER | AMBER | AMBER | GREEN | Revised schedule for final delivery approved by steering committee. Project progressing to revised schedule. | 2017-03-31
Q3-2016-17 | 423EF30E-2193-43FE-A033-B594A2008F76 | Department of Health and Human Services | DHHS | Bendigo Hospital - Group 2 & 3 ICT infrastructure and support systems | Health | Delivery of state-of-the art high availability network, technologies and modern support systems that compliment the new Bendigo Hospital. | 2013-05-28 | PRINCE2 |  | Completed | 2015-08-01 | 45000000 | 2017-01-23 | 36920000 |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | Project successfully completed. | 2017-03-31
Q3-2016-17 | 10553C6A-4DBD-4AFE-AF7C-F6A1DC5C854F | Department of Health and Human Services | DHHS | Network user authentication devices upgrade | Community Services | Replace out-of-date infrastructure to provide user authentication and vendor support services. | 2014-03-11 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | In progress - implementation | 2016-10-19 | 380109 | 2018-11-05 | 1069891 |  | 1464250 | GREEN | GREEN | N/A |  |  | Project progressing to schedule. | 2017-03-31
Q3-2016-17 | EF92AE62-E893-4F6D-A6F4-7700D962211F | Department of Health and Human Services | DHHS | Client Relationship Information System (CRIS) Legislative Changes (Permanency) | Community Services | Significant changes to Integrated Client and Case Management Systems to support child protection permanency reform/legislative changes to the Children, Youth and Families Act 2005, including a better alignment of Children’s Court orders and department case plans and a new range of Children’s Court Orders to support the Permanency Planning Framework | 2014-11-20 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | Completed | 2015-05-22 | 284839 | 2016-02-29 | 3800000 | 2016-08-06 | 3814000 | N/A | GREEN | GREEN | GREEN | GREEN | Project successfully completed. | 2017-03-31
Q3-2016-17 | 6C1E7725-6C25-4B52-BC43-20546CE22337 | Department of Health and Human Services | DHHS | Melton Community Based Ambulatory Care Centre (MCBACC) | Health | Implementation of the ICT integration solution between five health providers at the new Melton Community Based Ambulatory Care Centre | 2016-07-07 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project planning in progress. | 2017-03-31
Q3-2016-17 | 48DF1774-D1D8-4185-9316-96191311523C | Department of Health and Human Services | DHHS | Housing Application Online | Community Services | Enabling potential tenants of Community Service Organisations to submit housing applications online. | 2015-02-20 | Agile |  | Completed | 2016-02-02 | 0 | 2016-07-27 | 1598000 | 2016-09-30 | 1491317 | N/A | GREEN | GREEN | AMBER | GREEN | Project successfully completed. | 2017-03-31
Q3-2016-17 | 9E946175-99B9-4617-A0E9-9AD24D9F6DE6 | Department of Health and Human Services | DHHS | Housing Infrastructure Capital Refresh | Community Services | Replace ageing and unsupported hardware for the production and disaster recovery environments of the Housing Integrated Information Program (HiiP). | 2015-05-28 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | In progress - implementation | 2016-12-13 | 415000 | 2017-03-31 | 5000000 | 2017-06-30 | 5100000 | AMBER | GREEN | N/A |  |  | Schedule and cost revised due to storage performance issues. Project progressing to revised schedule. | 2017-03-31
Q3-2016-17 | F3FF16EB-7A83-44B0-A2DD-9AE829302DB6 | Department of Health and Human Services | DHHS | Budget and Reporting System | Health | The strategic driver in implementing a new budgeting & reporting system is to transform the finance function from a transactional to a value-adding service by providing users with self service capability. The system will replace the current Budget Management System. | 2015-06-01 | PRINCE2 |  | Completed | 2015-12-31 | 178000 | 2016-10-25 | 2752567 |  |  | N/A | GREEN | GREEN | GREEN | GREEN | Project successfully completed. Further works integrated into the implementation of the new Modelling & Payments System (MAPS) project. | 2017-03-31
Q3-2016-17 | 041491EE-BCD4-43E1-84F2-EE08A8273A15 | Department of Health and Human Services | DHHS | Corporate Reporting Tool Upgrade | Community Services | Upgrade the Corporate Reporting software and hardware. | 2015-06-25 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | In progress - implementation | 2015-11-13 | 0 | 2016-06-30 | 1103846 | 2017-05-31 | 1120000 | GREEN | AMBER | AMBER | GREEN | GREEN | Schedule revised due to Steering Committee approved scope increase. Project progressing to revised schedule. | 2017-03-31
Q3-2016-17 | E8BD9A4A-9C3D-4F3B-9446-0479C9402ABC | Department of Health and Human Services | DHHS | Victorian eReferral Program | Health | The Program aims to make referral processes more efficient, safe and reliable. The focus of the program, while necessarily including a significant technical component, will also be establishing appropriate governance, standardisation in business processes and information and the change management necessary to deliver the planned benefits and client outcomes. | 2015-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Pre-implementation activities in progress. | 2017-03-31
Q3-2016-17 | AE143C36-2082-406E-9A3C-C0FC04A6CD94 | Department of Health and Human Services | DHHS | Real-time prescription monitoring system | Health | Implement software that transmits pharmacy records in real-time to a centralised database, enabling doctors and pharmacists to make safer clinical decisions prior to prescribing or dispensing medicines at high risk of misuse. | 2016-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Pre-implementation activities in progress. | 2017-03-31
Q3-2016-17 | B58D2FCF-3C95-4FC1-9D58-CD0BB3375A3C | Department of Health and Human Services | DHHS | Victorian Health Incident Management System (VHIMS) | Health | The key objectives are to (1) Simplify and significantly improve VHIMS functionality for health sector users. (2) Ensure that the process for reporting on VHIMS data is made easier and more meaningful and (3) Enable routine analysis of VHIMS data and dissemination of meaningful standardised reports | 2015-07-06 | PMBoK |  | In progress - implementation | 2017-01-01 | 2250000 | 2019-06-30 | 2700000 |  |  | AMBER | N/A |  |  |  | Oversight of the solution implementation was transferred to the Victorian Agency for Health Information in January 2017. The VHIMS2 project has successfully delivered an improved data store and reporting platform. A simplified dataset and new user interface was co-designed with the sector, and developed as a software upgrade. The pilot phase commenced with two services implementing the new dataset/taxonomy as a software upgrade in September and October 2016. Implementation of the software upgrade proved more complex than anticipated. The approach to implementation of the new dataset/taxonomy is under review. | 2017-03-31
Q3-2016-17 | 8E9ECAF3-7446-4D04-AFD5-F70E6861F814 | Department of Health and Human Services | DHHS | Records Management system upgrade | Community Services | Upgrade the current recordkeeping system software and hardware for all existing users. | 2015-07-12 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | In progress - implementation | 2017-03-07 | 227153 | 2017-08-28 | 2547340 |  |  | GREEN | N/A |  |  |  | Project progressing, vendor to confirm project plan and implementation options end April. | 2017-03-31
Q3-2016-17 | F0A030E2-0262-4E95-AEA4-CCACD742DB1F | Department of Health and Human Services | DHHS | Program Unity | Community Services | Transition DHHS to the Government Shared Platform hosted by CenITex by joining the networks, upgrading infrastructure and moving to a Windows 8.1 desktop. | 2015-07-13 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | Completed | 2016-05-12 | 10795732 | 2016-12-30 | 5182166 | 2017-03-31 |  | GREEN | GREEN | AMBER | AMBER |  | Project successfully completed. | 2017-03-31
Q3-2016-17 | 4895BCC7-1650-49DD-9E0A-6A1A5FACFA1B | Department of Health and Human Services | DHHS | Enabled Divisional Area Enhancements (EDAE) | Community services | Address outstanding issues and deliver enhancements to the Housing Integrated Information Program and Integrated Client and Case Management Systems to reflect the organisational restructure from regions to divisions and areas. | 2015-08-10 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | In progress - implementation | 2016-09-12 | 738470 | 2017-06-24 | 1205363 |  |  | GREEN | N/A |  |  |  | Project progressing to schedule. | 2017-03-31
Q3-2016-17 | 8F362E05-B419-4109-818C-354494E3AFD3 | Department of Health and Human Services | DHHS | Intranet | Community Services | A new combined intranet for the merged former departments. | 2015-08-26 | Agile |  | In progress - implementation | 2016-04-01 | 192105 | 2017-06-30 | 1007895 |  |  | GREEN | GREEN | GREEN |  |  | Project progressing to schedule. | 2017-03-31
Q3-2016-17 | 085D4872-3606-493B-98B5-AE35C523B09A | Department of Health and Human Services | DHHS | Bendigo Hospital - Electronic Medical Record | Health | Electronic Medical Records and Digital Medical Records implementation at the new Bendigo Hospital | 2015-12-23 | PRINCE2 |  | In progress - implementation | 2016-10-05 | 11343000 | 2018-03-31 | 14987000 |  |  | GREEN | GREEN | N/A |  |  | Project progressing to schedule. | 2017-03-31
Q3-2016-17 | 188112FA-CA80-49BF-870F-1F92BDE41A69 | Department of Health and Human Services | DHHS | Automation of Family Violence Referral form - Phase 1 | Community services | Replace fax transmission of Family Violence Referral forms from Victoria Police to Child Protection, Specialist Family Violence Agencies and other community bodies. | 2016-02-15 | Agile |  | Completed | 2016-04-27 | 139680 | 2016-11-16 | 2551720 | 2016-12-06 | 2355534 | N/A | GREEN | AMBER | GREEN |  | Project successfully completed. | 2017-03-31
Q3-2016-17 | 50ED1655-7220-4ECC-BD80-C1A25EBFDAC1 | Department of Health and Human Services | DHHS | Health Sector Finance and Materials Information System (FMIS) upgrade | Health | Upgrade of the Finance and Materials Information System (FMIS) for the Victorian Public Health Sector. | 2016-07-01 | PRINCE2 |  | In progress - implementation | 2016-08-10 | 59997 | 2017-09-15 | 2536110 | 2017-12-20 | 2176240 | AMBER | GREEN | GREEN |  |  | Project delay caused by issues identified during user acceptance testing. Project go-live postponed to accommodate health services' end of financial year reporting period. Project progressing to revised schedule. | 2017-03-31
Q3-2016-17 | DCC9DD56-E088-4568-B3B5-83B16E2DA8ED | Department of Health and Human Services | DHHS | Integration Solution Replacement | Health | Replacement of the integration solution to support Victorian acute public health services with ongoing capability to integrate patient and clinical information within and across health services. | 2016-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project planning in progress. | 2017-03-31
Q3-2016-17 | 92E0212C-3F9F-493D-A891-16F27158A066 | Department of Health and Human Services | DHHS | Integrated Client and Case Management Systems (ICCMS) Data Warehouse transition to Corporate Reporting Tool | Community services | Upgrade unsupported data warehouse for integrated client and case management systems. | 2016-09-01 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | Terminated | [11 empty] | Project not to proceeding past feasibility phase due to identification of significantly reduced cost benefits. | 2017-03-31
Q3-2016-17 | 269F2AD8-C692-45A1-AD9F-5FD0A4AB8725 | Department of Health and Human Services | DHHS | Clinical Services Technology Replacement Program | Health | Replacement of clinical services technology assets at Victorian acute public health services. | 2016-07-01 | PRINCE2 |  | In progress - implementation | 2017-01-10 | 0 | 2017-06-30 | 10000 |  |  | GREEN | N/A |  |  |  | Project progressing to schedule. | 2017-03-31
Q3-2016-17 | 9875085D-F469-4DEF-B614-F51EBA1EDEF8 | Department of Health and Human Services | DHHS | Windows Server Remediation Program | Community services | Upgrade, replace or decommission outdated servers and database instances. | 2016-07-01 | Agile |  | In progress - implementation | 2016-07-01 | 0 | 2019-06-30 | 11800000 |  | 9808000 | GREEN | GREEN | GREEN |  |  | Project progressing to schedule. | 2017-03-31
Q3-2016-17 | 6289B205-46EE-4CFF-AF04-40302D7FF061 | Department of Health and Human Services | DHHS | Parkville Precinct Electronic Medical Record | Health | Implementation of an Electronic Medical Record into Melbourne Health, Peter MaCallum Cancer Centre and The Royal Women's Health Services. | 2016-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project planning in progress. | 2017-03-31
Q3-2016-17 | 1EE7596A-96E9-4CEE-9364-36B3A3F3D033 | Department of Health and Human Services | DHHS | Digital Patient Identification | Health | Implementation of a state-wide Enterprise Master Patient Index (EMPI) to support the objectives of Health 2020, the Clinical Information Exchange (CIE), improved analytic capability and access to My Health Record. | 2016-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project planning in progress. | 2017-03-31
Q3-2016-17 | 5B1A20E6-E473-4F0D-8AEF-FB6532F23E4C | Department of Health and Human Services | DHHS | Immunisation Provider System (ImPS) Replacement | Health | Implementation of a computerised solution to allow local governments and other stakeholders in Victoria to manage local immunisation programs including vaccine stock control and data reporting. | 2016-12-14 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | Initiated | [11 empty] | Project proposal with business owner for consideration. Decision to proceed pending. | 2017-03-31
Q3-2016-17 | F13D456C-7EDE-4946-B30A-B6267D63B765 | Department of Health and Human Services | DHHS | Modelling and Payments System (MAPS) | Health | Replacement for the budget modelling, payments and National Health Reform reporting platforms - the Budget and Payments System Modeller (BPS Modeller), the Budget and Payments System (BPS) and the National Health Funding Body Payments System (NHFBPS) - with an integrated, single solution. | 2016-05-23 | PRINCE2 |  | In progress - implementation | 2016-06-07 | 0 | 2017-08-09 | 1226060 | 2018-02-01 |  | GREEN | AMBER | AMBER | GREEN |  | Formal budget / contract variation (additional costs) being sought for revised implementation date following Project Board endorsement. Project progressing to schedule. | 2017-03-31
Q3-2016-17 | 7D3BCD20-7CC4-4053-939E-3ADFAF6A800D | Department of Health and Human Services | DHHS | Client Incident Management Solution (CIMS) | Community services | Development of a technology solution to support implementation of a state-wide policy for management of client incidents. | 2016-05-30 | Agile |  | In progress - implementation | 2016-08-31 | 0 | 2017-06-30 | 2659000 |  |  | GREEN | N/A |  |  |  | Project progressing to schedule. | 2017-03-31
Q3-2016-17 | A6425E12-3672-4792-8E17-EA647A652A0D | Department of Justice & Regulation | DJR | Rostering for Prisons | Law and justice | Procurement and implementation of a rostering system that assists prisons to effectively and efficiently meet their staffing, management and reporting needs. | 2011-11-14 | Other – please specify | Project Management Excellence | In progress - implementation | 2013-02-04 | 0 | 2015-06-30 | 1396882.28 | 2017-10-31 | 5415000 | GREEN | GREEN | GREEN | GREEN | GREEN | Grampians and Loddon Prisons have gone live (5th and 19th February 2017). MRC currently in trial period. | 2017-03-31
Q3-2016-17 | 8A47D6A2-0453-49CE-99FE-FDFD9C116C7B | Department of Justice & Regulation | DJR | LaGIS - Liquor and Gambling Information System Project | Law and justice | The Liquor and Gambling Information System (LaGIS) aims to improve the efficiency of the Victorian Commission for Gambling and Liquor Regulation's regulatory processes by delivering an integrated system for licensing and compliance. | 2012-02-22 | Other – please specify | Project Management Excellence | Completed | 2012-05-31 | 344816.04 | 2015-12-22 | 11820849.01 | 2017-02-23 | 12690093 | GREEN | GREEN | GREEN | AMBER | AMBER | The LaGIS system went into production on 5 December 2016 and has now successfully transitioned to the VCGLR ICT and Business Administrators for ongoing carriage and routine management. Project has been closed following Steering Committee endorsement in February 2017. | 2017-03-31
Q3-2016-17 | 06067601-2D18-48E3-8F60-71489A6AA73F | Department of Justice & Regulation | DJR | Mobile Camera Replacement (MCR) Project | Law and justice | MCR Project is the procurement of a replacement mobile camera system for the IMES business unit. The mobile camera system is the key component of the mobile camera service provided to the State by Serco Traffic Camera Services. | 2012-12-03 | Other – please specify | Project Management Excellence | In progress - implementation | 2014-02-19 | 1568992.5 | 2015-12-21 | 0 | 2017-06-30 | 0 | AMBER | AMBER | GREEN | GREEN | GREEN | The Pilot Stage is continuing with two short listed camera suppliers. The project team is preparing for testing, training and final on-road evaluation trials. | 2017-03-31
Q3-2016-17 | B65282BF-398B-481C-A821-E4AAAAC6B0BC | Department of Justice & Regulation | DJR | Upgrade project - Electronic Document and Records Management System (eDRMS) Upgrade | Law and justice | TRIM is DJR's electronic document and records management system (eDRMS). It requires an upgrade from v6 [last installed 2008] to v8.2, being compatible with Windows 8.The project is in the development environment stage, close to a pre-production environment with go-live likely this calendar year. | 2013-02-26 | Other – please specify | Project Management Excellence | In progress - implementation | 2015-03-25 | 2020139 | 2016-07-31 | 3470677 | 2017-05-30 | 3470677 | GREEN | GREEN | GREEN | GREEN | GREEN | Deployment is complex but is on track to complete in June 2017. Project successfully progressed to pre-deployment status. | 2017-03-31
Q3-2016-17 | D4183B03-BEA3-4423-A3BD-D425C03B60F7 | Department of Justice & Regulation | DJR | Win 8 Desktop Upgrade Project | Law and justice | Win 8 Upgrade to replace Win XP DJR desktops | 2013-07-01 | Other – please specify | Project Management Excellence | Completed | 2013-12-13 | 2800000 | 2015-12-31 | 5400000 | 2016-11-30 | 4105000 | GREEN | GREEN | GREEN | AMBER | GREEN | Project is complete. | 2017-03-31
Q3-2016-17 | CA3494BE-4208-47F0-A8FF-0AB9E0756753 | Department of Justice & Regulation | DJR | ACMA Compliance | Emergencies and safety | This project moves five agencies from their existing radio systems onto shared, multi-agency radio systems, in order for the agencies to comply with new ACMA regulations. The project also includes the procurement of new radio terminals and associated services under a state-based managed services contract. | 2013-07-01 | Other – please specify | Project Management Excellence | In progress - pre-implementation | [11 empty] | The procurement process for the new Managed Device Service is complete and is progressing with delivery from January 2017. The State is continuing network procurement activities for on-boarding customer agencies, which are due for completion by the end of May 2017. | 2017-03-31
Q3-2016-17 | BB8F3133-4BC8-414B-AE5B-25A4ADB96F23 | Department of Justice & Regulation | DJR | Births, Deaths and Marriages (BDM) Core System Replacement Project | Law and justice | The replacement of the BDM core system will provide a scalable and robust design with enhanced functionality and migrated data. | 2013-10-01 | Other – please specify | Project Management Excellence | In progress - implementation | 2014-06-30 | 1518095.36 | 2017-06-19 | 13925000 | 2017-12-20 | 17526000 | GREEN | GREEN | GREEN | GREEN | GREEN | The project is in Delivery Stage and system development is underway. First round of testing has been completed. Second round of testing will be completed by June 2017. Additional scope approved by the Justice Finance Committee has resulted in an overall increase to the budget and extended completion to December 2017. | 2017-03-31
Q3-2016-17 | 11CD0994-A403-493F-AD1B-22520AF00611 | Department of Justice & Regulation | DJR | CV-CATS- APB Case Workflow System - | Law and justice | The provision of an electronic database and case workflow system that aligns to a re-engineered set of business processes to deliver a significantly improved and enhanced user experience | 2014-04-01 | Other – please specify | Project Management Excellence | In progress - implementation | 2015-11-20 | 996219 | 2016-12-15 | 3811985 | 2018-12-31 | 6909298 | AMBER | AMBER | AMBER | GREEN | GREEN | Phase 1 of the Adult Parole Board (APB) Case Workflow System is in operation. Project will be delivered in stages through to 2018 which includes additional supporting infrastructure and further analysis to confirm workflow solution requirements. Project is continuing to resolve procurement arrangements. | 2017-03-31
Q3-2016-17 | 4A60FB2A-9801-4262-AF2C-4E070D46E907 | Department of Justice & Regulation | DJR | E*Justice Strengthened Enforcement | Law and justice | Implement changes to the current IT system and database to ensure compliance with new legislative, policy and practice changes to support the Government's parole reform agenda. | 2014-07-01 | Other – please specify | Project Management Excellence | In progress - implementation | 2015-12-23 | 0 | 2016-06-30 | 1028095 | 2017-07-30 | 1872300 | AMBER | AMBER | AMBER | AMBER | GREEN | Three components have been completed as planned. The fourth component is behind schedule following testing issues with an external agency. UAT defects are being addressed and the project is aiming to complete the production release on 30 May 2017. | 2017-03-31
Q3-2016-17 | BFFBD9BE-A506-4455-AF71-75D06FA8B864 | Department of Justice & Regulation | DJR | Emergency Alert Phase 3 - Delivery | Emergencies and safety | Capital works associated with the Emergency Alert carrier contract extensions up to June 2018. 4G implementation and technology uplift. | 2014-07-01 | Other – please specify | Project Management Excellence | In progress - implementation | 2015-07-01 | 1405046 | 2016-07-25 | 11533626 | 2017-06-30 |  | GREEN | AMBER | AMBER | AMBER | GREEN | 4G upgrade completed. Telstra have completed all works and are ready for final commissioning which is due 2 May 2017. | 2017-03-31
Q3-2016-17 | 6C50E709-47D4-41E4-B77D-3FD0C4B0CA9A | Department of Justice & Regulation | DJR | Prisoner Transport Order System (PTOS) | Law and justice | The PTOS Project will deliver an integrated transport order and information management system for implementation across Corrections, Police and DHHS to provide transport orders to the contractor and management information for all prisoner transports. | 2014-11-04 | Other – please specify | Project Management Excellence | In progress - implementation | 2014-12-04 | 180000 | 2016-09-05 | 3761184 | 2017-03-01 | 7540249 | GREEN | AMBER | GREEN | GREEN | GREEN | The Prisoner Transport Program (PTP) Steering Committee held on 8 February 2017 approved a revised project schedule and budget to deliver more detailed functionality prior to launch. | 2017-03-31
Q3-2016-17 | 8FD77B53-37C0-4739-BF5B-8F0D38B9E30D | Department of Justice & Regulation | DJR | Asset Refresh | Law and justice | The Asset Refresh program of work is an ongoing, multi-year program that uses infrastructure assets depreciation funds to replace like for like infrastructure to maintain the environment at DJR and promote stability and continuity. | 2015-07-01 | Other – please specify | Project Management Excellence | Completed | 2015-12-30 | 5000 | 2016-06-30 | 2416180 | 2016-08-30 |  | GREEN | GREEN | GREEN | GREEN | GREEN | Project is complete. | 2017-03-31
Q3-2016-17 | 2417684C-75F3-4F2C-B486-2845B2C69F2E | Department of Justice & Regulation | DJR | DJR Information Management Strategy | Law and justice | A program of work to build information management capability within the department and address known issues in relation to the management of information. | 2015-07-01 | Other – please specify | Project Management Excellence | In progress - implementation | 2015-09-01 | 83000 | 2018-06-30 | 1375600 |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | Stage Two of IMS (2015-18) builds on the policy framework developed in Stage One by embedding behavioural change. All streams including communications, training and IM capability assessments progressing to plan. | 2017-03-31
Q3-2016-17 | 34709842-E4CC-4D8B-B697-2B9CBE4A99EF | Department of Justice & Regulation | DJR | Jcare - electronic prescribing | Law and justice | The Jcare - electronic prescribing project will provide additional functionality to the current electronic health record used in Victorian prisons (Jcare) to allow clinicians to prescribe medication within Jcare. | 2015-07-01 | Other – please specify | Project Management Excellence | In progress - implementation | 2015-07-01 | 0 | 2017-01-01 | 1716000 | 2017-07-01 | 1808719 | GREEN | GREEN | GREEN | GREEN | GREEN | Rollout of the eMM functionality commenced on 6 February 2017 and has been released successfully to 10 of the 15 prison sites. The remaining sites will be completed before 30 June 2017. | 2017-03-31
Q3-2016-17 | B2C53213-E810-4199-AB05-016E482D260D | Department of Justice & Regulation | DJR | CCS Accommodation Expansion Program | Law and justice | IT fitout for sites being constructed or modified to accommodate additional staff for Community Correctional Services (CCS) and other business units across Victoria. The number of sites potentially requiring IT treatment has recently increased from 29 to 59 sites. | 2015-07-29 | Other – please specify | Project Management Excellence | In progress - implementation | 2016-01-18 | 88043 | 2016-12-30 | 2610975 | 2019-06-30 | 6895000 | GREEN | GREEN | GREEN | GREEN | GREEN | Eight sites successfully deployed to March 2107. Project is on track to deliver a further five sites between April and June 2017. Program is expected to run until June 2019. | 2017-03-31
Q3-2016-17 | C6CDEC69-2300-4AEF-BD39-EEAA677EEC53 | Department of Justice & Regulation | DJR | Police Digital Radio Upgrade Project ('PDRUP') | Emergencies and safety | Migrate Victoria Police outside of the metro (MMR network) area from the legacy (analogue unencrypted) radio network (StateNet Mobile Radio ('SMR')) to the new (digital and encrypted) network (Regional Mobile Radio ('RMR')) | 2015-09-07 | Other – please specify | Project Management Excellence | In progress - implementation | 2016-01-14 | 0 | 2017-08-07 | 14100000 | 2018-11-30 |  | AMBER | AMBER | RED | AMBER | GREEN | The procurement process for the new Managed Device Service is complete and is progressing with delivery from January 2017. The State is continuing network procurement activities for on-boarding customer agencies, which are due for completion by the end of May 2017. | 2017-03-31
Q3-2016-17 | C8C50184-9D92-4C7B-8D5F-35D8757A878B | Department of Justice & Regulation | DJR | New Infringements ICT System | Law and justice | Reform Program following the successful passage of the Fines Reform Act (2014). The ICT component of the program involves the procurement of an end-to-end COTS system to replace its current legacy infringement management system, VIMS, addressing all changes under the Act. | 2015-10-27 | Other – please specify | Project Management Excellence | In progress - pre-implementation | [11 empty] | The contract has been awarded and the project remains on schedule. The testing of Software Drop #2 has been completed. The Data Conversion team have completed workshops. The independent review related to the 'Go / No Go' decision is underway. The project has an aggressive timeline to complete and as such, will be very closely monitored. | 2017-03-31
Q3-2016-17 | 4714C415-0D0F-4703-B62B-FB2AA0E5CD79 | Department of Justice & Regulation | DJR | Internet Remediation Project | Law and justice | A program of works to remediate and stabilise the Internet used by Courts & DJR. This includes proxy servers, DNS, SMTP, core switches and mobility. | 2015-11-30 | Other – please specify | Project Management Excellence | Completed | 2015-12-09 | 25 | 2016-12-31 | 4156300 | 2017-03-31 | 4156300 | GREEN | GREEN | GREEN | GREEN | GREEN | Project delivery is now complete. | 2017-03-31
Q3-2016-17 | 46E3F515-0E50-4E2C-9207-302BF866E461 | Department of Justice & Regulation | DJR | Capacity Uplift Project | Law and justice | This project will procure and implement additional capacity into the DJR Data Centres at Burwood and Ballarat. | 2016-03-22 | Other – please specify | Project Management Excellence | Completed | 2016-07-01 | 0 | 2016-10-31 | 2301476 | 2017-03-31 | 2693100 | GREEN | GREEN | GREEN | GREEN | GREEN | Project delivery is now complete. | 2017-03-31
Q3-2016-17 | 64FBAE5B-1C9F-4CCF-8D22-F99DEE02A842 | Department of Justice & Regulation | DJR | Emergency Alert Phase 4 - Delivery | Emergencies and safety | Secure service continuity and delivery of a national telephony based emergency warning system, ensuring a more sustainable EA service: a service that remains up to date and relevant to community use and demand, maintains an acceptable performance standard and incurs minimal capital expenditure and cost surprises. | 2016-05-06 | Other – please specify | Project Management Excellence | In progress - pre-implementation | [11 empty] | Tenders closed 22 December 2016. Evaluations have been completed. Negotiations with the preferred Offerer(s) underway. | 2017-03-31
Q3-2016-17 | F5BED7E2-6D2D-4213-8951-E4B88A9716AC | Department of Justice & Regulation | DJR | Hosting Services Project | Law and justice | SecureWorx currently provides a number of hosting services for DJR. The provision of hosting services is an ongoing requirement for a number of key applications within Corrections Victoria (CV). The project will manage the procurement and transition of hosting, monitoring, disaster recovery, penetration testing and performance testing services for CV. | 2016-06-15 | Other – please specify | Project Management Excellence | In progress - pre-implementation | [11 empty] | The Steering Committee has approved that a selective tender be conducted to ensure value for money. The services that are being sought include hosting, monitoring, high availability/disaster recovery, penetration testing and performance testing. | 2017-03-31
Q3-2016-17 | CE460EA7-12D8-4014-92C1-65F231E1574D | Department of Justice & Regulation | DJR | Oracle R12 & BI Implementation Project | Law and justice | To ensure the Oracle E-Business Suite (EBS) is upgraded to the current, supported ‘release 12’ version. Currently DJR uses a release 11 version that is unsupported by the vendor. Business Intelligence (BI) reporting also requires enhancement to support the R12 upgrade. | 2015-05-01 | Other – please specify | Project Management Excellence | In progress - implementation | 2015-11-24 | 0 | 2017-10-31 | 4100000 |  | 5100000 | AMBER | AMBER | N/A | N/A | N/A | On 24 February, the project Steering Committee approved rescoping of the project to include BI R12 alignment as part of the project because of co-dependency. The project is undertaking development and system testing focussing on the functional components of the system. The project is currently assessing the impact of current testing issues on the planned implementation date. | 2017-03-31
Q3-2016-17 | BA6B2E7E-CA2D-4DA6-A5DF-5CACFFD6AFF0 | Department of Justice & Regulation | DJR | Electronic Sourcing Project | Law and justice | The purpose of the eSourcing Project is to enhance the department’s procurement capability (across people, processes, governance and technology systems). To achieve this objective, the project will seek to implement an ICT solution that will automate and standardise procurement practices presently performed manually and inconsistently in the department. | 2015-08-01 | Other – please specify | Project Management Excellence | In progress - implementation | 2016-07-30 | 120000 | 2017-08-31 | 2980000 | 2017-12-11 |  | AMBER | GREEN | N/A | N/A | N/A | The first stage of tender evaluation is complete and Evaluation Team reports are being considered by the Evaluation Panel. Implementation date has been extended due to the Steering Committee request to investigate suitability of the department's Oracle system, which was not originally included in the project scope. | 2017-03-31
Q3-2016-17 | D12E9555-2777-43D2-B7FA-8A183E1300FD | Department of Justice & Regulation | DJR | Regional Radio Command Service | Emergencies and safety | Establish new command and control level voice communication service on the Regional Mobile Radio network. Establish interconnectivity between Regional Radio Command Service, Incident Control Centres and operational facilities | 2014-07-01 | Other – please specify | Project Management Excellence | In progress - implementation | 2016-06-30 | 8000000 | 2017-06-30 | 5000000 | 2018-06-30 |  | AMBER | AMBER | AMBER | GREEN | GREEN | Project has been transitioned from CFA to EMV for delivery. Work continues to extend the existing command channel network and provide connectivity from Command Radio sites into Incident Control Centres. | 2017-03-31
Q3-2016-17 | 2AEBC647-D000-4594-8684-7E1D7BF179C5 | Department of Justice & Regulation | DJR | Asset Refresh 2016-17 | Law and justice | The Asset Refresh program of work is an ongoing, multi-year program that uses infrastructure assets depreciation funds to replace like for like infrastructure to maintain the environment at DJR and promote stability and continuity. | 2016-07-01 | Other – please specify | Project Management Excellence | In progress - implementation | 2016-09-30 | 5000 | 2017-06-30 | 2000000 |  |  | GREEN | GREEN | N/A |  |  | Project is on track to complete by end of June 2017. | 2017-03-31
Q3-2016-17 | B3F0DDD6-CAC6-4D65-A776-94770FEAA74A | Department of Premier and Cabinet | DPC | ACHRIS Phase 2 Enhancement Project | Culture, sport and recreation | The ACHRIS Phase 2 Enhancement Project will deliver new functionality to AVs online application to support the implementation of the Aboriginal Heritage Amendment Act 21016 and a new infrastructure environment to enable the required flexibility, scalability and operational efficiency to implement these changes. | 2015-01-01 | Agile |  | In progress - implementation | 2015-12-30 | 42900 | 2019-06-30 | 1950000 |  |  | GREEN | GREEN | GREEN | GREEN |  | Overall the ACHRIS Phase 2 project is progressing according to schedule however the transition to the cloud is running a few months behind the anticipated timeline. This was brought about by competing priorities. A draft project schedule for transition ACHRIS to the cloud has been produced and a testing strategy is currently being developed. | 2017-03-31
Q3-2016-17 | 91D2745E-B192-4E8E-BCD6-4022F8F89DAE | Department of Premier and Cabinet | DPC | Single Digital Presence | Government and economy | The Victorian Government will make it easier for Victorians to find, access and understand government information by redesigning and re-platforming Premier & Cabinet websites, including vic.gov.au. This project will also reduce the cost and risk associated with digital services and help us create new services faster. | 2015-09-17 | Agile |  | In progress - implementation | 2016-06-30 | 118800 | 2018-06-30 | 4200000 | 2018-12-30 | 4200000 | GREEN | GREEN | GREEN | GREEN |  | The CMS platform has been recommended (Drupal 8) and endorsed by PCB. The project is now focused on finding a vendor to implement the recommendation. A RFQ is being prepared for release by end of May 2017. It will address implementation and customisation of the platform, hosting and operational support to meet the departments needs. | 2017-03-31
Q3-2016-17 | 63FE2940-257B-4616-AEFF-516138AC73E8 | Department of Premier and Cabinet | DPC | Service Victoria | Government and economy | Service Victoria will create a new whole of government service capability to enhance the delivery of government transactions with citizens, enable the delivery of a more effective customer experience and create new distribution channels for simple, high volume transactions. | 2015-07-01 | Other – please specify | Waterfall and agile methodologies used. | In progress - pre-implementation | [11 empty] | Service Victoria is focusing on the needs of the customer and establishing new systems, processes and digital platform to deliver a better customer experience. It has completed its planning phase which included working through policy, technology and customer requirements and is now transitioning into implementation | 2017-03-31
Q3-2016-17 | 303A0D99-1A4D-4D45-B607-DF242EF08EF0 | Department of Premier and Cabinet | DPC | TPAMS2025 Project | Government and economy | TPAMS2025 will replace the current Telecommunications Purchasing and Management Strategy (TPAMS) State Purchase Contracts (SPCs) with new SPC arrangements for data, voice, mobile and unified communications services. | 2015-03-31 | PRINCE2 |  | Completed | 2016-01-21 | 226977 | 2016-11-30 | 2773023 | 2017-02-01 |  | N/A | GREEN | GREEN | GREEN |  | The approval process for the TPAMS2025 Business Case was completed. External project resources were engaged. Working groups from major customer agencies provide technical input. | 2017-03-31
Q3-2016-17 | 1705C2A7-9C48-4716-8396-8B9FAA9CA040 | Department of Premier and Cabinet | DPC | Central Consultation Platform (CCP) Project | Government and economy | This project will deliver a service and platform for use by the Whole of Vic Government (WoVG) to conduct online consultations with the Victorian public. A basic platform will initially be released as a pilot to collect feedback. A fully featured solution will be delivered in subsequent project releases. | 2016-05-01 | Agile |  | In progress - implementation | 2016-05-01 | 42531 | 2017-06-15 | 1158270.3977 |  |  | GREEN | GREEN | GREEN | GREEN |  | The engage.vic.gov.au site has been operational since October 2016. All government departments are either using the platform to conduct online community consultations or are planning to in the near future. New platform features and enhancements are currently under development with the next major release due mid March 2017. | 2017-03-31
Q3-2016-17 | D8CBFD64-4931-4E0A-B7AA-B651F4951035 | Department of Treasury and Finance | DTF | ERP - Financial system | Government and economy | DTF are replacing its legacy Finance and procurement systems | 2017-01-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project in planning phase, RFT distributed to market for solution. Vendor selection is anticipated to be complete by July 2017 | 2017-03-31
Q3-2016-17 | 15A4F0E1-5BB9-4DD4-9B62-F29900483FED | Eastern Health | EH | Eastern Health - Electronic Medical Record | Health | Build a single Longitudinal Medical Record which ensures that relevant critical information for the provision of patient care is available in the one place at the time of clinical decision making, and ensures presentation in a comprehensive, consistent and contextual manner. | 2015-01-01 | Other – please specify | Cerner Consulting Framework | In progress - implementation | 2015-09-30 | 1027020 | 2017-12-31 | 18852980 |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | Project progressing to schedule. | 2017-03-31
Q3-2016-17 | FED55D67-55A2-4A73-A3D6-F3FA60CAE3D6 | Eastern Health | EH | Eastern Health - PCMS Project | Health | Replacement of five (5) existing Patient Administration Systems with the Patient and Client Management System (PCMS) solution. | 2016-08-22 | Other – please specify | HTS PCMS Implementation Methodology | In progress - pre-implementation | [11 empty] | Project progressing to schedule. | 2017-03-31
Q3-2016-17 | 88C23C21-C776-4E66-A652-AD92B4F2BE29 | Eastern Health | EH | Eastern Health - Angliss and Maroondah Hospitals Emergency Department IS Replacement | Health | Emergency Department information system replacement at Angliss and Maroondah Hospitals. | 2016-10-10 | Other – please specify | Cerner Consulting Framework | In progress - implementation | 2017-03-30 | 366750 | 2018-06-30 | 2092300 |  |  | GREEN | GREEN |  |  |  | Project progressing to schedule. | 2017-03-31
Q3-2016-17 | B37A3DF7-7887-4027-AFB7-7694396FECAE | Energy Safe Victoria | ESV | 0005 - Gas Online Application | Business and industry | Replacement of manual forms process with automated portal process for Applications for Gas Supply | 2014-10-01 | Agile |  | Completed | 2015-04-15 | 35900 | 2016-06-30 | 604000 | 2016-08-31 | 1087238 | GREEN | GREEN | GREEN | GREEN | GREEN | Final project costs now received with an addition $15k spent in this reporting period bring the project to closure. | 2017-03-31
Q3-2016-17 | 2E9F5826-352A-403D-95D4-A449DCA9521A | Energy Safe Victoria | ESV | 0033 - ESV Connect: Licensing and Registration | Business and industry | Replacement of legacy system | 2016-06-01 | Agile |  | Completed | 2016-08-01 | 395628 | 2017-06-30 | 2000000 | 2017-03-17 | 1126958 | GREEN | GREEN | GREEN | GREEN | GREEN | Project is complete. | 2017-03-31
Q3-2016-17 | B571CFA9-98DC-4EBD-8418-90772E62F356 | Gippsland Health Alliance | GHA | Electronic Medical Record and Community Health (EMRCH) | Health | The EMRCH project is a core component to the facilitation of highly integrated health services across all aspects of the specific services administered by the members of the Gippsland Health alliance, its implementation will facilitate the implementation of new models of care. | 2016-02-02 | PMBoK |  | In progress - pre-implementation | [11 empty] | Detailed evaluation completed. Product demonstrations completed. BAFO clarification completed. Finalising selection results. Business case being submitted to Project control group. | 2017-03-31
Q3-2016-17 | C8B101DA-DB87-4F37-B359-1B033477845D | Goulburn-Murray Rural Water Corporation | Goulburn MW | ECMS Upgrade / Replacement | Environment and water | The existing Records and Document Management System is not meeting the organisation's requirements. The objective of this project is to define the organisation's requirements and to source and implement an Enterprise Content Management System (ECMS) that meets the organisation's current and future requirements for Records, Documents and Information Management. | 2016-01-18 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | The project is in the pre-implementation phase. | 2017-03-31
Q3-2016-17 | 34D73A18-7CC8-43F8-88DB-25219C34E20E | Goulburn Valley Region Water Corporation | Goulburn VW | Financial Management Information System | Environment and water | Upgrade of Goulburn Valley Water's existing and aging financial management information system | 2016-03-01 | Other – please specify | Internal GVW Project Management Methodology | In progress - implementation | 2017-03-31 | 105567 | 2018-03-31 | 1382285 |  |  | GREEN | GREEN |  |  |  | Project has commenced | 2017-03-31
Q3-2016-17 | B1E7A8CD-2CF3-4255-8A86-C67CACE54298 | Grampians Rural Health Alliance | GRHA | Ballarat Health Services - Rostering & Payroll Interface Project | Health | Implement organisation-wide rostering application and integrate with existing payroll application | 2015-03-16 | Agile |  | In progress - implementation | 2015-06-30 | 465200 | 2017-06-30 | 2252013 | 2017-09-30 |  | GREEN | AMBER | GREEN | GREEN | AMBER | Project is progressing well, with uptake across multiple clinical and corporate departments. An independent interim review was completed in February/March to assess the level of adoption and identify key benefits and issues. Work is continuing with Allocate to maximise efficiency of the application to ensure optimum performance. | 2017-03-31
Q3-2016-17 | 4ED08A36-BDB2-47DE-AD26-A594F7262903 | Grampians Rural Health Alliance | GRHA | Regional EMR/HIE Implementation | Health | The development and implementation of shared electronic medical records across the Grampians region | 2015-08-01 | PRINCE2 |  | In progress - implementation | 2016-06-30 | 1206242 | 2017-03-31 | 1493758 | 2018-02-28 | 1693758 | AMBER | GREEN | GREEN | GREEN | GREEN | Timeline has been extended by 11 months by challenges implementing the shared infrastructure environments, this is a delicate process as the solution merges with existing production EMR at Ballarat Health Services. Positive stakeholder engagement allows us to proceed with confidence and regional budget collaboration is underway to ensure delivery. | 2017-03-31
Q3-2016-17 | 3675C2AB-2414-4C5C-8EB2-0C83A452C323 | Grampians Wimmera Mallee Water Corporation | GWMWater | Water Treatment Plant PLC Replacements | Environment and water | Renewal of PLCs (Programmable Logic Controllers) at priority Water Treatment Plants to replace redundant technology. | 2014-08-12 | PRINCE2 |  | In progress - implementation | 2016-09-30 | 164327.1 | 2018-06-30 | 1069673 |  |  | GREEN | GREEN | GREEN | GREEN |  | Contract was awarded in March 2017. Development of PLC code will commence in May 2017. | 2017-03-31
Q3-2016-17 | 5D00C5DD-BF2A-40AA-B46C-90AC539A6B7D | Health Purchasing Victoria | HPV | Supply Chain Reform Program - Project P058 (Purchasing and Logistics Improvement Project) | Health | Design, source and implement at Melb Health a state-wide purchasing and logistics solution | 2016-05-04 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Business case submitted to DHHS for review | 2017-03-31
Q3-2016-17 | 2127CD86-21D1-469B-B403-5F99CF0D563D | Health Purchasing Victoria | HPV | Supply Chain Reform Program - Project P061 (Information Standards and Master Data Project) | Health | Develop common catalogue data and master data processes for the state | 2016-05-04 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Business case submitted to DHHS for review | 2017-03-31
Q3-2016-17 | 658AB860-05DC-43E9-9A20-6119C3BBA05F | Hume Rural Health Alliance | HRHA | Patient Administration System (PAS) replacement project | Health | A replacement Patient Administration System (PAS) to address problems associated with end of life technology, difficulty harnessing integrated data and difficulty keeping pace with advances in health management technology. The replacement PAS will be adopted by health services within the Hume Region | 2014-02-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | The project Implementation Planning Study (IPS) was completed in April 2017. The project implementation plan and cost allocation model are currently being finalised. | 2017-03-31
Q3-2016-17 | 42840EA7-8031-4E89-9342-5D301A102B3D | Hume Rural Health Alliance | HRHA | Goulburn Valley Health Redevelopment | Health | The ICT component of the redevelopment of the Goulburn Valley Health Hospital to support improved health outcomes for the GV community, better access to health care in the GV community and the better use of health resources in Victoria. | 2016-04-20 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | The project is currently in the design development phase | 2017-03-31
Q3-2016-17 | A601DB88-0FBF-4450-8710-DADC3B5FCE23 | Melbourne Health | Melb H | Pathology Laboratory Information System Replacement | Health | Implementation of a common laboratory information system as an externally hosted fully managed service in collaboration with two other state public health services. Will replace existing internally hosted pathology laboratory system. | 2014-07-21 | Other – please specify | Overarching Prince 2 approaching with Agile management of agency configuration and build. | In progress - implementation | 2015-06-04 | 50000 | 2017-01-31 | 1826610 | 2017-09-22 | 3053000 | AMBER | AMBER | GREEN | GREEN | GREEN | Project is behind schedule. End to End Integration Testing Progressing. Planning deployment at 1st site | 2017-03-31
Q3-2016-17 | 6058F428-4889-46F0-9259-7E21AB31AF32 | Melbourne Health | Melb H | Enterprise Billing System | Health | Implementation of an Enterprise Billing System will enable Melbourne Health to achieve a centralised approach for managing patient billing services and improving revenue collection across all clinical areas. | 2016-03-01 | PRINCE2 |  | In progress - implementation | 2016-05-01 | 0 | 2018-08-01 | 4800000 | 2018-11-07 | 4854146 | GREEN | AMBER | GREEN | GREEN | GREEN | The Readiness Project had been completed (Mar 17). The PBRC project is tracking to project timelines. | 2017-03-31
Q3-2016-17 | 74DC68C6-3BD8-4A79-A727-5A8596045DF5 | Melbourne Health | Melb H | Enterprise Content Management System (digitisation of clinical record content) | Health | Implementation of an Enterprise Content Management System to achieve digitised medical record content and automated workflows for Specialist Clinic Referrals Management, Coding and Release of Information | 2015-06-01 | Other – please specify | Overarching Prince 2 approach with Agile management of agency configuration and build. | Completed | 2015-06-01 | 143000 | 2016-10-07 | 5226000 | 2016-10-07 | 4538653 | GREEN | GREEN | GREEN | GREEN | GREEN | Project completed 7th October 2016. | 2017-03-31
Q3-2016-17 | 8C8C55FB-D493-4997-8831-CBEDC7D121BE | Melbourne Health | Melb H | CAFM Project - Computer Aided Facilities Management | Health | Implementation of an electronic Computer Aided Facilities Management system that will provide functionality for: Help desk; Task triage; Resource allocation; Job Management; Maintenance & Scheduled Management; Contract Management; Asset & Life Cycle Management; Property and Estate Management; Facility Condition Assessment and Maintenance management. | 2015-11-01 | Other – please specify | DMAIC (Six Sigma) for Stage Gate Processes & PRINCE2 for IT deployment | In progress - pre-implementation | [11 empty] | High level implementation planning study (IPS) commenced. Expected completion June 2017 including 6 IPS deliverables. | 2017-03-31
Q3-2016-17 | 14E85FD1-D05A-4C00-8232-2A9F6A3BF20D | Melbourne Health | Melb H | Human Resource Information System (HRIS) | Health | Implementation of a Human Resource Information System that contains the following modules; Employee HR data portal, Recruitment, Onboarding, Learning, performance and Goals, Succession and Career planning. | 2015-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Implementation planning has identified a phased approach with approval to commence implementation of first module in July 2017, which will be the Learning Management System module. | 2017-03-31
Q3-2016-17 | E524823C-5D64-48B7-98FE-00D4DB28D485 | Melbourne Polytechnic | MelbPoly | Customer Relationship Management Platform and Telephony Upgrade | Education | Implementation of Customer Relationship Management system to increase student enrolment numbers | 2016-04-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project does not yet have any budget allocated. Request for Tender responses received and evaluated against pre-defined criteria. Final recommendations about to be made. | 2017-03-31
Q3-2016-17 | E92EACA0-0742-4723-AA6A-B2B8F6E7AD18 | Melbourne Polytechnic | MelbPoly | Centre for Applied Innovation | Education | ICT resources to support the establishment of the Centre for Applied Innovation | 2016-08-29 | Other – please specify | Outsourced to Computer Sciences Corporation | Completed | 2016-10-24 | 20000 | 2016-12-01 | 2670000 |  |  | GREEN | GREEN | GREEN | N/A | N/A | Implemented successfully and now in operation | 2017-03-31
Q3-2016-17 | BA0C9E3B-264F-4B4C-BDCB-064F6EBD1A58 | Melbourne Polytechnic | MelbPoly | Network Modernisation (WAN) | Education | Development of a high speed wide area network for interconnecting Melbourne Polytechnic campuses | 2017-03-01 | Other – please specify | PM methodology not yet warranted | Initiated | [11 empty] | Undertaking a very early feasibility of the market. | 2017-03-31
Q3-2016-17 | DFE833EE-2DB7-4DCC-A07F-DEC882F6C0CC | Melbourne Water | MW | Q04323 - Developer Funded Works System | Environment and water | The Developer Funded Works System replacement project will migrate an existing system and separate database to an enterprise capability for asset management that is consistent with the Melbourne Water asset information and asset management processes. | 2013-09-02 | PRINCE2 |  | In progress - implementation | 2016-01-25 | 0 | 2016-09-30 | 3455000 | 2017-07-30 | 3424549.57 | AMBER | AMBER | AMBER | AMBER | GREEN | Melbourne Water is delivering the required business functionality in 2 Phases. Phase 1 was delivered in December. Phase 2 is in progress with build activities commenced on 10 April. Construction phase to be completed by end of June. Go-live planned for July. | 2017-03-31
Q3-2016-17 | C5B95B39-CB36-4FBE-B071-B2F89035A4BD | Melbourne Water | MW | Q04322 - Development Services System | Environment and water | System enhancement/replacement to improve our ability to manage and respond to statutory referrals, development enquiries and works applications. | 2013-09-02 | Agile |  | Completed | 2016-02-18 | 0 | 2016-12-30 | 4949000 | 2017-03-29 | 5350000 | GREEN | AMBER | AMBER | AMBER | GREEN | The system has been released to production and the project is now in the warranty support period and preparing for project closure. | 2017-03-31
Q3-2016-17 | 0C4D8B5D-8A4A-45FB-9ECC-B913D2E00211 | Melbourne Water | MW | Q04263 - Field Mobility (Enterprise Mobility Platform) | Environment and water | Selection and introduction of an enterprise mobility platform & asset management integrated mobility client for field works management. Provision of mobile access to the asset management system from inside and outside of the MW network, including offline access. | 2014-05-02 | PRINCE2 |  | Completed | 2015-12-23 | 0 | 2016-04-30 | 2578000 | 2016-07-14 | 2569818.11 | GREEN | GREEN | AMBER | AMBER | AMBER | Project now complete | 2017-03-31
Q3-2016-17 | 10E7B7E1-050B-4628-ADD5-193B3CA21926 | Melbourne Water | MW | Q04407 - Enhance Disaster Recovery IT Capability | Environment and water | Provide a fully-managed enterprise-wide Backup & Recovery Cloud Solution | 2014-06-01 | PRINCE2 |  | Completed | 2015-11-19 | 0 | 2016-03-31 | 1652000 | 2016-03-31 | 1325731.33 | GREEN | GREEN | AMBER | AMBER | GREEN | Project now complete | 2017-03-31
Q3-2016-17 | 4CEBC455-29CA-4398-AD50-638CCB707312 | Melbourne Water | MW | Q05292 - ETP PCS Virtualisation | Environment and water | Refresh Technology platform for SCADA at key location/s | 2015-05-14 | PRINCE2 |  | Completed | 2015-11-26 | 0 | 2016-05-31 | 1100000 | 2016-07-31 | 906536.68 | GREEN | GREEN | GREEN | GREEN | AMBER | Project now complete | 2017-03-31
Q3-2016-17 | 24B917D1-8FB2-4B5A-A612-39ECFA53990B | Melbourne Water | MW | Q05543 - LIQUID | Environment and water | Replace the legacy databases with a single data repository that will also support ad-hoc sampling. | 2016-02-25 | PRINCE2 |  | Completed | 2016-06-30 | 0 | 2017-01-27 | 1209000 | 2017-03-01 | 1006695.34 | GREEN | GREEN | AMBER | GREEN | GREEN | Project now complete | 2017-03-31
Q3-2016-17 | 7B151389-ECAD-45C5-9308-825BBD79F563 | Melbourne Water | MW | Q05496 - CRM R1_4 Build Release | Environment and water | CRM Enterprise phase will release new mature iterations for improved benefits and KPI's. This phase will also offer enhanced enterprise support for ALL 9 customer segments | 2015-07-31 | Agile |  | Completed | 2016-08-01 | 0 | 2016-10-30 | 1404000 | 2016-08-22 | 1317211.92 | GREEN | GREEN | GREEN | AMBER | GREEN | Project now complete | 2017-03-31
Q3-2016-17 | 066CD218-AB3F-4856-9CD9-66B6F82668CE | Melbourne Water | MW | Q03317 - Enhanced Headworks Model Development | Environment and water | This project will provide the ability to consider the total water cycle in developing water supply strategies, enabling a method of delivering water supply, waterways and sewage services holistically. | 2015-08-03 | PRINCE2 |  | In progress - implementation | 2016-08-26 | 0 | 2017-09-30 | 1204000 | 2017-09-29 | 1136987.3 | GREEN | GREEN | GREEN | GREEN | GREEN | Implementation in progress. Tracking to schedule & budget | 2017-03-31
Q3-2016-17 | 6B13CDE9-97ED-49DC-B160-426D7C8E3304 | Melbourne Water | MW | Q04319 - Risk Management System | Environment and water | To implement an enterprise risk management system that provides a consolidated repository for management of corporate and specialist risks throughout Melbourne Water. | 2013-12-09 | Agile |  | Completed | 2015-02-19 | 0 | 2015-09-15 | 1110000 | 2015-07-10 | 1019154.13 | GREEN | GREEN | GREEN | GREEN | GREEN | Project now complete | 2017-03-31
Q3-2016-17 | C1E9CABE-2E6C-42D7-8A83-CF7D9FDB528D | Melbourne Water | MW | Q05557 - Active Directory Enhancement | Environment and water | Uplift Directory services for IT and OT systems. | 2016-04-01 | PRINCE2 |  | In progress - implementation | 2016-11-25 | 0 | 2017-06-30 | 1270000 | 2017-06-30 | 895770.14 | GREEN | GREEN | AMBER | GREEN | N/A | Implementation in progress. Tracking to Schedule | 2017-03-31
Q3-2016-17 | 9EAE07D6-3E38-4D3F-9FBA-E803C3CD1ED0 | Melbourne Water | MW | Q04359 - CWAN Enhancement | Environment and water | Uplift network security to protect against threats entering and spreading within the Melbourne Water network. | 2014-06-16 | PRINCE2 |  | In progress - implementation | 2016-11-25 | 0 | 2017-06-30 | 3150000 | 2017-06-30 | 2322466.04 | GREEN | GREEN | AMBER | GREEN | GREEN | Implementation in progress. Tracking to Schedule | 2017-03-31
Q3-2016-17 | C7747F4A-0B2D-4496-934C-7D4064BFFBEF | Melbourne Water | MW | Q04365 - SCADA DMZ | Environment and water | Uplift security by improving segregation to ensure SCADA/PCS infrastructure is isolated & protected via security zones. | 2015-07-03 | PRINCE2 |  | In progress - implementation | 2016-11-25 | 0 | 2017-06-30 | 1310000 | 2017-06-30 | 945095.21 | GREEN | GREEN | AMBER | GREEN | AMBER | Implementation in progress. Tracking to Schedule | 2017-03-31
Q3-2016-17 | E8687351-B277-4073-8740-BC7E54CD79A4 | Melbourne Water | MW | Q05130 - Site Security Upgrades | Environment and water | Upgrade security at critical sites to meet the Australian Government Security Vulnerability Risk Assessment Guidelines | 2015-07-01 | PRINCE2 |  | In progress - implementation | 2016-10-21 | 0 | 2017-08-30 | 1971000 | 2017-08-30 | 1793624.61 | GREEN | GREEN | GREEN | GREEN | GREEN | Implementation in progress. Tracking to Schedule | 2017-03-31
Q3-2016-17 | 5F441075-B09B-45D6-8197-2F7092CC7C29 | Melbourne Water | MW | Q05487 - Integrated Assurance and Compliance Management | Environment and water | An integrated solution to address MW's need to centrally manage, track and report compliance and regulatory obligations end to end | 2015-08-11 | PRINCE2 |  | In progress - implementation | 2017-02-05 | 0 | 2017-09-07 | 1424000 | 2017-09-07 | 1323633 | GREEN | GREEN | GREEN | GREEN | GREEN | Implementation in progress. Tracking to Schedule | 2017-03-31
Q3-2016-17 | 3617E3A8-101E-4080-80A3-2A2F15BD51FA | Melbourne Water | MW | Q05564 - SAN Storage Renewal | Environment and water | Renewal of the SAN storage infrastructure used to store electronic files and documents, as well as copies of server configurations and data. The current SAN is expensive to support and is due for replacement. | 2016-02-02 | PRINCE2 |  | In progress - implementation | 2017-02-27 | 0 | 2017-07-31 | 1900000 | 2017-01-31 | 1749209.94 | GREEN | GREEN | GREEN | GREEN | GREEN | Final phase of migration of data from the old SAN to the new. | 2017-03-31
Q3-2016-17 | CDA562B6-6B54-479A-BB77-DC207EBE2CE5 | Metropolitan Fire and Emergency Services Board | MFESB | Purchase of Electronic Document and Records Management System (EDRMS) | Emergencies and safety | Procurement and implementation of a new electronic records management system to replace eDocs (DocCentral). | 2013-07-01 | Other – please specify | MFB Project Management Framework (PME) | In progress - implementation | 2014-07-09 | 60737 | 2017-06-30 | 1200000 |  | 1558668 | AMBER | GREEN | GREEN | GREEN | N/A | Implementation in progress, with the required consultation ongoing. Completion still expected by 30 June 2017. | 2017-03-31
Q3-2016-17 | 1A41DD56-D037-41FD-B5B2-A7586EB48131 | Metropolitan Fire and Emergency Services Board | MFESB | Replace Legacy Dell Servers | Emergencies and safety | Replacing legacy server hardware. | 2014-07-01 | Other – please specify | MFB Project Management Framework (PME) | In progress - implementation | 2014-10-01 | 0 | 2018-06-30 | 2180000 |  |  | GREEN | GREEN | GREEN | GREEN | N/A | Implementation in progress. Services contract finalised | 2017-03-31
Q3-2016-17 | 1D1BEC37-2120-4036-8F3B-DBAA2742577A | Metropolitan Fire and Emergency Services Board | MFESB | Legacy SAN Storage Refresh | Emergencies and safety | Replacing legacy and upgrading network storage. | 2015-07-01 | Other – please specify | MFB Project Management Framework (PME) | In progress - implementation | 2015-10-01 | 0 | 2017-06-30 | 1500000 | 2017-12-05 | 1230000 | AMBER | GREEN | GREEN | GREEN | N/A | Storage Strategy completed. Implementation timelines are longer than expected, the implementation end date has been revised to reflect this. | 2017-03-31
Q3-2016-17 | 457BDED1-EAE5-45FC-9819-1E1E30095198 | Metropolitan Fire and Emergency Services Board | MFESB | Mobile Data for Vehicles Pilot | Emergencies and safety | Pilot project of mobile data devices installed in fire appliances to receive and display relevant event information. | 2015-07-01 | Other – please specify | MFB Project Management Framework (PME) | In progress - implementation | 2016-02-04 | 0 | 2017-06-30 | 1750000 |  |  | GREEN | GREEN | GREEN | GREEN | N/A | System Testing due to commence. Training arrangements being finalised. | 2017-03-31
Q3-2016-17 | 12FDE857-12A0-4996-91A4-26F7AB4AE5A2 | Metropolitan Fire and Emergency Services Board | MFESB | End User Device Refresh | Emergencies and safety | Replacement of end user computing devices and consolidation of devices where possible. | 2015-07-01 | Other – please specify | MFB Project Management Framework (PME) | In progress - implementation | 2015-10-01 | 0 | 2018-06-30 | 1343000 |  |  | GREEN | GREEN | GREEN | GREEN | N/A | Progressive delivery, installation and retirement of devices. | 2017-03-31
Q3-2016-17 | DFC0F938-9AD5-48E6-9206-C11D6E1C303F | Metropolitan Fire and Emergency Services Board | MFESB | Enterprise Resource Planning solution | Emergencies and safety | Replacement of existing SAP (financial management system) system that has reached end of life. (incl SES) | 2015-07-01 | Other – please specify | MFB Project Management Framework (PME) | In progress - pre-implementation | [11 empty] | Awaiting final approvals on establishment of preferred tenderer. | 2017-03-31
Q3-2016-17 | 20D91422-040A-4858-986F-18B73FFB974F | Monash Health | Monash H | Monash Children's Hospital Patient Entertainment System | Health | Implementation of a Patient Entertainment System (PES) for the new Monash Children's Hospital which provides access to services such as the internet, meals ordering , education services, and movie and television channels. | 2015-05-11 | PRINCE2 |  | Completed | 2016-06-01 | 0 | 2017-03-01 | 1649000 |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | Project is completed | 2017-03-31
Q3-2016-17 | 210E4505-9127-40F2-A7E0-9FE7DECB4B21 | Monash Health | Monash H | Medical Grade Network | Health | Implementation of an enterprise wide wired and wireless data network to support the implementation of an Electronic Medical Record (EMR) system. | 2015-10-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project planning is in progress. Scheduled to be implemented within plan. | 2017-03-31
Q3-2016-17 | B299B052-58F6-4D7C-9825-07F649025FAB | Monash Health | Monash H | Healthcare Billing System Phase 1 | Health | Implementation of an enterprise billing system for selected services across Monash Health. | 2015-11-16 | PRINCE2 |  | In progress - implementation | 2016-04-01 | 202050 | 2017-02-01 | 1900000 | 2017-10-01 |  | AMBER | AMBER | GREEN | GREEN | GREEN | Project Planning is progressing as expected | 2017-03-31
Q3-2016-17 | C943D2F6-1C32-49D0-8762-EC1C6FF81A1D | Monash Health | Monash H | Electronic Medical Record | Health | Implementation of an Electronic Medical Record (EMR) system, including clinical documentation, results viewing, and medications management | 2016-01-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Contract signed with preferred Vendor. Project implementation to start shortly | 2017-03-31
Q3-2016-17 | C27D0976-27AF-4844-AC85-13AF88B324C9 | Northern Health | NHS | EMR Project-EMR Readiness phase | Health | Implementation of an Electronic Medical Record at Northern Health including all sites | 2016-10-18 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Business case costings are being reviewed and the business case will be updated for submission to the Department in September 2017. EMR Project Manager appointed. EMR demonstrations are planned for May 2017. Split IPS will commence in June. Infrastructure review is underway | 2017-03-31
Q3-2016-17 | 9F62B569-9844-4406-AA03-35C542783FCC | Parks Victoria | PARKSVIC | Customer Relationship Management solution (Pilot and Phase 1) | Environment and water | Implementation of a Customer Relationship Management solution to manage stakeholder data and migration of organisational areas and systems to the new platform. | 2015-07-01 | Agile |  | In progress - implementation | 2016-04-30 | 245033 | 2017-06-30 | 4716000 |  |  | GREEN | GREEN | GREEN | GREEN | AMBER | Stakeholder Relations was delivered as the Pilot in July 2016 and continues to be rolled out across the organisation. Phase 1 started in August and delivers four functional areas: Visitor Information Centre (VIC), Scientific Research Permits (SRP), Volunteer Management (VM) and Commercial Agreements (CA). The VIC was delivered in November 2016 and pilot feedback was sort for VM and SRP in February 2017. Feedback has been reviewed and is being incorporated with implementation scheduled for May 2017. Implementation planning for CA is also underway with the expectation that Licensed Tour Operators will be the first group to also go live in May 2017, prior to tenants being introduced in July 2017. | 2017-03-31
Q3-2016-17 | 01BC8633-E3AF-4C05-8132-0996098C87AE | Parks Victoria | PARKSVIC | Infrastructure Roadmap | Environment and water | Technology Infrastructure replacement and modernisation program updating core IT infrastructure and associated services, network infrastructure, and end user devices. | 2016-10-21 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | The program business case is being finalised for presentation to the program board and relevant governance bodies. Future state requirements have been gathered and are being compiled in to ‘go to market’ documents. | 2017-03-31
Q3-2016-17 | 88EB2212-AC0C-4001-9396-3CFC81EA4523 | Peninsula Health | PenHealth | Rostering Time & Attendance | Health | Enterprise electronic Rostering system | 2015-05-01 | Other – please specify | Adaption of Prince II in conjunction with Vendors PM Planning | In progress - implementation | 2015-12-31 | 566654 | 2017-10-15 | 1847451 | 2018-03-03 |  | AMBER | GREEN | GREEN | AMBER | AMBER | Project is late. Vendor delivery of software is late and inaccurate. Significant engagement with vendor is underway to resolve outstanding matters | 2017-03-31
Q3-2016-17 | 370BB806-42C5-4180-AAE9-9AD29FDB68F5 | Peninsula Health | PenHealth | Electronic Health Record - Clinical Documentation | Health | Clinical Documentation | 2016-10-01 | Other – please specify | Adaption of Prince II in conjunction with Vendors PM Planning | In progress - implementation | 2016-11-15 | 200000 | 2018-03-28 | 2500000 |  |  | GREEN | GREEN | N/A | N/A |  | Project progressing as planned. | 2017-03-31
Q3-2016-17 | 3F54D2D0-B807-4457-82D2-D5E816F05F1C | Peter MacCallum Cancer Centre | Peter Mac | Picture Archive and Communication System | Health | Implementation of a Radiology Picture Archive and Communication System (PACS) / Vendor Neutral Archive (VNA). | 2014-02-01 | PRINCE2 | Adapted to relevant scope of the project | Completed | 2015-05-20 | 77840 | 2016-07-18 | 1954070 | 2016-07-01 |  | GREEN | GREEN | GREEN | GREEN | GREEN | Project completed. | 2017-03-31
Q3-2016-17 | 1EFA6AD2-088C-4DC4-A098-741D63C68E65 | Peter MacCallum Cancer Centre | Peter Mac | Laboratory Information System | Health | Implementation of a common Laboratory Information System as an externally hosted fully managed service in collaboration with two other state public health services. | 2014-07-21 | Other – please specify | Overarching PRINCE2 approach with AGILE management of agency configuration and build | In progress - implementation | 2015-06-04 | 132268 | 2017-01-31 | 1669586 | 2017-09-22 | 1998392 | AMBER | AMBER | GREEN | GREEN | GREEN | Project Executive Governance Committee authorised a 2 Stage approach with PMC stage 1 to Go live end of June. Stage 2 timeline to be confirmed. | 2017-03-31
Q3-2016-17 | 64BF4A07-D43B-4E7C-A725-D5DB05182A4F | Peter MacCallum Cancer Centre | Peter Mac | Relocation Project | Health | As part of the broader redevelopment program, the objectives of the Building ICT Program are to accept ICT systems and products, transition existing systems from Peter Mac to Parkville, ensure that users are familiar with the new technology, ensure that Peter Mac ICT can support the products in the future | 2014-09-18 | PRINCE2 | Adapted to relevant scope of the project | Completed | 2015-10-31 | 219969 | 2016-07-29 | 941098 | 2016-09-30 | 4003194 | GREEN | GREEN | GREEN | GREEN | AMBER | Project completed. | 2017-03-31
Q3-2016-17 | FBD35B2A-E0EE-47EB-A1F9-8076BF0A201C | Peter MacCallum Cancer Centre | Peter Mac | Precinct UR Number | Health | Unique Precinct UR number is required to support patient movement across the Precinct Hospitals at Parkville. | 2015-02-13 | PRINCE2 | Adapted to relevant scope of the project | In progress - implementation | 2015-10-30 | 176826 | 2016-11-18 | 3024816 | 2017-06-30 |  | GREEN | GREEN | AMBER | GREEN | AMBER | Phase 1 and 2 implemented in production. Phase 3 progressing and finished packages progressively deployed into production. End date includes post go live support. | 2017-03-31
Q3-2016-17 | 10814502-29DB-4E6F-A701-E5578656528B | Peter MacCallum Cancer Centre | Peter Mac | Clinical Viewer | Health | Access to clinical information across the Precinct Hospitals at Parkville is required for the new Clinical Service Operating Model. | 2015-08-24 | PRINCE2 | Adapted to relevant scope of the project | Completed | 2015-12-18 | 91453 | 2016-10-17 | 1106838 |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | Project completed. | 2017-03-31
Q3-2016-17 | 7354C7E5-427F-4E70-BCCE-452A704D91FA | Peter MacCallum Cancer Centre | Peter Mac | Radiotherapy Treatment Planning System | Health | Implementation of a new centralised Treatment Planning System at Peter Mac’s main Parkville site and satellite campuses | 2016-12-07 | PRINCE2 | Adapted to relevant scope of the project | In progress - pre-implementation | [11 empty] | Procurement activities underway for a solution provider of Treatment Planning System. | 2017-03-31
Q3-2016-17 | F7F16506-281A-41DD-811F-0BAD6887C081 | Places Victoria | Places Victoria | PIMS | Property and planning | System that allows for the management of construction projects within a single system | 2014-10-01 | PRINCE2 | Agile | In progress - implementation | 2015-10-15 | 60000 | 2016-10-24 | 2500000 | 2017-06-23 | 2500000 | GREEN | GREEN | GREEN | GREEN | GREEN | PIMS has successfully delivered the key components of the project. A number of value add enhancements have been identified and being assessed for delivery. | 2017-03-31
Q3-2016-17 | 212D5A15-2DCB-42A5-BFFB-6038A079B5F0 | Public Record Office Victoria | PROV | Digital Archive Program | Government and economy | This program is progressively renewing and replacing Public Record Office Victoria's digital archive infrastructure. The program is expected to enable better access to PROV records while facilitating long term preservation and reducing operating costs. | 2015-07-01 | PRINCE2 |  | In progress - implementation | 2015-07-01 | 200000 | 2018-06-30 | 4062000 |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | The technical specifications for key systems are now completed. Expressions of Interest are being prepared for two systems prior to RFQ. | 2017-03-31
Q3-2016-17 | BF7990AA-E1D3-4AF4-862C-4960C8A9949B | Public Transport Victoria | PTV | Train SCADA (Electrol) Replacement | Transport and vehicles | Replacement of Electrol Train SCADA system - Telemetry Communication Network, and establish a disaster recovery centre and implementation of a new control monitoring system (CMS) for the Melb Underground Rail Loop (MURL). | 2009-02-06 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2010-06-04 | 500000 | 2016-07-30 | 30550000 | 2017-06-30 |  | AMBER | RED | AMBER | AMBER | AMBER | Project is currently within budget. This project is now actively in the final stages of delivery. The original scope to replace the SCADA system was delivered and has been in operation since April 2013. The project is delivering an enhanced scope (using savings realised during the project) that has been delayed. Of the 4 new scope items, 2 have been completed with the final two items forecast for completion by June 2017. The final two items are the Disaster Recovery Centre (DRC) work at Metro and the Electrol SCADA system (ESS) interface. | 2017-03-31
Q3-2016-17 | 3097600A-919A-482B-89D7-DA90882BF77F | Public Transport Victoria | PTV | Regional Radio Communications Network | Transport and vehicles | The project involves modernisation of the following legacy systems; the train control centre (Centrol) Voice Communications Systems (VCS); the In-cab Communications Equipment (ICE) in the V/Line fleet; and the voice communications network service. | 2012-03-01 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2014-02-27 | 7250000 | 2018-04-03 | 65300000 | 2018-08-30 |  | AMBER | AMBER | AMBER | AMBER | AMBER | A total of $65.3 million of funding was provided for the project, a recent Section 30 transferred $10.5m of OPEX to CAPEX resulting in a total budget split of $54.352 of CAPEX and $10.948 of OPEX. Project is progressing and is currently within budget. Project is on schedule to deliver within the Business Case timeframes (by June 2019) however there are risks that delays might be caused by; access to rolling stock to undertake equipment installation work; resolution of Digital Train Radio System (DTRS) interworking issues; availability of drivers for training; and some additional works currently being processed through the change management framework that may be required to complete the project. PTV and VicTrack are actively pursuing mitigation measures to contain potential budget issues associated with the above risks. | 2017-03-31
Q3-2016-17 | 0041F85B-F19A-4D4F-9D12-81F36DEF9C2D | Public Transport Victoria | PTV | Operator Payment System Modernisation | Transport and vehicles | Replace the PASS suite of programs (PASS Payments and Bus IT), myriad of spread sheets and manual processes related to operator contract and performance management and operator payments. Decommission of PASS Payments and Bus IT. | 2014-05-14 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2015-07-16 | 765000 | 2016-03-30 | 10000000 | 2017-05-31 | 12658100 | GREEN | AMBER | AMBER | AMBER | AMBER | Project delivery is underway but was delayed during the contract execution period. The project has been re-baselined and minor slippage is being managed. The revised implementation budget of $12,658,100 for all 4 releases (phases) has been approved. Go Live of Release 1 will occur in May 2017. Per the initial plan, the project has commenced work on future releases. A contract has been signed for Releases 2, 3 and 4 and the project has returned to a GREEN status. | 2017-03-31
Q3-2016-17 | F1A28FC4-80F0-4117-A15F-0E55BB1A4165 | Public Transport Victoria | PTV | Special Event Management System | Transport and vehicles | The project will deliver a web-based cloud-based application designed to interface with data sources including bus, tram and train stops/routes, bus/tram/train timetables via Chronos (middleware), planned occupations from Operators, Base Maps, GIS spatial data from PTV libraries, patronage data from Marketing Access database, Road occupations from VicRoads. | 2014-08-05 | Other – please specify | PTV Investment Lifecycle | Completed | 2015-05-18 | 104000 | 2016-09-23 | 1810000 | 2017-02-06 | 1763693 | GREEN | AMBER | AMBER | GREEN | GREEN | SEMS went live on 21 Dec 2016 as the first roll-out of a 3 phased approach. The final roll-out activity occurred on 6 February 2017. The project is now closed | 2017-03-31
Q3-2016-17 | 8E2C3A60-3C22-448D-B455-248EF1F86DCC | Public Transport Victoria | PTV | Timer Solution on Tram Fleet | Transport and vehicles | To purchase and install a pilot timer solution across the entire tram fleet (one per class) and to incorporate the use of timers in future tram installations. | 2014-08-27 | Other – please specify | PTV Investment Lifecycle | Terminated | 2015-12-18 | 91453 | 2016-10-17 | 1106838 | 2016-12-09 | 3303 | [5 empty] | Project did not progress past value for money assessment and is to be formally closed out. | 2017-03-31
Q3-2016-17 | EEC2C527-849A-4B53-80BD-9D2AC3CDE6F0 | Public Transport Victoria | PTV | Delivering Real Time Train Information - Phase 1 | Transport and vehicles | Deliver real time Metro train information to customers via PTV and operator mobile apps, PIDs and via open access to data. | 2014-11-18 | Other – please specify | PTV Investment Lifecycle | Completed | 2015-11-13 | 0 | 2016-09-19 | 2000000 | 2016-10-20 | 1592908 | GREEN | GREEN | GREEN | GREEN | GREEN | Go live completed on 20/10/16 with Minister and PTV CEO media announcement event. | 2017-03-31
Q3-2016-17 | 900DD93B-437F-4BD7-BD3B-568C6ADB6E77 | Public Transport Victoria | PTV | Data Analytic Platform | Transport and vehicles | Provide PTV wide data access to enable the business to analyse, visualise, share and report data insights. | 2014-11-19 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2015-05-31 | 100000 | 2016-10-04 | 4780000 | 2017-06-30 |  | AMBER | RED | AMBER | GREEN | AMBER | The original implementation date for DAP was October 2016, however this is now expected by the end of June 2017. The project identified a number of data quality issues and remaining works are being delivered by a team of internal resources within the PTV CIO to ensure that delivery timeframes and quality are achieved. | 2017-03-31
Q3-2016-17 | F9B591DD-3771-4B49-AFD0-BBFDCD2D60C9 | Public Transport Victoria | PTV | Vehicle Passenger Information System (VPIS) A & C Class | Transport and vehicles | Procure and implement a system using commercial-off-the-shelf (COTS) products to provide reliable and dynamic on-tram passenger information. | 2015-05-01 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2016-02-29 | 0 | 2017-05-30 | 8732000 | 2018-04-12 | 10160000 | GREEN | GREEN | AMBER | AMBER | GREEN | Project delivering on schedule and budget against the revised scope and timelines. A-Class trials are complete. C1-Class trials are on track to commence in Q4 2016/17. | 2017-03-31
Q3-2016-17 | FF2B5DFD-2557-4525-B2E6-3C5DF315690E | Public Transport Victoria | PTV | Time Table on Demand | Transport and vehicles | Establish authoritative information repository for each identified data set. This repository will form the single source of truth for PTV timetabling needs. Uplift to outdated technology (DIVA and EFA), introduction of new technologies to enable standardised information exchange with Operators. | 2015-06-19 | Other – please specify | PTV Investment Lifecycle | Terminated | 2015-12-09 | 150000 | 2016-06-29 | 4195000 | 2017-06-30 | 9860085 |  | RED | RED | AMBER | GREEN | This project has been terminated. | 2017-03-31
Q3-2016-17 | B04B01FB-75C3-4DC5-BDA3-26728F5808EC | Public Transport Victoria | PTV | Bus Information Improvement Project | Transport and vehicles | Develop common reference data model for Bus Information, improve stop data quality and completeness, empower operators to self-manage bus data and develop and establish a framework for bus performance monitoring. | 2015-07-19 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2015-12-18 | 20000 | 2016-07-29 | 1412000 | 2017-07-31 |  | AMBER | AMBER | AMBER | AMBER | GREEN | The overall schedule has been impacted due to extra work required on the scheduling and timetabling systems to handle the impacts of Timetable on Demand project being terminated and delays due to the revised external connectivity solution requiring an additional server to be set up, configured and tested. The expected implementation of system changes will be completed by end-April 2017. However the external connectivity solution implementation is forecast to be completed by early June 2017, due to additional delays in confirming Oracle and Windows licensing implications and costs. The project close-out is now tracking to an end of July 2017 completion. | 2017-03-31
Q3-2016-17 | 209855D5-316B-4FC8-98C9-0EB3DBF9D212 | Public Transport Victoria | PTV | Rail Industry Only (RIO) - Mobile and Handheld Radio Replacement | Transport and vehicles | Replace 500 existing mobile and handheld radios with new devices and update the supporting infrastructure to address the ACMA regulatory requirements to operate within the Harmonised Rail Industry Only (RIO) spectrum. | 2016-05-20 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2016-06-24 | 0 | 2016-12-07 | 1950000 | 2017-08-31 |  | AMBER | RED | RED | GREEN |  | VicTrack have confirmed in writing that Yarra Trams (YT) will not need to move to the Rail Industry Only (RIO) spectrum until 2023. An extension has been granted by the Australian Communications Monitoring Authority for YT to continue to operate in the commercial band and avoid fines for doing so. YT received notification that there 25 commercial band licences have been updated for a further 12 months. PTV have requested an option paper be prepared by YT to understand the operational needs to continue with the project. The options paper will be assessed and a decision made in Q4. | 2017-03-31
Q3-2016-17 | C8BCC4C4-6590-4258-A4CA-93E6577ED584 | Public Transport Victoria | PTV | Train Control Monitoring System (TCMS) for South Morang and Hurstbridge | Transport and vehicles | To deliver a modern Train Control Monitoring System 'instance' at Epping to replace the standalone WESTCAD and SIGVIEW workstations and to support more efficient train control operations on the South Morang and Hurstbridge lines. | 2016-10-21 | Other – please specify | PTV Investment Lifecycle | In progress - pre-implementation | [11 empty] | Project Brief has been approved by PTV and external stakeholders. A funding memo has been submitted to the Melbourne Metro Rail Authority requesting funding for the delivery stage of the project. | 2017-03-31
Q3-2016-17 | 00C1F30A-A205-4DF6-9EA1-FB421B3550F2 | Public Transport Victoria | PTV | PTV Intranet Update | Transport and vehicles | Redesign and review/develop/migrate content from PTV's existing intranet to a new cloud-hosted solution in order to enhance capability for collaboration, information and knowledge management. | 2016-10-21 | Other – please specify | PTV Investment Lifecycle | In progress - pre-implementation | [11 empty] | Project is in the development phase. User research activities are underway and the functional and non-functional requirements are well progressed. | 2017-03-31
Q3-2016-17 | 90506C0B-9234-4580-91BA-0F3FAD7CD487 | Public Transport Victoria | PTV | Digital Train Radio System (DTRS) upgrades - Gateway GPRS Support Node (GGSN) and Lawful Interception Management System (LIMS) | Transport and vehicles | Upgrade, installation and commissioning of GGSN and LIMS at both the primary and back-up data centres. | 2016-06-24 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2016-08-08 | 0 | 2017-03-03 | 3164223 | 2017-05-11 |  | AMBER | AMBER | GREEN | N/A |  | Project has passed the Provisional System Acceptance milestone with full System Manageability Acceptance (practical completion) scheduled for 11 May 2017. End dates have been pushed out as two defects were discovered during testing that needed to be rectified before System Acceptance. | 2017-03-31
Q3-2016-17 | 7B9CF170-B52D-43E0-B11C-7D8F80BD0E42 | Public Transport Victoria | PTV | myki and PTV Website Integration and Development | Transport and vehicles | The project will include a complete website redesign focused on user experience, integration of the myki portal and the PTV website, a fully scalable website that renders to mobile devices, accessibility to WCAG 2.0 standards and integration with the PTV knowledge management system. | 2015-12-16 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2016-10-21 | 200499 | 2017-11-08 | 3634100 |  |  | GREEN | GREEN |  |  |  | Project is progressing to schedule and budget. Contracts were signed with suppliers in March 2017 and works have commenced. | 2017-03-31
Q3-2016-17 | E615B7EF-C947-4281-B93A-8CD0F7721EFD | Public Transport Victoria | PTV | Digital Train Radio System (DTRS) Obsolescence Upgrades Program | Transport and vehicles | Upgrade of DTRS sub-systems as they reach their end-of-life. | 2016-11-29 | Other – please specify | PTV Investment Lifecycle | In progress - pre-implementation | [11 empty] | The Project Brief and funding was approved in Q3. PTV has started to receive System Development Work Orders from vendors. Initial works have commenced on two of the seven work packages. | 2017-03-31
Q3-2016-17 | 69E81A8D-D604-414B-8EA9-38983ACAF241 | The Royal Children's Hospital | RCH | Electronic Medical Record Project | Health | Implement an integrated Electronic Medical Record to support the delivery of high quality, safe and sustainable healthcare. | 2012-07-01 | PRINCE2 |  | Completed | 2014-06-30 | 2306233 | 2016-12-31 | 45747763 | 2016-12-31 | 45747763 | GREEN | GREEN | GREEN | GREEN | GREEN | Project successfully completed on time and to budget | 2017-03-31
Q3-2016-17 | 75840376-FEDA-41EE-9597-249DE68B97F8 | The Royal Children's Hospital | RCH | Payroll & Rostering Project | Health | Delivery of high quality, real-time and contemporary payroll end to end solution; including electronic rostering to support automated integration of payroll services | 2015-11-01 | PRINCE2 |  | In progress - implementation | 2016-10-18 | 429523 | 2018-06-30 | 5412120 |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | Parallel testing underway | 2017-03-31
Q3-2016-17 | 9BCE9086-FEFA-4F65-8B3B-134D771F80E4 | The Royal Victorian Eye and Ear Hospital | Eye and Ear | ICT redevelopment Stage 3 Hardware Tender | Health | Fit-out of new IT infrastructure to support hospital redevelopment objectives | 2013-07-01 | PRINCE2 |  | In progress - implementation | 2014-06-30 | 0 | 2018-12-31 | 1180000 |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | Project progressing to schedule | 2017-03-31
Q3-2016-17 | C5C5EA10-5B30-4891-A4B4-DC13F806D5FA | The Royal Victorian Eye and Ear Hospital | Eye and Ear | Electronic Medical Record Project | Health | Implementation of further EMR modules to provide a clinical information system for the hospital. | 2016-08-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project progressing to schedule | 2017-03-31
Q3-2016-17 | 6E9A75AD-6936-4720-9CD3-278979DD766C | Royal Women' s Hospital | RWH | Clinical Viewer Replacement Project | Health | The existing clinical viewer, is being replaced at RWH. RWH objectives are to provide real-time, electronic, point of care imaging, pathology results and acknowledgement to facilitate efficient planning of patient care, enhance access to results for clinicians, minimize clinical risk and maximize clinician time. | 2015-09-22 | PRINCE2 |  | Terminated | 2015-10-14 | 76000 | 2016-07-05 | 1040422 |  | 292500 |  | N/A | N/A | AMBER | GREEN | The Clinical Viewer Replacement project has been terminated by RWH due to the replacement solution not being functionally fit for purpose. RWH intend to continue operating with the existing clinical viewer solution until an appropriate replacement is acquired. | 2017-03-31
Q3-2016-17 | 7D730679-870B-4E34-BF28-9830A0EA99E9 | South West Institue of Technical and Further Education | SW TAFE | SWTAFE Smart Classroom - TSAF Funded | Education | To install 15 'smart classrooms' across the Institute Campuses along with a telephony and wifi upgrade. | 2015-09-24 | Other – please specify | SWTAFE | Completed | 2016-03-07 | 510561 | 2016-12-30 | 1639863 | 2016-12-30 | 2470000 | GREEN | AMBER | GREEN | GREEN | GREEN | The classrooms were fully installed and commissed by Friday March 10. The project is now being closed out contractually and transitioned into ICT and teaching department operations. | 2017-03-31
Q3-2016-17 | F45605DD-5216-4E6D-A8D6-6F39094645B9 | South East Water | SEW | Trade Waste Information System | Environment and water | The project will deliver a new solution for South East Water to manage our Trade Waste business. This new solution replaces a VB6 application and will enhance customer service by enabling mobility and improved analytical reporting | 2014-09-15 | Agile |  | Postponed | 2015-01-05 | 0 | 2016-12-12 | 1879878 |  |  | AMBER | AMBER | AMBER | AMBER | AMBER | The review has been completed and we are now analysing results to determine the most appropriate path forward | 2017-03-31
Q3-2016-17 | B1B47682-7C50-49C0-97AD-8E17CD1D7DFF | State Revenue Office | SRO | LPR #2&3 - Land Ownership, NOAs and Land Usage Vicroads. | Government and economy | This project is part of the Better Revenue Management System program to redesign the Land Tax administration business processes to achieve operational efficiencies, improve effectiveness of managing land ownership data (using Notice of Acquisition (NOA Data and Vicroads Data) and to extend the life of SRO's revenue management system. | 2015-09-17 | PRINCE2 |  | In progress - implementation | 2016-09-30 | 1505896 | 2018-04-13 | 3881729 | 2018-04-13 | 4250885 | GREEN | GREEN | GREEN | GREEN | GREEN | The project has moved into the implementation phase and is progressing according to the approved project plan. We are working through detailed planning and costing of a voluntary scope increase and will advise the outcomes at the next reporting period. | 2017-03-31
Q3-2016-17 | 8A05D8AC-5DF3-45DA-BFFA-FAFC3C4356B7 | South West Alliance of Rural Health | SWARH | Barwon Health Data Warehouse Refresh | Health | Barwon Health is undertaking a project to rebuild their current data warehouse to enable us to move from reporting off individual transactional systems to a federated repository of all data required for reporting. | 2013-08-01 | PRINCE2 |  | In progress - implementation | 2016-06-01 | 0 | 2016-06-30 | 1760000 | 2017-11-30 |  | GREEN | GREEN | GREEN | AMBER | AMBER | Project on track to meet revised implementation date of 30 November 2017. Project remains on budget. | 2017-03-31
Q3-2016-17 | 1A1D78FE-A909-464F-81B7-27ECED47AC97 | South West Alliance of Rural Health | SWARH | SWARH Accelerated adoption of a Regional E.H.R | Health | The 13 SWARH agencies that utilize the SWARH EHR do not have dedicated change management agents to facilitate functionality uptake. The project aims to improve functionality to directly capture information in the Patient Administration System, eMedication Management, Clinical, Emergency, Theatre, appointment scheduling and community workflows. | 2015-07-01 | PRINCE2 |  | In progress - implementation | 2015-09-20 | 0 | 2017-09-21 | 3045000 |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | Project is progressing to schedule. | 2017-03-31
Q3-2016-17 | 6E0B5B53-9A3C-48C7-8EDA-E1CFEF7E14D1 | Transport Accident Commission | TAC | Claims Business Model | Transport and vehicles | The Claims Business Model program of work aims to deliver solutions that enables balance between claims management effort and liability management across the business, and through that, empowering clients , making it easier to work with the TAC, and improving the efficiency of the management of claims. | 2013-11-01 | PRINCE2 |  | In progress - implementation | 2014-06-30 | 704927 | 2018-06-30 | 39290751 |  | 55000000 | GREEN | AMBER | AMBER | AMBER | GREEN | Detailed planning for one of the major transformation initiatives was finalised in March 2017, returning the program to a status of GREEN. The increase in investment of $15 million was approved at the February 2017 Board meeting and remains within the existing approved financial boundaries of the TAC's Corporate Plan 2016-20. The program is on track to be completed in 2018. | 2017-03-31
Q3-2016-17 | EE466748-D9CB-4827-8D66-FA317634B247 | Transport Accident Commission | TAC | Integration Platform Refresh for TAC | Transport and vehicles | Joint project with WorkSafe to upgrade the Integration Platform to the latest version, which will also enable the consolidation (and decommission) of some of the older Integration Software products in use. | 2014-07-01 | PMBoK |  | Completed | 2015-08-31 | 620089 | 2016-06-30 | 313437.2 | 2016-07-31 | 558404 | GREEN | GREEN | GREEN | AMBER | AMBER | The Integration Platform Refresh project had been aligned with the WebSphere Application Platform Refresh project. These projects had significant interdependencies and required a joint schedule for migration. The Integration Platform Refresh Project completed at end of July 2016. | 2017-03-31
Q3-2016-17 | B90383E6-B6EA-4C94-9CE4-3EB46982E6A8 | Transport Accident Commission | TAC | Enterprise Database Rationalisation (Stream2) | Transport and vehicles | This project is to uplift and rationalise the database platforms across both the TAC and WorkSafe. This will deliver improved performance and capacity and allow us to decommission legacy database systems across TAC & WorkSafe. | 2014-12-01 | Other – please specify | Other - Internally Developed framework | Completed | 2016-01-31 | 899904 | 2016-06-30 | 929262 | 2016-07-31 | 928207 | GREEN | GREEN | GREEN | GREEN | GREEN | The project completed the TAC deliverables within the TAC approved budget at end July 2016. | 2017-03-31
Q3-2016-17 | 4475E5D8-2435-4D86-A034-91B3AA53ED3A | Treasury Corporation of Victoria | TCV | Treasury System Review | Government and economy | Review of front office treasury software | 2016-11-16 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Pre-implementation expenditure is anticipated to reduce the cost and risks associated with any subsequent implementation project. | 2017-03-31
Q3-2016-17 | D31393AB-7B6A-40ED-B864-1116ABFF5E25 | The Gordon Institute of Tafe | The Gordon | BlendED Learning - Technology Applications | Education | Creation of blended online learning resources for major courses offered by the Institute. Provision of supporting ICT infrastructure including an upgraded WiFi network at major campuses, improved access for BYODs, new lecture capture enabled classrooms; and providing additional computer resources to support a blended online learning model within the Institute. | 2014-12-01 | Other – please specify | Project Control group oversight. Reporting against Project Plan Phases and Deliverables. | In progress - implementation | 2014-12-01 | 0 | 2017-12-31 | 4658000 |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | Project proceeding according to schedule. | 2017-03-31
Q3-2016-17 | E6921E38-5284-4018-9163-A2C934330ECB | Victorian Auditor-General's Office | VAGO | ERP Solution Replacement | Government and economy | Replace aging Components of existing ERP solution and provide additional functionality. | 2016-09-02 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Business case development and business / functional requirements documentation | 2017-03-31
Q3-2016-17 | F4FFFA37-46AC-42C5-A70C-A4B83DBCE884 | Victorian Building Authority | VBA | Business Systems Transformation - Phase (1) | Government and economy | The BST program is intended to progressively re-engineer VBA regulatory processes and implement new integrated applications which will replace legacy systems and manual processes, to: mitigate technology risk, enhance risk based regulation, reduce regulatory burden, increase efficiency and reduced cost; and, improve consumer outcomes | 2014-10-01 | PRINCE2 |  | In progress - implementation | 2016-06-30 | 986248 | 2019-07-01 | 12375133 | 2019-07-01 | 12375133 | GREEN | GREEN | GREEN | GREEN |  | Initial business case was approved in April 2015. The revised business case (post market process) and proposed allocation of funding for stage (1) was tabled for VBA Board approval in mid-May. Vendor on boarding and commencement of delivery has commenced as at 1 July 2016 and the project is now in the build phase for Phase 1. The project has 3 phases and phase 1 is intended to be completed by June 2017. This project is on track for Phase 1 release prior to 30 June 2017 - UAT testing is about to commence. | 2017-03-31
Q3-2016-17 | 4F0C9D77-471C-4AC2-A4DD-66053BA0124C | Victorian Ombudsman | VO | ICT Relocation to new premises | Government and economy | Various ICT projects such as infrastructure, desktop hardware, audio/visual, telephony and CenITex services to support and enable the relocation of the Ombudsman's office to Level 2, 570 Bourke St | 2016-02-01 | Other – please specify | Various - from waterfall to agile | In progress - implementation | 2016-02-01 | 0 | 2017-03-30 | 2000000 | 2017-06-30 | 2000000 | AMBER | AMBER | GREEN | GREEN | AMBER | Original implementation timeline has not been met due to resourcing and other conflicting priority issues. As such the project timelines has been revised | 2017-03-31
Q3-2016-17 | 831734FC-8A3B-48C3-9421-FD2984BAE38F | Victoria Police | VicPol | Parole System Reform | Law and justice | Undertake system modifications to support the introduction of the Corrections Amendment (Breach of Parole) Act 2013 and the adoption Measure 11 of the Callinan "Review of the Parole System in Victoria" into Victoria Police. | 2013-07-01 | PRINCE2 |  | In progress - implementation | 2014-11-01 | 0 | 2016-03-31 | 2005700 | 2017-06-30 | 2000000 | AMBER | AMBER | AMBER | RED | GREEN | Overall Breach Of Parole is tracking against the revised schedule. Significant progress has been made in resolving previously reported defects within the Attendance & Custody Modules that support the Breach of Parole processing enhancements. The project has successfully completed the first cycle of joint UAT with Corrections Victoria. | 2017-03-31
Q3-2016-17 | 5CE0DDC4-65F9-4832-8A3E-258484DF6E2D | Victoria Police | VicPol | PIPP Transformation | Law and justice | To provide police with the ability to access the information they need securely, where and when they need it. This is about delivering benefits to the frontline, freeing up police from time consuming administrative tasks. | 2013-07-01 | PRINCE2 |  | In progress - implementation | 2015-06-30 | 0 | 2017-03-30 | 10919000 | 2018-11-01 | 4200000 | GREEN | GREEN | GREEN | GREEN | AMBER | Police Assistance Line/Online Reporting Business Case submitted. Work for the Case Management Business Case has commenced with Transform scheduled to close by 30 June 2017. | 2017-03-31
Q3-2016-17 | B9D633EA-D960-4138-80DC-279DD4950271 | Victoria Police | VicPol | PIPP Sustain | Law and justice | The PIPP Sustain project will address immediate issues to maintain the performance of LEAP and Interpose Victoria Police information systems to enable the commencement of planning for longer-term reforms to these systems and processes. | 2013-07-01 | Other – please specify | IT PMO Project Management Framework | In progress - implementation | 2013-06-30 | 0 | 2015-12-31 | 12301000 | 2017-06-30 | 12301000 | GREEN | GREEN | GREEN | GREEN | AMBER | Interpose 2.2 upgrade released to production in June 2016. A minor enhancement release is planned to complete this activity and is the cause of the revised implementation date. Delivery remains within budget. | 2017-03-31
Q3-2016-17 | 7B8DCA81-5A8F-4F5B-A85D-98B488D9572D | Victoria Police | VicPol | Timely Warrants | Law and justice | Deliver the technical system changes including the development of: 1.1 - Central Brief Storage System; 1.2 - Updates to LEAP Warrant Management to and from Courts Victoria; 1.3 - Changes to the EWOK system include printing of electronic warrants. | 2014-12-17 | PRINCE2 | DMAIC (Six Sigma) for Stage Gate Processes & PRINCE2 for IT deployment | Completed | 2015-07-30 | 0 | 2015-12-30 | 2167000 | 2016-08-31 | 2167000 | N/A | N/A | GREEN | GREEN | GREEN | Project Completed Central Brief Storage System (CBSS) successfully implemented and in Production. | 2017-03-31
Q3-2016-17 | CD1CD84B-7B9A-45AC-BF36-80217E2EF216 | Victoria Police | VicPol | BlueConnect - Mobile Technology | Law and justice | Handheld, mobile devices to put critical information into the hands of frontline police and allow them to feed it back into the organisation’s intelligence from the field. | 2015-11-01 | PRINCE2 |  | In progress - implementation | 2016-06-30 | 0 | 2021-06-30 | 73569000 |  |  | AMBER | AMBER | AMBER | N/A |  | Both vendor contracts signed. Capability development has commenced with technical difficulties in integration to Victoria Police data being identified and resolved. Full scope and device rollout remains on target for 30 June 2019, in advance of the completion of the overall package. After completion of the project, additional devices and additional capacity will continue to be added under Business As Usual processes. | 2017-03-31
Q3-2016-17 | 96298933-1BE6-432C-8592-DE0D8059B6EB | Victoria Police | VicPol | BlueConnect - Intelligence Management | Law and justice | A new intelligence capability to bring together Victoria Police’s multiple data sources to deliver quick, easy access to intelligence to better inform police. | 2015-07-01 | PRINCE2 |  | In progress - implementation | 2016-06-30 | 0 | 2021-06-30 | 82644000 |  |  | AMBER | GREEN | GREEN | N/A |  | Initial Phase 1 implementation in mid-2017 considered to be at risk due to technical complexities with establishing ongoing data updates, however delivery of full capability by 2019 remains achievable. | 2017-03-31
Q3-2016-17 | DC0C1FE8-AEFA-45AB-974C-7F1EA95D950D | Victoria Police | VicPol | Body Worn Camera (BWC) | Law and justice | Victoria Police will procure and deploy BWCs capable of capturing direct and objective audio and video face-to-face interactions, in an operational context between police members and the public, and real-time capture of video evidence of the scene of an incident. | 2015-07-01 | PRINCE2 |  | In progress - implementation | 2016-06-30 | 0 | 2021-06-30 | 42591900 |  |  | AMBER | GREEN | GREEN | N/A |  | Project staff have commenced. Investigation of policy and legislation requirements and BWC product requirements has commenced. | 2017-03-31
Q3-2016-17 | 350BE61D-B129-42F0-961C-D858ED208609 | VicRoads | VicRoads | Payment Card Industry (PCI) Program | Business and industry | Vicroads has a program of works to meet the required compliance under the PCI-DSS merchant banking scheme to the 3.1 standard (moving to 3.2 August 1st 2016) | 2014-01-10 | Other – please specify | Waterfall supported by prince2 | In progress - implementation | 2015-12-24 | 600000 | 2016-11-30 | 3000000 | 2017-12-30 | 3000000 | GREEN | GREEN | GREEN | AMBER | AMBER | The project is on track for delivery in December 2017 as agreed by the Project Authority and Westpac. Work has commenced on ongoing compliance management activities to ensure PCI compliance is maintained. | 2017-03-31
Q3-2016-17 | 66415365-BA83-4FD3-A39F-C819A9411D4D | VicRoads | VicRoads | Connect - Finance and Payroll upgrade | Transport and vehicles | This project is to upgrade VicRoads core finance & payroll system to provide a supported, cost-effective system that aligns VicRoads for future change, provides opportunities for process improvement and reduces risk of system failure. | 2014-10-09 | PRINCE2 |  | In progress - implementation | 2016-02-01 | 192000 | 2017-05-01 | 5511000 | 2017-12-15 | 5800000 | AMBER | GREEN | GREEN | GREEN | N/A | The Project Authority endorsed the change in project completion date to Dec 17. This delay takes the GoLive from May 2017 to last quarter 2017. This revised timeline includes an allowance for a month post-GoLive and closure activities. The change in completion date was required due to two key factors: 1. A number of essential components for GoLive not being sufficiently advanced for UAT commencement, and 2. The 'End Of Financial Year / Finance Systems Moratorium' Period (Jun / Jul 2017) drawing key resources away from Development and Testing activities. | 2017-03-31
Q3-2016-17 | DDCE6B02-4DF3-4E93-BE4F-AD4F8B35372C | VicRoads | VicRoads | R&L IT Systems Transformation (Stage 1) | Transport and vehicles | This comprises of two components; critical remediation of current back end systems as a result of the RandL pause and cancellation; and Proof of Concept and planning to transform back end VicRoads IT systems that support registration and licencing services (R&L). | 2015-07-01 | Agile |  | Completed | 2015-11-30 | 0 | 2016-06-30 | 4500000 | 2016-09-30 | 4500000 | N/A | GREEN | GREEN | GREEN | GREEN | Project Completed | 2017-03-31
Q3-2016-17 | 06764DA4-CAB2-46AF-94D2-AFB343489106 | VicRoads | VicRoads | Asset Maintenance Reporting | Transport and vehicles | Asset Maintenance Reporting is being established to integrate various VicRoads road and asset maintenance related datasets to deliver compliance reporting and analytics that support effective road network and asset planning. | 2015-10-24 | Agile |  | In progress - implementation | 2016-11-30 | 1190000 | 2017-03-30 | 248000 | 2017-06-22 |  | GREEN | GREEN | N/A |  |  | Phase 1 ,2,3 are now complete. Project is in implementation phase. The self service portal has been developed and been through pilot. The portal to be progressively rolled out scheduled to be fully rolled out by end of June 2017. | 2017-03-31
Q3-2016-17 | 58F9F700-240D-4A11-B898-27BB1B398A3C | VicRoads | VicRoads | Electronic Document Records Management System (EDRMS) Upgrade | Business and industry | A back-end systems upgrade of VicRoads' current Electronic Document Records Management System (EDRMS) to the vendors OpenText (Content Suite). The key objectives are to provide a more robust and supported platform. | 2015-11-26 | PRINCE2 | Waterfall supported by prince2 | Completed | 2015-11-20 | 115000 | 2016-10-30 | 2150000 | 2017-02-28 | 2150000 | N/A | GREEN | GREEN | GREEN | GREEN | Project was implemented as per plan in Feb 2017. | 2017-03-31
Q3-2016-17 | 8E3DBEF4-6A94-4F88-83DE-CE4DE2EEFE39 | VicRoads | VicRoads | ICT/ITS Infrastructure Transformation | Business and industry | This project is to establish commercial arrangements for, and the transition into, new data centre hosting and managed infrastructure services to support VicRoads current and future ICT and Intelligent Transport System requirements. | 2016-05-09 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Tender period has closed and responses are being evaluated. | 2017-03-31
Q3-2016-17 | 1CB5876A-3C65-4438-9495-5EC79BD4A7C1 | VicRoads | VicRoads | R&L Digital Services Transformation (Stage 2) | Transport and vehicles | Digital Services Transformation Stage#2 continues to rollout key vicroads transactions online including Individual and partner transactions, Organisation Portal and refunds/ cancellations | 2016-05-30 | Agile |  | In progress - implementation | 2016-06-30 | 0 | 2017-06-30 | 12523000 |  |  | GREEN | GREEN | GREEN | GREEN |  | Organisation Portal testing completed, pilot to commence shortly. Build of enhanced payments capabilities complete, testing in progress. Design and build of additional enhancements to Individual and Partner transactions is in progress. | 2017-03-31
Q3-2016-17 | C5289C03-B1CD-452A-8FA6-77335FB7B9FD | VicRoads | VicRoads | R&L IT Systems Transformation (Stage 2) | Transport and vehicles | R&L IT Systems Transformation Stage#2 comprises initiation activities for the R&L Systems Back-end Transformation which includes Business Case Development for ERSC submission, Project specification and planning activities for the transformed system | 2016-07-01 | Agile |  | Initiated | [11 empty] | Business Case and Project Specification has been developed. Development of target system architecture and associated design documentation is now complete for initiation. Project estimates finalised against latest project documentation. Material for Economic Review Sub-Committee (ERSC) submission has been submitted for ERSC consideration | 2017-03-31
Q3-2016-17 | C133D9C6-7A58-4AE6-B676-6B66FB6F2B21 | VicRoads | VicRoads | Registration System Upgrades | Transport and vehicles | This initiative comprises of improvements to R&L front end and back end systems to provide improvements to customer service and payments options. | 2016-07-01 | Agile |  | In progress - implementation | 2016-07-31 | 0 | 2017-06-30 | 7350000 |  |  | GREEN | GREEN | GREEN | GREEN |  | Project is on track. Design and build activities for improved customer service and payments capabilities nearing completion. | 2017-03-31
Q3-2016-17 | DAAE32BD-136F-48C1-BCE8-719A044943E5 | VicRoads | VicRoads | Sydney Coordinated Adaptive Traffic System (SCATS) Connectivity Migration Project | Transport and vehicles | Supply, Install and Manage the communication service for all the Managed Traffic Signal Sites. Supply, Install and provide a communication service for all unmanaged Traffic Signal Sites. | 2016-09-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project progressing on track as per baselined schedule. Phase 1 (Requirements gathering and Market engagement) of the project is complete. Phase 2 - Preparation for Request for Tender(RFT) was released in November 2016 and responses received in December. Contract negotiation completed with the preferred supplier. Tender evaluation report approved and Contract awarded. | 2017-03-31
Q3-2016-17 | 02530175-FEA5-498A-AC9C-506FA050D66B | VicRoads | VicRoads | CityLink Tullamarine Widening (CTW) Section 3 Project | Transport and vehicles | This project includes the upgrade of STREAMS (core ITS system for monitoring and control of field devices installed other than traffic signals). It provides integration, testing, and configuration of ITS devices to communication network and control systems and upgrade of backend systems and infrastructure to support the managed motorway. | 2015-10-01 | PRINCE2 |  | In progress - implementation | 2016-03-01 | 238683 | 2017-12-31 | 12591000 |  | 12591000 | GREEN | GREEN | AMBER | GREEN | GREEN | Completed System Acceptance Testing (SAT) for STREAMS Enhancement Release 1. Planned deployment on 20 April 2017. Awaiting confirmation from Transurban for the solution design for STREAMS Enhanced Center to Center . Commencement of the development of testing framework. Completed procurement of fibre nodes and commencement engaging contractor to undertake Node replacement work. Road Asset Inventory System (RAI) (VicRoads' Intelligent Transport Systems device management application) Enhancement contract has been advertised in the market. | 2017-03-31
Q3-2016-17 | 15CBBB50-AF2E-42B9-AF08-181D3313D4DA | VicRoads | VicRoads | CityLink Tullamarine Widening (CTW) Section 1 & 2 Project (M80 Upgrade ) | Transport and vehicles | This project includes the integration, testing and configuration of ITS devices to communication network and backend control systems, provide upgrade of STREAMS (core ITS system for monitoring and control of field devices installed other than traffic signals) and infrastructure to support the managed motorway. | 2016-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Ongoing review of various design packages submitted by civil & ITS team. Project Initiation Document and stakeholder engagement plan is being signed off. Node procurement completed | 2017-03-31
Q3-2016-17 | 24DBC2E8-C9E8-4024-84E3-6644EA8507AD | VicRoads | VicRoads | Dynamic Variable Speed Limit (DVSL) Project - Phases 2 & 3 | Transport and vehicles | The development of a new DVSL system integrated with Coordinated Ramp Signal and Lane Use Management System to maximise freeway capacity, minimise flow breakdown and improve traffic safety in congested conditions. | 2016-06-30 | PRINCE2 |  | Initiated | [11 empty] | Phase 1 work completed, planning for the procurement of phases 2 - 3 is in progress. RFQ has been sent out to request for algorithm development work. Scope of this project is being finalised. | 2017-03-31
Q3-2016-17 | 8F2A88A3-F446-4468-858F-2D9EE0F3A80C | VicRoads | VicRoads | Monash Freeway Upgrade (MFU) Project | Transport and vehicles | The project includes the integration, testing and configuration of ITS devices to backend control systems and communication network, provides new communication network and upgrade of backend systems and infrastructure to support the managed motorway. | 2016-06-30 | PRINCE2 |  | In progress - implementation | 2016-09-30 | 0 | 2018-08-31 | 5300000 |  |  | GREEN | GREEN | N/A |  |  | Integrated program between Intelligent Transport System (ITS) and civil program is finalised and regularly updated. Review of ITS detailed design and layout design for Section 1, 2 and 3 completed. Procurement for communication network upgrade in progress. | 2017-03-31
Q3-2016-17 | 68CBA66B-61A8-46FA-B530-765A8BE1805E | VicRoads | VicRoads | Fines Reform Project | Transport and vehicles | Fines Reform is a mandatory legislative project driven by the Department of Justice and Regulation’s Infringement Management Enforcement Services. VicRoads must implement a range of system and business process changes in order to meet its legislative obligations. | 2017-01-03 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Requirement analysis are underway and will be completed by end of April. Commencing design and detailed implementation planning. | 2017-03-31
Q3-2016-17 | 53D79719-0C8E-475D-A1FA-CC76B22B27FE | Victorian Rail Track | VicTrack | VicTrack Telecommunications Service Management System (TSMS) Implementation - Phase 1 | Transport and vehicles | To implement a new service management system for the Telecommunications group to replace the existing tool that is end of life | 2014-07-01 | Other – please specify | VicTrack Project Management Framework | In progress - implementation | 2015-09-24 | 341000 | 2016-06-29 | 1405230 | 2017-11-27 | 2179896 | AMBER | AMBER | AMBER | AMBER | GREEN | Project scope changes were approved via PCR (Project Change Request) in April 2017. Reforecasting exercise is in progress to agree new completion schedule for Phase 1. Phase 2 works will be subject to a 'Go/No Go' assessment process. Project costs/dates have been updated with Phase1 initial planned figures and revised estimates (but not yet approved by VicTrack PSC). | 2017-03-31
Q3-2016-17 | E0A097AE-85FC-4CA3-A69A-D2A00D3DD23C | Victorian Rail Track | VicTrack | Network Transformation - IP/MPLS Reference Design Project | Transport and vehicles | Primary deliverable is a Reference Design that describes a future vision for a single IP/MPLS based network to replace VicTrack’s current seven Telecommunications Networks. | 2016-01-27 | Other – please specify | VicTrack Project Management Framework | In progress - implementation | 2016-12-24 | 1111512 | 2017-03-01 | 2231285 | 2017-09-30 | 4052199 | GREEN | GREEN | GREEN | GREEN | GREEN | Project has commenced evaluation of two shortlisted consortia, side-by-side. Evaluation will be based on consortia's performance during the design and testing phases of this project. There is no change to end date. | 2017-03-31
Q3-2016-17 | A7965C46-BFF4-4EBC-B7AA-C00516D1330C | Victorian Rail Track | VicTrack | Network Transformation - Analogue Gateway | Transport and vehicles | The project scope is to go through an RFT process to identify an analogue gateway device(s) that is flexible to allow combinations of different analogue interface types on as need basis. | 2016-02-02 | Other – please specify | VicTrack Project Management Framework | In progress - implementation | 2016-07-31 | 493762 | 2016-11-30 | 1834668 | 2017-04-13 | 1834668 | GREEN | GREEN | GREEN | GREEN | GREEN | The analogue gateway project has successfully completed all the planned functional and additional cyber security tests. The project will complete when the supplier contract has been executed by the preferred vendor. This is expected by mid-April 2017 | 2017-03-31
Q3-2016-17 | 3EE8F5A9-EB16-487D-8023-7BC0AF3E89F1 | Victorian institute of Forensic Medicine | VIFM | Development of a new Medico-Legal Case Management System | Law and justice | The VIFM ICT department is designing and developing a medico-legal case management system.. The system will be capitalised as an Intangible asset when complete. The system will be deployed at the VIFM and will be provided to the Coroners Court of Victoria under licence. | 2014-12-01 | Agile |  | In progress - implementation | 2015-05-15 | 0 | 2016-08-31 | 710000 | 2017-06-30 | 1250000 | GREEN | N/A | N/A | N/A | N/A | This in-house system has been designed using VPS and agency staff employed by VIFM. The original system was built with a workflow management module to allow for the development of predefined workflows as part of the BAU post implementation stage once the base system is completed. The system at a cost of $710K was completed on time and on budget. A delay in roll-out of the system allowed for the development of 34 predefined workflows to be included in the system before it is capitalised. At the pre-implementation phase, this development work was planned to be undertaken as part of BAU on an ongoing basis and would not be part of the capitalised developed software. As the system has not yet been capitalised as an intangible asset, we are able and will be required to fully capitalise all the cost of development including the 34 workflows in accordance with accounting standard AASB 138. (subject to VAGO audit) hence the revision in cost and identification that this project now falls within reporting scope. | 2017-03-31
Q3-2016-17 | 9B79AB3D-E162-4537-A2BF-27552C85CFDA | Victoria Legal Aid | VLA | Mobile Workforce (Desktop Replacement) | Law and justice | Replacement of current computer, iPad and PABX with single device | 2015-07-01 | PRINCE2 |  | Completed | 2015-11-30 | 150000 | 2016-08-30 | 1480000 |  |  | N/A | N/A | GREEN | GREEN | GREEN | The project has been completed and closed. | 2017-03-31
Q3-2016-17 | CB1A0B60-3D33-481E-831B-9EFAB2DEFE14 | V/Line pty Ltd | V/Line | V/One Phase 2 | Transport and vehicles | Implementation of HSE, Contract Management and Project Management into V/Line's ERP system | 2014-04-01 | Agile |  | In progress - implementation | 2015-06-30 | 11300000 | 2016-12-30 | 3455000 | 2017-08-30 | 11500000 | AMBER | GREEN | GREEN | GREEN | GREEN | Revising Employee Self Service (ESS & MSS) Module | 2017-03-31
Q3-2016-17 | 9683AA7B-6F46-4705-A126-D1C60D4E1BE2 | V/Line pty Ltd | V/Line | Budgeting and Forecasting Tool | Transport and vehicles | Budget & Forecast tool, fixed, locked and monitored financial model over a period of future years, integrated with core ERP system. | 2016-04-30 | Agile |  | In progress - implementation | 2016-04-30 | 0 | 2017-06-30 | 1200000 | 2017-05-31 | 1500000 | AMBER | GREEN | GREEN | GREEN | GREEN | Revising Business Requirements & Deliverables | 2017-03-31
Q3-2016-17 | 8BED38EF-FE3E-4495-BC7E-F3FA2C3D2C01 | V/Line pty Ltd | V/Line | Rail Information and Operations System | Transport and vehicles | Replacement of scheduling, rostering and day of operations system | 2016-06-15 | Other – please specify | Not Yet Known | Postponed | [6 empty] | N/A |  |  |  |  | Revising Business Requirements & Deliverables | 2017-03-31
Q3-2016-17 | 51F0DD75-C48D-4116-BC1B-B746A0B52B18 | Victorian Managed Insurance Authority | VMIA | DBI IT Platform upgrade | Government and economy | Upgrade of VMIA's Domestic Building Insurance claims and policy management system. The upgrade is being undertaken to drive improvements and efficiencies through the delivery of an integrated technology platform for the distribution and management of domestic building insurance. | 2016-04-19 | Other – please specify | Waterfall | In progress - implementation | 2016-10-30 | 65000 | 2017-07-01 | 1783683 |  |  | GREEN | GREEN | GREEN | GREEN |  | Current development progressing to plan and solution has entered User Acceptance Testing. Planned implementation costs include 3 years of SalesForce licences and Year 1 development costs. | 2017-03-31
Q3-2016-17 | E3E19E82-6DBC-4C66-9766-04CE45D2DB0C | Victorian Ports Corporation Melbourne | VPCM | Vessel Traffic Services Resilience Improvements | Transport and vehicles | Resilience critical replacement of two existing Vessel Traffic Services Radars and Voice Data Recorders. It is expected that the replacements will enhance VPCM's capability in delivering Vessel Traffic Services. This project precedes the Vessel Traffic Services Systems Upgrade project. | 2015-02-11 | Other – please specify | VPCM (PMBoK) | Completed | 2015-10-19 | 60000 | 2016-09-30 | 1700000 | 2016-09-30 | 1700000 | GREEN | GREEN | GREEN | GREEN | GREEN | Project is now complete. Installation and integration with the existing system completed and have been functioning satisfactorily. Project close out process with project capitalisation now underway with Gate 6 Benefit Realisation to be completed and signed-off. | 2017-03-31
Q3-2016-17 | C0981DCE-AC0C-4F97-AB34-E1A5835C8179 | Victorian Ports Corporation Melbourne | VPCM | Vessel Traffic Services Systems Upgrade | Transport and vehicles | Replacement of existing / ageing Vessel Traffic Services Information Communications Technology systems with a focus on upgraded system integration, redundancy and disaster recovery. Affected systems include radio, telephony, radar, vessel AIS (Automatic Identification System), vessel DUKC (Dynamic Under-Keel Clearance), CCTV and Met Ocean (tide, wind, wave and weather). | 2015-12-03 | Other – please specify | VPCM (PMBoK) | In progress - pre-implementation | [11 empty] | Project has been initiated and has achieved concept approval. The pre-implementation phase of the project has now commenced - A Project Consultant has been appointed and the process of documenting the business and technical requirements for the project has progressed. A two stage procurement commencing with an expression of interest will allow a shortlist to be selected from competent and experienced vendors who will then be offered the RFT to bid for he works. The implementation phase of the project is currently scheduled for commencement from FY2017-18. Planned implementation stage end date is currently scheduled for late FY2018-19. Current project budget is $8.2m. | 2017-03-31
Q3-2016-17 | 497B1254-6F84-40F4-B994-6F6126E46989 | Wannon Region Water Corporation | Wannon Water | IT Infrastructure Upgrade | Environment and water | To ensure currency and to provide adequate computing capacity and storage platform for WW business systems | 2016-01-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | The project is at the option investigation stage. Options for reducing the project costs through the use of Cloud solutions are being investigated. | 2017-03-31
Q3-2016-17 | 78565F2D-B3FE-44E5-8E29-2D3EF03A3A0E | Western Health | WH | Western Health Electronic Medical Record (EMR) Project | Health | Implementation of the Statewide Electronic Medical Record (EMR) Solution to provide a clinical information system for the hospital | 2016-08-19 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project pre-implementation and planning activities are progressing to schedule | 2017-03-31
Q3-2016-17 | AF619CB7-77DB-495D-BE54-9B4ED4B62D2D | William Angliss Institute | WAI | Access Angliss | Education | Project is to mature e learning offerings and delivery for the Institute by uplifting the Information Technology infrastructure foundation underpinning the Institute's delivery and administration, and also upgrading e-learning tools and staff capacity and capability in utilising these tools | 2015-06-30 | Other – please specify | Streamlined Prince2 | In progress - implementation | 2015-09-30 | 0 | 2016-06-30 | 4955000 | 2017-06-30 | 4955000 | AMBER | AMBER | GREEN | GREEN | GREEN | The previous issues of integrating multiple systems on a single platform has been resolved by assigning the project to more appropriate and senior resources. WAI has created it's own ADFS Server and have successfully implemented Single Sign On against it's Student portal and linking to the Moodle(s). This has been done in a test environment and the mapping of user groups and study modules are currently being undertaken in order to move to the production environment for full sign off. | 2017-03-31
Q3-2016-17 | 5F80910B-8B8A-4A46-B3DA-2D2D5D02CFBC | WorkSafe Victoria | WSV | VMware 5 Migration | Government and economy | The VMware 5 project is upgrading the Virtualisation Server Platform (VMware) from a mixture of older non supported software versions to a current vendor supported software version. | 2014-07-01 | PMBoK | NA | Completed | 2015-11-30 | 597295.47 | 2016-09-30 | 884383 | 2017-03-31 | 1098383 | N/A | GREEN | GREEN | GREEN | GREEN | The project has successfully completed. | 2017-03-31
Q3-2016-17 | C985DC72-C877-475A-9189-AA80C5D7B729 | WorkSafe Victoria | WSV | Integration Platform Refresh for WorkSafe | Government and economy | The Integration Platform Refresh project will upgrade the platform to the latest vendor-supported versions of the Integration Services Platform. | 2014-07-01 | PMBoK | NA | Completed | 2015-08-31 | 620089.13 | 2016-06-30 | 313437.2 | 2016-07-31 | 573999.2 | N/A | GREEN | GREEN | AMBER | AMBER | The project has successfully completed. | 2017-03-31
Q3-2016-17 | DDF6B9FA-8C1A-4FF8-9D9C-45F701F7C75F | WorkSafe Victoria | WSV | Portal & Intranet Services Upgrade Project | Government and economy | The project will upgrade the legacy IBM Portal, Intranet and Web Content Management systems to supported products and platforms. | 2014-07-21 | PMBoK | NA | Completed | 2016-04-30 | 323226 | 2016-12-31 | 728834 | 2017-02-28 |  | N/A | GREEN | GREEN | GREEN | GREEN | The project has successfully completed. | 2017-03-31
Q3-2016-17 | 4CA01AF3-5A25-497D-B379-FF49A9DEFC18 | WorkSafe Victoria | WSV | WebSphere Application Platform Refresh | Government and economy | The upgrade of IBM WebSphere Application Server software platforms to the latest supported version. | 2014-09-01 | PMBoK | NA | Completed | 2015-08-31 | 713847.43 | 2016-10-31 | 792135.51 | 2017-03-31 | 1217167 | N/A | GREEN | AMBER | GREEN | AMBER | The project has successfully completed. | 2017-03-31
Q3-2016-17 | AC034513-A73B-4CA5-89C8-C0C9F3C4D626 | WorkSafe Victoria | WSV | Agent Contract 2016 | Government and economy | WorkSafe's is renewing the contract with it's Insurance Agents. | 2014-10-01 | PMBoK | NA | Completed | 2016-03-31 | 306903.71 | 2016-09-30 | 1325269 |  |  | N/A | GREEN | GREEN | GREEN | GREEN | The project has successfully completed. | 2017-03-31
Q3-2016-17 | ECE53766-9848-46FA-99E9-DF0BF34EA8FE | WorkSafe Victoria | WSV | Enterprise DB Rationalisation (S2) | Government and economy | The project will upgrade the legacy hardware and software database platforms to current vendor supported platforms. | 2014-12-01 | PMBoK | NA | Completed | 2016-01-31 | 902808.1 | 2016-07-30 | 1765203.83 |  |  | N/A | GREEN | GREEN | GREEN | GREEN | The project has successfully completed. | 2017-03-31
Q3-2016-17 | C3727867-4771-40CB-94A3-D1BFBAA10C87 | WorkSafe Victoria | WSV | TRACCtion (WorkSafe ACCtion Replacement Project) | Government and economy | The feasibility study and high level planning for the possible transition off WorkSafe's Mainframe legacy systems. | 2015-12-01 | PMBoK | NA | Completed | 2016-09-29 | 0 | 2016-09-30 | 1483736 |  |  | N/A | GREEN | GREEN | GREEN | GREEN | The project has successfully completed. | 2017-03-31
Q3-2016-17 | 226212B6-FB10-429D-B510-EEE51B71F2A5 | WorkSafe Victoria | WSV | Digital Claims File | Government and economy | The electronic document management system which is currently used for Invoices and Certificates of Capacity will be expanded to include all other Claims File documents. | 2015-07-01 | PMBoK | NA | In progress - implementation | 2016-08-31 | 1246158 | 2017-12-31 | 4753842 |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | The project is tracking to plan. The 20 March 2017 technical go live was successful. The Release 1 documents successfully released into production. | 2017-03-31
Q3-2016-17 | 09B42D4B-6916-42A9-890C-305AF3B2C8AE | WorkSafe Victoria | WSV | End User Computing (EUC - Application Remediation) | Government and economy | To undertake Application Remediation activities, and design and implementation of 2 foundation services - secure network connectivity to Office 365 and identity management enabled as a part of the lifecycle replacement program of works. | 2016-09-01 | PMBoK | NA | In progress - implementation | 2017-03-31 | 457000 | 2017-06-30 | 931188 |  |  | AMBER | N/A | N/A | N/A | N/A | Project is waiting the completion of Data Services by Telstra who are tracking 8 weeks behind the agreed and planned completion date. However, 28th April implementation status is 'GREEN'. | 2017-03-31
Q3-2016-17 | 5884FC74-66D3-4FCD-B1F0-A6F6DCCB2DDA | Yarra Valley Water | YVW | Project ENGAGE | Environment and water | Implementation of an Integrated Contact Centre Service to provide Yarra Valley Water customers with a choice of contact channels. | 2015-04-24 | PRINCE2 |  | In progress - implementation | 2016-04-01 | 347000 | 2016-09-30 | 1422900 | 2017-05-30 | 1563900 | AMBER | AMBER | AMBER | AMBER | GREEN | Customer communication channels by phone (including self-service options) and e-mail have been delivered and are operating as planned. Web chat and SMS communications will be delivered in May to complete the project. Benefits of the new Contact Centre platforms are already being realised. A comparison of the January – March quarter of 2017 to our historical average, shows that the time to respond to customer e-mails has reduced by 67%. | 2017-03-31
Q3-2016-17 | A1F0BB0F-0CFD-45DF-9086-6CE531C56C9F | Yarra Valley Water | YVW | Customer Communication & Management (CC&M) Phase 3 | Environment and water | Implement in-house production of bills ready for print to reduce the dependency on external providers. | 2015-06-26 | Agile |  | Completed | 2016-01-26 | 0 | 2016-06-24 | 1102800 | 2016-11-17 | 841200 | GREEN | GREEN | GREEN | GREEN | GREEN | The core purpose of the project was to provide YVW with greater control over changes to bills and letters sent to customers, and these were delivered in June 2016 (bills) and November 2016 (letters). The functionality to archive and retrieve originals of customer communication has broadened to address a wider business need and has therefore been descoped from this project and is being run separately. The budget ($967k) for the two projects is still less than original combined budget ($1,103k). | 2017-03-31
Q3-2016-17 | A6CE860F-C61C-4EAE-B20D-F57BF53D9CA4 | Yarra Valley Water | YVW | Upgrade Yarra Valley Water Website | Environment and water | Upgrade the YVW Website to resolve technical limitations, meet regulatory requirements, mitigate security risks, adopt a platform that supports responsive design, and improve website functionality. | 2015-07-27 | Agile |  | Completed | 2016-07-05 | 561000 | 2016-11-01 | 1303000 | 2016-10-27 | 647607 | GREEN | GREEN | GREEN | GREEN | N/A | Website implementation is now complete providing a more useful, relevant and easier engagement channel for our customers (i.e. extensible, can be used on mobile devices). It is compliant to regulatory requirements and reduces work effort to manage content. A significant saving has been made on the development effort by utilising less resources than planned | 2017-03-31
Q3-2016-17 | 974BF457-F585-460B-90A4-506248FADAF3 | Yarra Valley Water | YVW | Trade Waste Management system | Environment and water | Create a new system for managing sewer quality and trade waste agreements | 2016-05-04 | Agile |  | In progress - implementation | 2016-11-30 | 404714 | 2018-07-18 | 2006304 |  |  | GREEN | GREEN | GREEN | GREEN | N/A | The first stage of development is in progress with implementation of Greasy Waste scheduled for June 2017 | 2017-03-31
Q3-2016-17 | E83A9962-05CC-4377-9EB2-1556EC70558C | Emergency Services Telecommunications Authority | ESTA | Multi-Agency Communications Gateway | Emergencies and safety | Delivery of a common interface with ESTA's Computer Aided Dispatch (CAD) system to improve operational dispatch data flow between ESTA and the Emergency Services Organisations, particularly to facilitate mobile devices in the field. | 2016-05-01 | Other – please specify | ESTA Project Management Methodology | In progress - pre-implementation | [11 empty] | An initial requirements review has been conducted. The solution sought will be agency neutral. Detailed design workshops have commenced. | 2017-03-31
Q3-2016-17 | 1E2E4EA4-B729-40AA-874F-FEC6177162EE | Victorian Registration and Qualifications Authority | VRQA | VRQA State Register CRM Upgrade | Education | The State Register system is used by the VRQA for the registration of education and training providers, including schools, Vocational Education and Training, and Overseas Secondary Student Exchange Organisations. The project aims to upgrade the current CRM platform to provide improved functionality to support the VRQA’s ongoing business functions. | 2014-06-16 | PRINCE2 |  | In progress - implementation | 2017-03-31 | 634657 | 2017-08-01 | 1371024 |  |  | GREEN | N/A | N/A | N/A | N/A | Project activities have progressed to plan. Design and development has been completed and User Acceptance Testing is progressing. | 2017-03-31
Q3-2016-17 | 9E7A0013-0E70-496E-B229-2FA0B18A7599 | Victorian Registration and Qualifications Authority | VRQA | EPSILON | Education | The EPSILON project will replace the existing legacy system "DELTA" to enable VRQA to meet its legislative obligations with respect to apprentices and trainees. | 2014-07-07 | PRINCE2 |  | In progress - implementation | 2016-02-29 | 373000 | 2016-08-22 | 2310749 | 2017-07-17 |  | RED | AMBER | RED | GREEN | GREEN | Project is in the final stage of Testing. Ongoing delay in the implementation of the Commonwealth’s Australian Apprenticeships Management System (AAMS) has impacted the implementation of EPSILON. As AAMS will not be available until Nov 2017, the EPSILON project will be completed as far as possible and will then go on hold until AAMS is available. | 2017-03-31